## KGMeCommerceTaggingActiveResul
ID | eCom Tag | POS Tag | Tags | Job Name | SH Project Manager | Status | Key Go Live Date | Key Go Live Status | Days since Active | Joint/Standalone | CS Executive Update | CS Kick Off Date | SH Functional Lead Consultant | POS Lead | Ecom Lead | SH Practice Lead | Go Live | Remaining work | CS Revised Target Go Live Date | CS Estimated First Go Live | Internal ID | Actual Duration (Days) | Adjusted Duration (Days) | Clock | Class | Customization | Requires Testing (to be confirmed) | Logged Task?
J869107 | #SCMA-PLUSCUSTOMIZATION |  | #SCMA-PLUSCUSTOMIZATION | Show Cats, LLC - Professional Services : Activation - SuiteSuccess for SuiteCommer | Noya, Maria | In Progress | 2023-04-29 | Revised | 362 | Standalone | #SCMA-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) May 18th 2023 - we will close on expiry date - May 28th April 21st 2023 - MN: Website is still too slow - when this is solved we are ready for go live April 13th 2023 - MN: Working on last issue : website is too slow. When this is fixed we'll go live. Feb 14th 2023 - MN: Customer is working in UATs , getting the payment processor and last adjustments Jan 18th 2023 - MN: Customer is working in UATs and getting the payment processor ready December 27th 2022 - MN: UATs Nov 4th 2022 - MN: Walkthrough - working on configurations October 17th 2022 - MN: Offline configurations. Working on customizations. October 2nd 2022 - MN: Offline configurations. Working on customizations. September 18th 2022 - MN: had personalization session. Doing offline configurations. September 5th 2022 - MN: Personalization session scheduled for this week. August 18th 2022 - MN: Kicked off and client enabled features and installed bundles. Waiting on the client setting up subdomain to work on. July 29th 2022 - MN: Waiting on an answer for the client to kick off. July 16th 2022 - MN: Waiting on an answer for the client to kick off. July 2nd 2022 - MN: Waiting on an answer for the client to kick off. June 19th 2022 - MN: Had Sales to PS KT. Waiting on client to give tentative time slots for kickoff June 5th 2022 - MN: Sales to PS KT scheduled for Monday 6th June | 2022-08-04 | Noya, Maria |  |  | Bazzani, Emiliano |  | -5.75 | 2023-04-29 | 2023-03-31 | 128379955 | 0 | 0 | 294.35 | AMO
J894949 | #SCMA-PLUSCUSTOMIZATION |  | #SCMA-PLUSCUSTOMIZATION | Colex Finishing Solutions - Professional Services : Activation - SuiteSuccess for | Kayastha, Piyush D | In Progress |  |  | 177 | Standalone | #SCMA-PLUSCUSTOMIZATION 12/14/2022 - PK - Internal Sales to PS KT completed. Customer has not yet reviewed/signed SOW 12/15/2022 - PK - Meeting with Jory at Mibar 12/22/2022 - PK - Follow up with sales team for POCs 1/12/2023 - PK - Additional job assigned J901093. Also Jory indicates meeting with the client. 1/16/2023 - PK - Ilan assigned as Dev 1/30/2023 - PK - Followed up with Jory on status of SOW and POC's 2/8/2023 - PK - Followed up with Jory, 3/29/2023 - PK - Followed up with Jory, AMO & DL | 2023-04-18 | Kayastha, Piyush D |  |  | Bazzani, Emiliano |  | 4.5 |  |  | 138936967 | 0 | 0 | 37.35 | New Business
J895968 | #SCMA-PLUSCUSTOMIZATION |  | #SCMA-PLUSCUSTOMIZATION | Srooc Holdings, LLC - Professional Services : Activation - SuiteSuccess for SuiteC | Villa, Myr Angeli | In Progress | 2023-05-31 | Original | 176 | Standalone | #SCMA-PLUSCUSTOMIZATION (tracking tag do not delete) 5/19/23 MV - Pending customer sign off for UAT completion. 4/17/23 MV - UAT is in progress. 3/17/23 MV - FRD Price Sheets menu have already sent to the customers for sign off. 03/10/23 MV - On going personalization sessions 2/28/23 AVV - Setting to In Progress to allow time entries to flow through OA 2/10/23 - Currently encountering an issue with bundle installation 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. 12/16/22 - Sales to PS KT Set |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 8.75 |  | 2023-05-31 | 139039014 |  |  |  | AMO
J868979 | #SCMA-CUSTOMIZATION |  | #SCMA-CUSTOMIZATION | Show Cats, LLC ¦ Implementation Service - Fixed Bid | Noya, Maria | In Progress |  |  | 365 | Standalone | #SCMA-CUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) May 18th MN: will request an extension Feb 14th 2023 - MN: Customization READY - Waiting on implementation UATs to be over to go live. Jan 18th 2023 - MN: Customization READY - Waiting on implementation UATs to be over to go live. December 27th - MN: Customization READY - Waiting on implementation UATs to be over to go live. October 17th 2022 - MN: Offline configurations. Working on customizations. October 2nd 2022 - MN: working on the customization. September 15th 2022 - MN: We are working in the final FRD, Developer started building the basics of the customizations in the meantime. September 5th 2022 - MN: We have a draft for the FRD, Developer started building the basics of the customizations while waiting for customer to create a subdomain. August 18th 2022 - MN: First draft of FRD July 29th 2022 - MN: Waiting for kickoff to start. July 16th 2022 - MN: Waiting for kickoff to start. July 2nd 2022 - MN: Waiting for kickoff to start. June 19th 2022 - MN: Had Sales KT to PS. Waiting for kickoff to start. June 5th 2022 - MN: Sales KT to Ps scheduled for Monday June 6th | 2022-08-05 | Noya, Maria |  |  | Bazzani, Emiliano |  | -4 |  |  | 128367338 | 0 | 0 | 293.35 | AMO
J895955 | #SCMA-CUSTOMIZATION |  | #SCMA-CUSTOMIZATION | Srooc Holdings, LLC ¦ Consulting Time | Villa, Myr Angeli | In Progress |  |  | 176 | Standalone | #SCMA-CUSTOMIZATION (tracking tag do not delete) 5/24/23 MV: Sent an email to customer for project closure approval before 5/30. Refer to J895955 for details |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | -2.75 |  |  | 139037310 |  |  |  | AMO
J901093 | #SCMA-CUSTOMIZATION |  | #SCMA-CUSTOMIZATION | Colex Finishing Solutions ¦ Implementation Service - Fixed Bid | Kayastha, Piyush D | In Progress |  |  | 140 | Standalone | #SCMA-CUSTOMIZATION |  | Kayastha, Piyush D |  |  | Bazzani, Emiliano |  | 75 |  |  | 141117412 |  |  |  | New Business
J880694 | #SCMA |  | #SCMA | Digital Academy - #SCMA : Activation | Joshi, Aarti | Closed - Lost (Rev Rec by Finance) | 2023-01-02 | Original | 276 | Standalone | 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. #SCMA (Tracking tag - Do Not remove). Job email: messages.NLCORP.522790109.2df4e01f52@nlcorp.email.netsuite.com 09/30/2022 AJ: personalization sessions are completed and client is waiting for the payment gateway integration to start the UAT. Integration is not started yet. 08/26/2022: Kick off call completed today received domain information My Account deployment is completed Next Step - Schedule PS session |  | Joshi, Aarti |  |  | Villaverde, Alfredo |  | 10 |  | 2023-01-02 | 133434383 |  |  |  | New Business
J896765 | #SCMA |  | #SCMA | Fitness Ventures International, LLC ¦ MyAccount Activation - SuiteSuccess | Zettler, Mark J | In Progress |  |  | 173 | Joint | 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. #SCMA email tag: messages.NLCORP.534973325.604874fa3e@nlcorp.email.netsuite.com Associated with job: J896675 Fitness Ventures International, LLC ¦ SuiteSuccess SuiteBilling & RM & P2P ¦ FB 1/4/2023 MJZ: sales KT held. 12/21/2022 MJZ: welcome email went out for this and associated job | 2023-01-10 | Villa, Myr Angeli |  | Bazzani, Emiliano | Haid, Elyse |  | 16.5 |  |  | 139276407 | 0 | 0 | 135.35 | AMO
J917239 | #SCMA |  | #SCMA | KBRA Holdings, LLC - Professional Services : Activation - SuiteSuccess for SuiteCo | Blakely, Mike | In Progress |  |  | 28 | Standalone | #SCMA (tracking tag DO NOT DELETE) 5/10/23 - kcristobal - KT done. Welcome email sent. 5/4/23 - kcristobal - KT scheduled |  | Blakely, Mike |  |  | Cristobal, Kevin S |  | 20.5 |  |  | 147942632 |  |  |  | AMO
J892082 | #SCMA |  | #SCMA | Trace3, Inc. - Professional Services : Activation - SuiteSuccess for SuiteCommerce | Onkka, Brady | In Progress | 2023-06-27 | Revised | 196 | Standalone | #SCMA. (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 5/18/23 - BO - Client has confirmed that all technical blockers for SCMA launch have been addressed. Client is currently working through some internal reviews and fine tuning of the site. Expected launch date is in late June. Will need an additional overage to cover hours spent chasing issues and escalations. Moving relationship back to Yellow. 4/18/23 - TK - Approved overage (6h) 4/14/23 - BO - SS4C Project effectively on hold due to desired customizations and various SSO issues encountered. Customer is focusing on SCMA and most hurdles for that implementation have been addressed. Current concerns center around migrating to production and issues with transaction history. SSO issues appear resolved. 4/4/23 - BO - Updating Relationship triggers to reflect current escalations and overage request to cover hours linked to escalations. Client wanted to be live last month at the latest. 2/9/23 - BO - Client has 5 customizations they are looking at between ERP and eCom to make this project successful. Currently pending call with client and our dev teams. Once complete we can move straight to Enable/Testing. 11/29/22 - Initial Site setup. Ideally call with client to review SCMA vs SC later this week. | 2022-11-29 | Onkka, Brady |  |  | Bazzani, Emiliano |  | 2.25 | 2023-06-27 | 2023-03-22 | 138093763 | 0 | 0 | 177.35 | AMO
J877084 | #SCMA |  | #SCMA | Asure Software : #SCMA Activation | Joshi, Aarti | In Progress | 2023-06-05 | Revised | 307 | Standalone | 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. #SCMA (Tracking Tag - DO NOT REMOVE) Job email: messages.NLCORP.519783694.dc1fa0f3fb@nlcorp.email.netsuite.com 05/15/23 Client is not moving forward with CO and working on UAT testing (payment process test for each subsidiary) once it is tested then ready for Go Live. It's scheduled for 5th June. J886574 is updated with SOW Expiry date as 09/30 04/21/23: Sent an estimates to implement requested requirement and waiting for client confirmation to move forward. 03/29/2023: Client is looking for additional requirement to display JE entries in My account section and pushed Go live date until this is solved. Sent an estimated efforts or cost to implement this change and waiting for client response. 11/29/2022: Sent follow-up email to client. 11/22/2022: Client is working on Payment Gateway config for other two subsidiary and UAT execution. Everything is setup for launch, once UAT is completed and payment gateway is configured for other two subsidiary. 11/01/2022 AJ: Client will be rolling out for two other subsidiary and another job #J886574 is created for another two subsidiary setup. Setup for three subsidiary completed. 10/10/2022 AJ: Personalization Session completed. 09/30/22 AJ: Domain setup , personalization sessions completed. Helped customer to configure the payment link. Currently client is doing UAT testing. Go Live date is not yet determined as they are rolling out my account for other 2 subsidiary as well. 08/01/2022 : Sales KT completed | 2022-08-23 | Joshi, Aarti |  |  | Villaverde, Alfredo |  | 2 | 2023-06-05 | 2022-08-31 | 131973823 | 0 | 0 | 275.35 | AMO
J912643 | #SCMA |  | #SCMA | TECO Pneumatic, Inc. ¦ Activation - SuiteCommerce MyAccount | Bertorelli, Yvonne A | In Progress | 2023-07-12 | Original | 58 | Standalone | #SCMA (tracking tag DO NOT DELETE) 5/24/2023 - YB - Bundles installed and site configured, waiting on the customer to complete training to kick-off personalization sessions. 4/26/2023 - YB - Kick off call with customer, they will be using this project to set up SCMA and see what it has to offer out of the box. After which the customer will customize the site before allowing their customers to access it. 4/12/23 - KSC - Welcome email sent | 2023-04-26 | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 17.5 |  | 2023-07-12 | 146052516 | 0 | 0 | 29.35 | AMO
J877320 | #SCMA |  | #SCMA | Sioux Nation Holdings, Inc - Professional Services : Activation - SuiteSuccess for | Onkka, Brady | In Progress | 2030-11-30 | Revised | 304 | Standalone | 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. #SCMA (tracking tag DO NOT DELETE) 5/9/23 - BO - Client is dealing with some testing issues (how to setup the account so that some customers can pay bills but not do re-orders. Once this is resolved, client should be ready for launch. Client has run into several issues with how they want the site to function and have been doing extensive testing with Support to address those issues. This is the main reason site has not launched by now. 4/14/23 - BO - Client is working with support to address some ACH issues as of 4/1/23. Reached out on 4/10 for an update, no response. Client is often non responsive in stretches. 3/7/23 - BO - Updating Client relationship status to Yellow due to some of the issues experienced and client going weeks to a month between responses. 3/7/23 - BO - Client has been running into testing issues with ACH due to pre-existing orders are no longer appearing within My Account. Client has requested I create a support case due to their issues submitting cases. Case 5087189 submitted. Once issue resolved we can hopefully proceed to launching site. 12/2/22 - BO - Updating launch date to 2030 as client is still running into some issues on their/erp side that are blocking launch. don't know when they will go live. 10/26/22 - BO - Spoke with client and assisted in updating some products. Client has one final issue with support to resolve around customer center roles, and their IT team has located the cause of the access issue. Issue is due to an old server and they are looking into a solution. 9-30-22 - BO - Client working with Support on some issues. 9/23/22 - BO - Client running into issues testing with their accounts, unsure cause. Client still unable to access from their work. Client still waiting on SoluPay to setup online profile. Moved start date to unknow. 9/2/22 - BO - Client confirmed they are still having IT issues with their office setup blocking the site. They believe the issue is now located and they are working to address. Delaying launch by another week as a result. 8/17/2022 - BO - GR4C and PS1 complete. Client working on the site, however, their IT setup is blocking access to their site. Client has requested to extend their go live by a possible week as a result. 7/29/22 - Sales to PS KT done; welcome email sent |  | Onkka, Brady |  |  | Cristobal, Kevin S |  | 5.5 | 2030-11-30 | 2022-08-31 | 132034195 |  |  |  | AMO
J917200 | #SCMA |  | #SCMA | Epicuren Discovery - Professional Services : Activation - SuiteSuccess for SuiteCo | Blakely, Mike | In Progress |  |  | 29 | Standalone | #SCMA Tag: messages.NLCORP.552878639.09dd884c1e@nlcorp.email.netsuite.com 5/18/23 mblakely welcome email set to client - will get kickoff scheduled |  | Blakely, Mike |  |  | Bazzani, Emiliano |  | 20.75 |  |  | 147937165 |  |  |  | AMO
J902562 | #SCMA |  | #SCMA | Harbinger Medical Group LLC - Professional Services : Activation - SuiteSuccess fo | Noya, Maria | Assigned | 2023-05-08 | Original | 122 | Standalone | #SCMA (tracking tag DO NOT DELETE) April 21st 2023 - MN: Found issues on the payment processor set up while testing- Freedom pay is working on it April 13th 2023 - MN: Had customization done so customers can see the sub customer info when logged in. We are testing if they can also pay the sub customers invoices. Customer is going to test the customization and is doing UAT for the site. March 13th 2023 - MN: Had personalization sessions, walkthroughs, now customer is in UAT. We found a gap with the sales process - they expected to see all subcustomer info from main customer login Feb 14th 2023 - MN: had KT and getting started session with customer. Waiting on customer to choose and get the domain. | 2023-02-28 | Noya, Maria |  |  | Cristobal, Kevin S |  | 0.25 |  | 2023-05-08 | 142216294 | 0 | 0 | 86.35 | New Business
J897198 | #SCMA |  | #SCMA | Advanced Pump & Equipment Inc. - Professional Services : Activation - SuiteSuccess | Bertorelli, Yvonne A | In Progress | 2023-07-26 | Revised | 168 | Standalone | #SCMA (tracking tag DO NOT DELETE) 5/24/2023 - YB - No progress on this job, I will reach out to the customer one more time then move this to delayed. 4/26/2023 - YB- This project is stalled, the customer seems to have no availability to move forward. 4/12/2023 - YB - Customer seems to have limited bandwidth to keep this project moving. 3/27/2023 - YB - Customer has not started training, will move launch out to May. 3/17/2023 - YB- Customer is very hard to get a hold of. I have emailed three times regarding our staging domain with no response. 2/22/2023 - YB - Call with customer occurred on 2/16 - waiting on customer to provide a domain so we can get the site configured and ready for personalization sessions. 1/27/2023 - Kick off call with customer is set for 2/3 1/4/23 - Welcome Letter sent 12/16/22 - Sales to PS KT set | 2023-02-16 | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 16.75 | 2023-07-26 | 2023-05-17 | 139566841 | 0 | 0 | 98.35 | AMO
J900514 | #SCMA |  | #SCMA | Key Industries, Inc. - Professional Services : Activation - SuiteSuccess for Suite | Hopper, Yelena | In Progress | 2023-06-01 | Original | 145 | Joint | #SCMA 5/18 - client did not make a lot of progress with their data. Waiting on Brent 5/4 - still working on config and started UAT 4/21 - still working on config 3/31 - config still in progress 3/17 - config is in progress 3/3 - client and FC resource are engaged and kicked off. 2/16 - WT1 are done. introduction to FC was made today 2/7 - Placed on delayed per other project until we are closer to begin in March. 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. 1/20 - Key Implementation began. Personalization sessions completed this week |  | Joshi, Aarti |  | Bazzani, Emiliano | Rupani, Gyanesh |  | 19.5 |  | 2023-06-01 | 140801355 |  |  |  | New Business
J885873 | #SCMA |  | #SCMA | AMI Entertainment Network, Inc - MyAccount Activation - SuiteSuccess | Zettler, Mark J | Delayed - Per PS | 2023-07-03 | Revised | 240 | Joint | #SCMA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 4/27: UAT still in progress, go-live target moved to 6/1 4/6 MJZ: Customer on track for 5/1 go-live. UAT in progress 3/22 MJZ: Customer on track for 4/1 go-live. 3/10: budget consumed, scope delivered as intended, project placed on delay as we wait for other jobs to complete the overall work of the implementation (so no one accidentally books time against this job). 3/1/2023 MJZ: job status changed to delayed by PS, switching to SuiteBilling job for remainder of UAT testing/cutover/PGLS 2/8: Go-live target moved to 4/1 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. 1/4/2023 MJZ: UAT in sandbox to complete in Jan. Go-live target 3/1. | 2023-08-26 | Green, Chris |  | Bazzani, Emiliano | Haid, Elyse |  | 0.5 | 2023-07-03 | 2023-04-01 | 135546256 | 0 | 0 | -92.65 | AMO
J860844 | #SCMA |  | #SCMA | Barracuda Networks, Inc. - Professional Services : Activation - SuiteSuccess for S | Villa, Myr Angeli | Completed | 2022-09-05 | Revised | 420 | Standalone | #SCMA (Tracking tag - DO NOT DELETE) 2/23/22 - KSC - still no response from customer. Will advise AMO that the job will be closed 9/16/22 - MLV - Client became unresponsive after they went live last month. Sent a follow up to set up a weekly call to utilize the remaining hours for this job. Waiting for their confirmation on the schedule. 7/25/22 - MLV - Completed the SCMA portal implementation on SB account. Started to migrate the portal on Production account. Go live will move to Aug. 16 4/29/22 - MLV - Had GRC call (4/27). Started to work on the My Account Deployment. 4/4/22 - KSC - Sales to PS KT set |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 0.5 | 2022-09-05 | 2022-08-16 | 124435781 |  |  |  | AMO
J902889 | #SCMA |  | #SCMA | Edmundson, Inc. – DBA – Arbor Valley Nursery - Professional Services : Activation | Noya, Maria | Assigned |  |  | 120 | Standalone | #SCMA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) March 13th 2023 - MN: Waiting on customer confirmation. This job is going to be closed. FEB 28TH - MN: THIS JOB IS GOING TO BE CLOSED. THE REASON IS THE CUSTOMER PURCHASED SS4C AND SCMA AND REALIZED THEY ONLY NEEDED SS4C BECAUSE IT INCLUDED THE MY ACCOUNT SECTION. |  | Noya, Maria |  |  | Bazzani, Emiliano |  | 21 |  |  | 142334429 |  |  |  | AMO
J896027 | #SCMA |  | #SCMA | Tenable, Inc. - Professional Services : Activation - SuiteSuccess for SuiteCommerc | Villa, Myr Angeli | In Progress |  |  | 176 | Standalone | #SCMA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) Email tag: messages.NLCORP.534719110.59f1b4ebe6@nlcorp.email.netsuite.com 5/19/23 MV: Pending customer action about the progress of SCMA pre-requisites. Sent a follow up and waiting for their response. 4/17/23 MV: Pending customer action to set up the DNS provider. 3/27/23 MV: Done with GRC (3/24) 3/20/23 MV: Customer is now ready to start the implementation. Changed the status of this project to in progress. 3/17/23 MV: Put this project to delayed status. No response from the client. 3/9/23 MV: Already sent 3 follow up to confirm the GRC schedule. No response from the customer yet. |  | Villa, Myr Angeli |  |  | Bazzani, Emiliano |  | 17.5 |  |  | 139041223 |  |  |  | AMO
J871297 | #SCMA |  | #SCMA | Chommerce LLC - Professional Services : Activation - SuiteSuccess for SuiteCommerc | Noya, Maria | Delayed - Per Customer | 2023-04-27 | Revised | 364 | Standalone | #SCMA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) May 18th 2023 - MN: Will be closed on May 26th (expiry date) April 21st 2023 - MN: Waiting on customer to be able to resume implementation. Only missing that they finish UATs and we are ready for go live. April 13th 2023 - MN: Waiting on customer to be able to resume implementation. Only missing that they finish UATs and we are ready for go live. Feb 27th 2023 - MN: On hold - waiting on customer to be ready. The site is ready - but has a whole design team and they are trying to push the design and functionalities. - whenever they are ready we will be able to go live Feb 23rd 2023 - MN: On hold - waiting on customer to be ready Jan 19th 2023 - MN: Client is working on configurations and design. They are trying to push the design and functionalities. December 27th 20222 - MN: Client is working on configurations and design. They are trying to push the design and functionalities. November 4th 20222 - MN: Client is working on configurations and design. They are trying to push the design and functionalities. October 17th 2022 - MN: Client is working on configurations and design. They are trying to push the design and functionalities. October 2nd 2022 - MN: Client is working on configurations and design. They are trying to push the design and functionalities. September 18th 2022 - MN: Client is working on configurations and design. They are trying to push the design and functionalities. September 5th 2022 - MN: Client is working on configurations and design. They are trying to push the design and functionalities. August 17th - MN: Client is working on configurations and design. Will have a check in meeting on the 19th. They are trying to push the design and functionalities. July 29th - MN: Client is working on configurations and design. July 16th - MN: Client is working on configurations and design. July 2nd - MN:Client is working on configurations. Had kickoff, personalization sessions and a check in already. | 2022-06-17 | Noya, Maria |  |  | Bazzani, Emiliano |  | -2.75 | 2023-04-27 | 2023-02-28 | 128655292 | 0 | 0 | 342.35 | AMO
J917160 | #SCA-PHASE |  | #SCA-PHASE | Computers & Structures, Inc. ¦ Implementation Service - Fixed Bid | Villa, Myr Angeli | In Progress |  |  | 29 | Standalone | #SCA-PHASE2 (tracking tag DO NOT DELETE) |  | Villa, Myr Angeli |  |  | Bazzani, Emiliano |  | 27.5 |  |  | 147933391 |  |  |  | AMO
J828852 | #SCA-PHASE |  | #SCA-PHASE | Snoasis Medical LLC #SCA-PHASE2¦ Change Order | Rodriguez, Amber | Delayed - Per Customer |  |  | 680 | Standalone | 2/22/22: Customer requested to put job on hold until April due to other projects of theirs taking priority #SCA-PHASE2 (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) AR 9/22/21: meeting scheduled with customer on 9/24 to review steps for testing |  | Rodriguez, Amber |  |  | Bazzani, Emiliano |  | 26 |  |  | 103880911 |  |  |  | AMO
J882577 | #SCA-PHASE |  | #SCA-PHASE | Cancer Diagnostics, Inc ¦ Consulting Time | Noya, Maria | In Progress | 2022-12-30 | Revised | 268 | Standalone | #SCA-PHASE2 Job record tag: messages.NLCORP.524835294.82b147c179@nlcorp.email.netsuite.com MN: 21april23: Waiting for the customer to sign change order to work on the customization for the states with exceptions. MN : 13april23: Solution was accepted and works fine - scoping a change order for states with exceptions. SE: 14dec22: Solution proposed by Support did not work. Opted for manual upload of customization to SBX and Production SE: 28nov22: solution to be Demo'd on December 1st, in SBX. Deployment issue to be fixed on Dec 12th. SE: 10Nov22: change in technical lead. SE: 28Oct22: Demo for MyAccount successful. Will deploy to production SE: 14Oct22: Scheduled demo for Monday. SE: 03Oct22: Resent request for latest backup codes for NS SE: 27Sep22: Met with SP and AMO to review second customization, to be scoped in a separate SOW SE: Met client, shared first FRD draft. Client agrees with first draft SE: 06Sep22: changing status to In Progress. Scheduling Sales to PS KT meeting | 2022-09-14 | Noya, Maria |  |  | Bazzani, Emiliano |  | -0.75 | 2022-12-30 | 2022-11-01 | 133885141 | 0 | 0 | 253.35 | AMO
J885047 | #SCA-CUSTOMIZATION |  | #SCA-CUSTOMIZATION | Intermex Wire Transfer LLC ¦ #SCA-CUSTOMIZATION | Komin, Alain | In Progress | 2023-06-26 | Revised | 245 | Standalone | #SCA-CUSTOMIZATION (Tracking Tag - DO NOT REMOVE) 01/25/2023 AKOMIN: This job will be used for UAT, Go Live and Post GL activities. | 2022-08-04 |  |  |  | Villaverde, Alfredo |  | 69 | 2023-06-26 | 2023-03-01 | 135162194 | 0 | 0 | 294.35 | AMO | Custom Checkout extension | Y | N
J870243 | #SCA-CUSTOMIZATION |  | #SCA-CUSTOMIZATION | Call One, Inc. ¦ Consulting Time - 4 Customizations #SCA-CUSTOMIZATION | Komin, Alain | In Progress | 2023-05-30 | Revised | 363 | Standalone | #SCA-CUSTOMIZATION (Tracking Tag - DO NOT REMOVE) 05/02/2023 AKOMIN: Requesting a SOW extension for 6 months. 01/25/2023 AKOMIN: Meeting with Customer today to define next milestones in terms of migration to Prod and UAT. 08/01/2022 AKOMIN: Estimated Go Live date set to December 5th, 2022. 08/01/2022 AKOMIN: Today we demo to the customer: Shipping Methods filtering successfully. | 2021-07-21 | Komin, Alain |  |  | Villaverde, Alfredo |  | 36.25 | 2023-05-30 | 2022-12-05 | 128499841 | 0 | 0 | 673.35 | AMO | Create ability to create sub-customer upon account registration Create ability in My Account for parent customers to see and transact sub-customer records (Also copy price list?) | Y | N
J880260 | #SCA-CUSTOMIZATION |  | #SCA-CUSTOMIZATION | Volcafe Specialty Coffee Corp. ¦ Consulting Time #SCA-CUSTOMIZATION | Bertorelli, Yvonne A | Delayed - Per Customer | 2023-06-16 | Original | 281 | Standalone | #SCA-CUSTOMIZATION (Tracking Tag - DO NOT REMOVE) 5/2/2023 - YB - Still no word from the customer on when we can begin work. Asked AMO to reach out to the customer again. 4/4/2023 - YB - Customer continues to delay us while he works on a project in his sandbox. Suggested he get a second sandbox so we can start but he didn't want that. Last email from DL has not been answered. 11/16/2022 - YB - Customer emailed back that he will not be ready to begin this project until Mid-Feb 2023. Putting this on delayed status and will check back with him in January 2023 10/31/2022 - YB - Customer emailed back in response to an email from the AMO that they might want to include Brain Tree or After Pay as part of this upgrade. Still no date as to when we can move forward. 10/13/2022 - YB - Will reach out to the customer again next week for an update. 9/27/2022 - YB - Customer has delayed us yet again and asked for another two weeks to provide an update. That puts us to October and this SOW was only issued with 3 months. Sent extension for customer to sign. |  | Bertorelli, Yvonne A |  |  | Villaverde, Alfredo |  | 402.5 |  | 2023-06-16 | 133211996 |  |  |  | AMO
J883489 | #SCA-CUSTOMIZATION |  | #SCA-CUSTOMIZATION | Ophthalmics, Inc ¦ Consulting Time (CC Fee Customization) | Komin, Alain | In Progress | 2022-12-12 | Original | 267 | Standalone | #SCA-CUSTOMIZATION (tracking tag DO NOT DELETE) Job email: messages.NLCORP.524257183.226dc1366b@nlcorp.email.netsuite.com Main job: J883488 05/02/2023 AKOMIN: Requesting a SOW extension for 3 months. 04/25/2023 AKOMIN: Reverting solution as issues were seen in Prod. Meeting with DEV. Requesting help form a TS resource to meet with Tom and review their billing process. 24/Apr/2023 AKOMIN: Customization deployed to Production. Customer validating. 06-Apr-2023 (MC) - overage approved 2/23/23 KCRISTOAL: currently looking into how to approach a particular aspect of the requirements (assigning credit to multiple invoices); reached out to RMO for an ERP developer 2/22/22 KCRISTOBAL: Legal issues resolved a while back. Customization being tested 11/14/2022 AKOMIN: Customization is currently blocked by legal as there are US states where adding surcharges to CC and debit cards are illegal. Kevin to inform the Customer about this. 11/3/22 (MC): Approved overage |  | Komin, Alain |  |  | Cristobal, Kevin S |  | 32.75 |  | 2022-12-12 | 133961866 |  |  |  | AMO | Create an extension to add credit card fee. | Y | N
J900704 | #SCA-CUSTOMIZATION |  | #SCA-CUSTOMIZATION | 824515 Driftwood Dairy, Inc. ¦ Consulting Time | Joshi, Aarti | In Progress | 2023-06-05 | Revised | 145 | Standalone | Job Email - messages.NLCORP.537592024.200b2948ba@nlcorp.email.netsuite.com #SCA-CUSTOMIZATION 03/01/23 AJ: Customization work is -in progress. Some of requirement are implemented and reviewed by client. 02/17/23: Website has been deployed and customization work is in-progress. There are some items which are not in scope which is still in discussion with AMO/SP | 2023-01-17 | Joshi, Aarti |  |  | Bazzani, Emiliano |  | 234.75 | 2023-06-05 | 2023-04-03 | 140856065 | 0 | 0 | 128.35 | New Business | Customizations have input fields | Y | N
J831547 | #SCA-CUSTOMIZATION |  | #SCA-CUSTOMIZATION | ACG, Inc ¦ #SCA-CUSTOMIZATION NetSuite Time & Material - NEW | Bertorelli, Yvonne A | In Progress | 2030-06-05 | Revised | 653 | Standalone | #SCA-CUSTOMIZATION (Tracking tag, keep at top and don´t delete) 10/31/2022 - YB - Customer has had on delayed and has now hired a new marketing/web person. Last update is that he expects to have this tested within the next two weeks but has not indicated a date he would go live with all the changes. 1/20/22-JAL-Implementation Partially On Hold due to Customer Readiness. The customer does not have enough staff to work on the SuiteCommerce-related tasks. 10/15 SJE-- - Customization development in progress - Additional scope identified on 10/14 - custom support case creation in the MyAccount section, gathering requirements to determine an estimate 10/8 SJE -- - Development: In Progress - Go Live date adjusted to 12/15 but ACG may push to 1/11 10/1 SJE -- - T&M CO signed by ACG - waiting on job creation to complete customizations. 9/24/21 SJE -- - Dev: In-Progress - CO creation in-progress for additional hours required to complete customizations - Offline Configuration: In-Progress 9/17/21 SJE -- - Discovered the customizations will take additional time than originally proposed in the CO. Meeting with ACG on 9/20 to discuss further and determine next steps 9/10/21 SJE -- - Development: In-Progress - Theme Chosen: Threads 9/3/21 SJE -- - FRD Creation in process - 3 FRDs approved by ACG - Development: In Progress - Need to complete the remaining FRDs 8/20/21 SJE -- - New go live date of 11/16 - Possible increase in scope from ACS - Personalization sessions: complete - FDD Review to be done before 9/1 |  | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 11.75 | 2030-06-05 | 2021-11-16 | 105962924 |  |  |  | AMO |  |  | N
J865349 | #SCA-CUSTOMIZATION |  | #SCA-CUSTOMIZATION | ACG, Inc ¦ NetSuite Time & Material - NEW | Bertorelli, Yvonne A | In Progress | 2023-06-06 | Original | 388 | Standalone | #SCA-CUSTOMIZATION (Tracking TAG DO NOT DELETE) 5/17/2023 - YB - Customer is not responding again, will loop in AMO. 4/21/2023 - YB - Next call with the customer is later today, hoping for a good update as he was scheduled to start testing on 4/17. 3/30/2023 - YB - Meet with customer tomorrow to see how he is progressing with his testing of the new site. 3/10/2023 - YB - Customer is finally communicating after getting call from AMO. Resetting the job to in progress so we can resume work. Developers have already checked sandbox to make sure we are set for customer to test. 1/30/2023 - YB - Customer has not been responding to my emails, included AMO and DL on all attempts. 12/22/2022 - YB - Customer has not reached out, will touch base for an update at the beginning of the year. 11/21/2022 - YB - Customer has hired a new marketing person who he wants to be in charge of the site. This person is now taking the Webstore Administrator training in order for us to meet and do personalization sessions. 10/31/2022 - YB - Customer has had on delayed and has now hired a new marketing/web person. Last update is that he expects to have this tested within the next two weeks but has not indicated a date he would go live with all the changes. 9/27/2022 - YB - Customer has not gotten back to me so reached out again for an update. 8/15/2022 - YB - Need to check-in with Chris to see if he has started testing the new site so we can set a go live date. |  | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 23.5 |  | 2023-06-06 | 126835360 |  |  |  | AMO |  |  | N
J799565 | #SCA-CONSULTING |  | #SCA-CONSULTING | PBUCC ¦ SCA PLGS & PM | Gamsu, Abby | Monitoring - Post Go-Live | 2023-04-03 | Actual | 946 | Joint | #SCA-CONSULTING (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) 5/219/23 - ARG - Additional PGLS hours purchased to extend through mid june 4/3/23 - ARG - Client goes live for SCA 12/25/23 - ARG - SCA login page complete 12/8/22 - ARG - Nico working on SCA Login page - deliverable date of mid jan 11/30/22 - ARG - CO signed, work started on SCA Login page 11/14//22 - AGAMSU - Still waiting for client to sign CO for SCA login 10/20/22 - AGMSU - working with AMO to have SC assigned to build SOW for multiple employer login solution 09/19/2022-LAL-Internal PBUCC mtg 09/16/2022-LAL-COA/Segments discussion-Tori 09/15/2022-LAL-Begin transition to new PM, Abby Gamsu 09/14/2022-LAL-SCA Portal Weekly Mtg 09/13/2022-LAL-Weekly status mtg & weekly DM mtg & COA/Segments discussion-Tori 09/12/2022-LAL-Internal PBUCC mtg 09/08/2022-LAL-Started PM daily check-ins with customer 09/07/2022-LAL-Internal PBUCC mtg - PDF Printing 09/06/2022-LAL-Weekly status mtg & weekly DM mtg 09/01/2022-LAL-Action Item 102-PDF printing discussion/scope & PS/TS Alignment mtg 08/31/2022-LAL-SCA Portal Weekly Mtg 08/30/2022-LAL-Weekly status mtg & weekly DM mtg 08/29/2022-LAL-Internal check-in & PS & TS Alignment mtg 08/26/2022-LAL-PM/Timeline Meeting 08/25/2022-LAL-KT mtg 08/24/2022-LAL-Internal discussion on timeline/go live & Internal KT mtg 08/23/2022-LAL-Weekly status mtg & weekly DM mtg 08/22/2022-LAL-this Job J783232 reopened for planning training and training (only training hours left on the job) 08/22/2022-LAL-Internal check-in & Training Planning mtg 08/18/2022-LAL-Notification on failed Import-jess & KT for customizations (Tori/Madhav/Jess) 08/16/2022-LAL-Weekly status mtg & weekly DM mtg 08/15/2022-LAL-Internal check-in 08/12/2022-LAL-Invoice Printing discussion-Jess & Internal KT 08/10/2022-LAL-SCA Portal Weekly Mtg & Internal KT mtg 08/09/2022-LAL-Weekly status mtg & weekly DM mtg & DTP Inbound integration (Leo) 08/08/2022-LAL-Internal check-in & Credit Memo (Leo) 08/05/2022-LAL-Project plan/timeline meeting - Lisa, John & Paul B 08/04/2022-LAL-WT-Roles & Reporting-Tori 08/03/2022-LAL-SCA Portal Weekly Mtg & WT2-P2P-Tori 08/02/2022-LAL-WT2-R2R-Tori 08/02/2022-LAL-Weekly status mtg & weekly DM mtg - Customer escalation mtg 08/01/2022-LAL-Internal check-in 07/27/2022-LAL-SCA Portal Weekly Mtg 07/26/2022-LAL-Weekly status mtg & weekly DM mtg 07/25/2022-LAL-AR Aging & Interfund Walkthroughs-Tori 07/20/2022-LAL-SCA Portal Weekly Mtg 07/19/2022-LAL-Weekly status mtg & weekly DM mtg 07/18/2022-LAL-Internal check-in & Test Scenario Discussion 07/12/2022-LAL-Weekly status mtg 07/11/2022-LAL-Internal check-in 07/08/2022-LAL-DTP SFTP Import Errors-Leo 07/06/2022-LAL-SC+/Data requirements clarification & SCA Portal weekly mtg 07/05/2022-LAL-Internal check-in & weekly status mtg 06/29/2022-LAL-SCA Portal Weekly Mtg 06/28/2022-LAL-Weekly status mtg 06/27/2022-LAL-Internal check-in & SFTP Check-in 06/22/2022-LAL-SCA Portal Weekly Mtg 06/21/2022-LAL-Weekly status mtg & AR Aging touchbase 06/15/2022-LAL-SCA Portal Weekly Mtg 06/14/2022-LAL-Weekly status mtg & Batch invoice PDF script demo (Heeju) 06/13/2022-LAL-Internal check-in 06/08/2022-LAL-SCA Portal Weekly Mtg 06/07/2022-LAL-Weekly status mtg 06/06/2022-LAL-Internal KT, Consolidated invoice mtg, AR Aging Script (Tori) 06/03/2022-LAL-SFTP credentials (Leo) & Script Requirement Checkpoint (Heeju) 06/02/2022-LAL-Internal KT, Weekly Status mtg, PM Project Plan Discussion 06/01/2022-LAL-Internal check-in & SCA Portal Weekly Mtg 05/21/2022-LAL-Internal KT, replacing Jess responsibilities 05/26/2022-LAL-Weekly Status mtg 05/25/2022-LAL-Internal check-in & SCA Portal Weekly Mtg & Adv PDF Scripting Requirement Discussion 05/19/2022-LAL-Weekly Status mtg 05/18/2022-LAL-Internal check-in 05/16/2022-LAL-Adv PDF Customization Requirement Discussion & DTP - NS SFTP Set up Call-Jess 05/13/2022-LAL-Data file transmission mtg/NT 05/12/2022-LAL-Weekly Status mtg 05/11/2022-LAL-Import Check-in, Internal check-in, SCA weekly check-in, & Test Case Discussion 05/10/2022-LAL-Internal check-in 05/09/2022-LAL- Job on hold for CO completion, EUT hours left on this job 05/05/2022-LAL-Thurs weekly check-in (AI & Project plan update) & Internal responsibilities mtg 05/04/2022-LAL-Internal check-in, weekly SCA check-in & 05/02/2022-LAL-NS to OMNI Return File mtg with PBUCC Week of 04/25 to 04/29-LAL-Internal check-in, Wed weekly SCA check-in & Thurs weekly check-in (AI & Project plan update) & SFTP Discussion with Michelle Week of 04/18 to 04/22-LAL-Internal check-in, Wed weekly SCA check-in & Thurs weekly check-in (AI & Project plan update) Week of 04/11 to 04/15-LAL-Wed weekly SCA check-in & Thurs weekly check-in (AI & Project plan update) - PM KTs 04/05/2022-LAL-Changed PM to Lisa LaRocco 11/23/2021 AB: Ally Baran will be PM of this project. Need change order for new requirements. ran into issue since SOW of this job expires. Ally has submitted request to extend. #SCA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2001 0913 SM - Project going very slow as customer and the ERP team still defining how they are going to work with aging, adjustments and credit memos. Once this is defined, we will have to issue a CO for this changes and other minor visual changes. 8/13/21 SJE -- - Confirmed they will be staying with SCA on 8/13 - Sofia to create a new project plan - Kiko to work with Sofia and Nico to craft a detailed estimate of the work 8/6/21 SJE -- - ERP/SCA/PBUCC joint meeting held to discuss SCMA vs SCA --> SCMA is not a feasible solution for the PBUCC team - Kiko/Nico/Alain/Sarah to provide estimates for SCMA and SCA work to share with the team 2021 0726 SM - Customer changed their mind about the accounting process they will use and now no unapproved invoices will be needed. This decreases the risk on performance impact and project can restart. Working with the team to determine the not in scope requirements to proceed with a CO creation. ERP team is estimating a go live on 1/3/2022, we still have to determine the work pending to define the SCA timeline. 2021 0524 SM - At a point where SCA may not be a good product for the customer because of their accounting processes, that are not native in Netsuite. That process requires complex customizations on the SCA side. Customer was explained this and is currently considering changing to a more native approach on the accounting side, he is going to be back to us this week. If not possible, this project is probably going to be closed. If it continues, a change order for new requirements is going to be issued. 2021 0428 SM - Set estimated go live date without an agreement from customer. Still working on defining requirements to include on change order. 2021 0201 SM - POC in progress, total effort for development still not defined. Once POC is complete (currently blocked by lack of payment processor). Go live date not defined yet (ERP implementation also in progress), there's a change order being estimated. 2020 1217 SM - kick off was on 11/26. Gaps were discovered on it (PSER created today). Customer dissapointed regarding timeline and dependencies with ERP. Currently working on a FDD for the inovice grouping and on a proof of concept to confirm feasibility of the invoice grouping. | 2020-11-16 | Komin, Alain |  | Villaverde, Alfredo | Gupta, Nalini | 2023-04-03 | 2 | 2023-04-03 | 2021-08-02 | 83668713 | 868 | 868 | 920.35 | New Business
J823044 | #SCA-CONSULTING |  | #SCA-CONSULTING | Call One, Inc. ¦ NetSuite Time & Material - NEW - #SCA-CONSULTING | Komin, Alain | In Progress | 2023-05-30 | Revised | 730 | Standalone | #SCA-CONSULTING (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE)' 05/02/2023 AKOMIN: Requesting a SOW extension for 6 months. 01/25/2023 AKOMIN: Meeting with Customer today to define next milestones in terms of migration to Prod and UAT. 08/01/2022 AKOMIN: Estimated Go Live date set to December 5th, 2022. 1/18/22 TE -- FRD review is almost complete. Once complete, Trisha to create RoMs/COs. 12/17/21 TE -- Call One team has reviewed FRDs/microsite requirement documents and have questions for Alain - in progress. Once these are finalized, COs may be needed for some things. 11/30 TE -- Alain has completed FRDs. Reviewing with Call One team this week. 10/15 SJE -- - After reviewing FRD with dev we determined we need to break out the microsite solution into multiple FRDs, review again with dev, finalize solution with DX, and then confirm with the customer. Planning to meet with the customer to review FRDs week of 11/8 10/8 SJE -- - FRD to be reviewed by Dev and DX 10/1/21 SJE -- - FRD Creation: In-Progress 9/24/21 SJE -- - FRD Creation: In-Progress 9/17/21 SJE -- - Requirements Gathering: In-Progress - FRD Creation: Not Started 9/10/21 SJE -- - Requirements Gathering: In-Progress - FRD Creation: Not Started 9/3/21 SJE -- - Requirements gathering for microsite replacement in progress 8/20/21 SJE -- - Call One will need to purchase 2 additional licenses (Active with AMO) - Unknown how PS will re-create functionality that exists today as microsites - discovery/poc required 8/13/21 SJE -- - Waiting on licensing discussion - need the customer to purchase 2 additional licenses, AMO to provide 2 additional licenses via a CAR, or work in SB - Meeting with SR dev scheduled for: 8/18 8/6/21 SJE -- - Need 2 temporary licenses for upgrade - Requested a SR. developer to help with the analysis of the customizations on the existing site and how the microsites will be upgraded with the SCA upgrade - Meeting again on 8/23 to discuss next steps with the Call One team 7/30/21 SJE -- - Microsite review: 8/3 7/21/21 SJE -- - Kick off: complete - Potential plan to move to 1 SCA site housing leveraging PCV for microsites on Vinson site - Estimated Go Live: 11/30 pending personalization sessions 7/9/21 SJE -- - GR4C: 7/21 - Estimated go live is TBD until we have the GR4C meeting 7/2/21 SJE -- - GR4C: Postponed until 7/21 per the customer request - Estimated go live is TBD until we have the GR4C meeting 6/25/21 SJE -- - GR4C: scheduled for 7/1 - After our initial discussion there is a possibility we do not need two SCA sites - waiting to hear more from the customer on this point - Estimated go live date TBD based upon the above finding 6/18/21 SJE -- - Web admin training: in progress - Bundle provisioning: complete - configuration: in progress 6/11/21 SJE -- - KT scheduled for 6/14 | 2021-07-21 | Komin, Alain |  | Villaverde, Alfredo | Villaverde, Alfredo |  | 52.25 | 2023-05-30 | 2021-11-30 | 100049284 | 0 | 0 | 673.35 | AMO
J811395 | #SCA- |  | #SCA- | ACG, Inc ¦ #SCA-CUSTOMIZATION NetSuite Time & Material - NEW | Bertorelli, Yvonne A | In Progress | 2030-05-31 | Revised | 828 | Standalone | Check Job J811425 #SCA- CUSTOMIZATION (TRACKING TAG - DO NOT DELETE) 5/17/2023 - YB - Customer is not responding again, will loop in AMO. 4/21/2023 - YB - Next call with the customer is later today, hoping for a good update as he was scheduled to start testing on 4/17. 4/11/2023 - YB - Met with customer, he has travel over the next couple of weeks. They used a third-party consultant to assist with testing and the site in general. This is the same team that assisted with their current site so they are familiar with their business, NetSuite and SuiteCommerce. 3/30/2023 - YB - Meet with customer tomorrow to see how he is progressing with his testing of the new site. 3/8/2023 - YB - This customer continues to be non-responsive despite my multiple emails. SOW's are out for signature for the 5th time and although the AMO said he would be ready to start in March, the customer has given no timeline. AMO to call them today. 2/15/2023 - YB - Per AMO customer is now deferring to March to start working on this. Will check back at the beginning of the month. 1/30/2023 - YB - Customer is not responding to my emails for an update. I have emailed him three times and included the AMO and the DL on each. 12/22/2022 - YB - Customer has not reached out, will touch base for an update at the beginning of the year. 11/21/2022 - YB - Customer has hired a new marketing person who he wants to be in charge of the site. This person is now taking the Webstore Administrator training in order for us to meet and do personalization sessions. 10/31/2022 - YB - Customer has had on delayed and has now hired a new marketing/web person. Last update is that he expects to have this tested within the next two weeks but has not indicated a date he would go live with all the changes. 9/22/2022 - YB - Emailed customer for an update on testing but have not received a response, will try again. 8/30/2022 - YB - Customer is not ready to start testing, has been out of the office. Hope to get some kind of timeline from him on his return. 8/15/2022 - YB - Need to check-in with Chris to see if he has started testing the new site so we can set a go live date. 7/28/2022 - YB - Waiting on customer to review all customizations for upgrade to formalize a plan to migrate to production and cutover. 7/12/2022 - YB - Have a call with the customer this week to review the last customization. 6/30/2022 - YB - Will need to request an extension on this job so customer has time to test all changes with the upgraded site. 6/14/2022 - YB - Waiting on file updates to start testing and then preview with the customer. 5/31/2022 - YB - Meeting with the customer today to review customization. 5/25/2022 - YB - Working on the final customization for the upgrade. 5/9/2022 - YB - CO has been signed, awaiting assignment so we can start working on the last customization. 5/2/2022 - YB - CO was delivered to the AMO but have not heard anything more. Will check again. 4/19/2022 - YB - Customer is waiting on NS for a CO to do additional work. 3/28/2022- YB - Customer is waiting on NS for a CO to do additional work. 3/14/2022 - YB - Waiting on new SOW to go through and be signed by customer so this work can begin. 3.8/2022 - YB - Waiting on new SOW to go through and be signed by customer so this work can begin. 2.28.2022 - YB - Met with customer and found that part of the reason the project has stalled was scope that was missed for one of their most important services on the site. Sent CO and PC to AMO so this can get moving. 2.22.22 YB - Trying to get one SOW through the process before sending the second. Customer is out of town but if the one he has is signed by all parties I will send the second to get these SOW's back as I am to meet with the customer this week to get a sense of timeline and will not be able to book. 2.7.2022 - YB - Just inherited these and awaiting intro to customer so I can have a call with them. My sense is that this job should be put on delayed per customer status if they have no time to engage with us. Since their SOW expires this month I have requested a 6 month extension. Requested a PM be assigned to all these jobs as there was one prior to Patrick's departure. 1/20/22-JAL-Implementation Partially On Hold due to Customer Readiness. The customer does not have enough staff to work on the SuiteCommerce-related tasks. 10/1 SJE -- - T&M CO signed by ACG - waiting on job creation to complete customizations. 9/24/21 SJE -- - Working on new CO for customizations identified by Fede 9/3/21 SJE -- - Fede completed customization review - New CO created for customizations found on this job 8/20/21 SJE -- - New go live date of 11/16 - Possible increase in scope from ACS - Personalization sessions: complete - FDD Review to be done before 9/1 8/13/21 SJE -- - CO: Complete - Waiting for job creation an dev assignment - Waiting for SOW Extension update in NSCORP - Project plan to be created once dev is assigned 8/6/21 SJE -- - Change Order: in-progress - Personalization Sessions: 8/23 - Project Plan to be created once a developer is assigned and we can review their forecast 7/30/21 SJE -- - Intro to customer: complete - Personalization Sessions: Begin week of 8/23 - Project approach: NS PS to complete SCA upgrade and customizations, Jason B. to follow up with CO 7/21/21 SJE -- - PM Intro sent - Path forward for customizations --> change order on original SOW for customization development - Rafa to begin Personalization sessions once ACG is ready 7/16/21 SJE -- - Project PM responsibilities transitioned to Sarah Erickson |  | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 29.25 | 2030-05-31 | 2021-11-16 | 92393123 |  |  |  | AMO |  | ? | N
J869312 | #SCA |  | #SCA | McIntosh Group Inc. ¦ Implementation Service - Fixed Bid | Bertorelli, Yvonne A | In Progress | 2023-09-27 | Revised | 364 | Standalone | #SCA (tracking tag DO NOT DELETE) 5/25/2023 - YB- Customer has not been back in touch since our call, reached out again to get production account ready for us to start personalization sessions. 5/4/2023 - YB - Customer is ready to start work on SCA now, they are projecting a launch at the end of summer. 5/2/23 - YB - Call with the customer this week to discuss this project and get a timeline from them. They have decided to implement a warehouse in the UK and a WMS rather than use the warehouse in the US. Not sure what that means on the SCA side. Will request a SOW extension after that call. 4/4/2-23 - Yb - Customer seems to be redefining their business requirements, waiting for further update after internal meetings. 11/21/2022 - YB - Putting this job on delayed status since customer is not planning to get started until 2023. 11/7/2022 - YB - Customer has indicated that they will not start on this project until Q1 2023, will check back with them in January to try and get a more specific date. 10/31/2022 - YB - This customer is a small company who don't seem to have the bandwidth to begin this project. Waiting on them to let me know when we can move forward. 9/27/2022 - YB - Please see issue comments below. |  | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 176.5 | 2023-09-27 | 2023-05-18 | 128399811 |  |  |  | AMO |  |  | N
J890683 | #SCA |  | #SCA | FH Canada ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 206 | Standalone | #SCA (Tracking Tag DO NOT DELETE) job email: messages.NLCORP.531066486.acf86deed0@nlcorp.email.netsuite.com 11/18/22 - KSC - Sales to PS KT done; Welcome Email sent |  | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 909 |  |  | 137360389 |  |  |  | AMO | Credit Card Processing Gateway for webstore – up to one (1). | Y | N
J824317 | #SCA |  | #SCA | Global Link Imports ¦ Consulting Time #SCA | Komin, Alain | In Progress | 2021-10-05 | Original | 728 | Standalone | #SCA #UPGRADE (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 05/02/2023 AKOMIN: Email received from Todd explaining that they are reviewing their ship methods and that he needs a refresher on some settings. Extending SOW. Setting the job as In Progress. 03/30/2023 AKOMIN: Setting the job as Delayed Per Customer. 01/23/2023 AKOMIN: Sent a follow up email to the customer. 11/14/2022 AKOMIN: Met with Todd. Customer is thinking to not do the ShipStation integration and use native shipping methods. 11/02/2022 AKOMIN: Project was reactivated last month but the customer is not responding again. 08/22/2022 AKOMIN: Setting the job to Delayed per Customer as customer is not responding emails. 10/15 SJE -- - No show by main ShipStation subject matter experts, requirements gathering pushed to week fo 11/1 10/8 SJE -- - Requirements gathering sessions for ShipStation scheduled for 10/11 10/1 SJE -- - Successful go live - Requirements gathering for ShipStation customization tbd 9/28/21 SJE -- - Adjusted go live from 9/28 to 9/30 to give DX additional time for the migration analysis and checkpoint 9/24/21 SJE -- - Preparing for go live on 9/28 - RISK: have not received a migration analysis from DX 9/17/21 SJE -- - UAT: 75% Complete 9/10/21 SJE -- - UAT: In-Progress - Go Live Scheduled: 9/28 @ 3 pm EST 8/20/21 SJE -- - Customer would like to go live on SCA (without customizations) on 9/14 or 9/15 - waiting on final confirmation - Moving to Production by EOW 8/27 8/13/21 SJE -- - Second extension review session scheduled for 8/18 8/6/21 SJE -- - Proposed go live of 9/13 accepted by the RV Locks team - Next session: 8/18 7/30/21 SJE -- - SCA site review w/ customer: 8/6 - Proposed project plan sent to customer: 7/27 7/21/21 SJE -- - Configuration up for new SCA site - CMS content to be copied over on 7/22 7/9/21 SJE -- - SB Refresh: Complete - GR4C Meeting: 7/14 7/2/21 SJE -- - GR4C Meeting: scheduled for 7/14 - Customer working on SB refresh 6/25/21 SJE -- - Customer completely unresponsive this week - No SB refresh - Hoping to schedule GR4C week of 7/12 6/18/21 SJE -- - PM/FC mtg: Complete - SCA install in SB: in progress --> need an SB refresh (tbd on timing) n 6/11/21 SJE -- - PM/FC intro scheduled for 6/14 - Go Live TBD until intro 6/4/21 SJE -- - KT scheduled for 6/8 | 2021-08-06 | Komin, Alain |  |  | Villaverde, Alfredo |  | 241.5 |  | 2021-10-05 | 100261510 | 0 | 0 | 657.35 | AMO | Shipping Customizations | Y | N
J876187 | #SCA |  | #SCA | Intermex Wire Transfer LLC ¦ PS #SCA | Komin, Alain | In Progress | 2023-06-26 | Revised | 316 | Standalone | #SCA (Tracking Tag - DO NOT REMOVE) Job Email: messages.NLCORP.519869777.251c35bf4e@nlcorp.email.netsuite.com 05/19/2023 AKOMIN: Customizations moved to SB1. Tested successfully. Customer is aware that needs to test. No response yet from them. 02/07/2023 AKOMIN: File Upload to be demo on thursday. 01/27/2023 AKOMIN: Issue with multi subsidiares to work like the customer expects is taking a lot of time to resolve. There is an issue with proxied domains in cloudflare showing as not secure in NS. This is also taking a lot of time to investigate and fix. 01/25/2023 AKOMIN: Ilan is finalizing the File Upload and then it will be scheduled a demo. Overage of 55 hours requested. 01/03/23 AKOMIN - Work in good progress. 2nd Demo to be done today. 11/14/2022 AKOMIN: Customizations development started by Ilan today. 11/11/22 AKOMIN - FRD reviewed with customer. Development to start by Nov 14th. 09/28/22 AKOMIN - Project on track. 08/10/2022 AKOMIN: Project Kickoff scheduled for 08/16/2022. 07/22/22 AKOMIN: Sales KT scheduled for 07/25. | 2022-08-04 | Komin, Alain |  |  | Villaverde, Alfredo |  | 27.25 | 2023-06-26 | 2023-03-01 | 131405298 | 0 | 0 | 294.35 | AMO | Credit Card Processing Gateway for webstore – up to one (1). | Y | N
J864548 | #SCA |  | #SCA | Brown's Partsmaster, Inc. ¦ SuiteCommerce | Anderson, Peter M | In Progress | 2023-07-03 | Revised | 391 | Joint | #OPI-CHILD-ECOMM (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) #SCA (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) 5/16/23 - PMA - SOW has been extended. Meetings scheduled with BPI to update Roles & Permissions before moving into PW2 next week. Need to get the CO in place for additional SuiteCommerce hours. Need to review requirements fro the Item Catalogue PDF. 5/4/23 - PMA - The SOW has expired; working with Ops and the AMO to get an extension. Main blocker for BPI was understanding how to manage Roles & Permissions. We reviewed that with them today, and they will make updates and assign appropriate roles to their users before moving forward with PW2. Need to capture any gaps from PW2 and complete all updates to the SuiteCommerce site before moving into UAT. SuiteCommerce SOW has also expired, and there is an active CO that is being scoped. This is also being reviewed with the AMO. 4/18/22 - HM Peter Anderson is now the PM instead of Cara Garcia-Jones who is no longer with NS. Client has been notified. 6/16/22 - BA - Discuss Tasks & Target Dates meeting with BPI team on Jun 13, Cara Garcia-Jones has been assigned as a new Project Manager for Brown's Partsmaster project, Knowledge Transfer & Handover session with Cara, Review Project Kickoff Deck with PM and Delivery Lead on Jun 14. 6/10/22 - BA - Review & Update Project Plan, Update Kickoff deck and request customer's inputs, Review eCommerce SOW & Job Record meeting on Jun 8, Review SS4C Requirments with ERP Consultants meeting Jun 9. 6/03/22 - BA - Review Kickoff Deck & Project Plan meeting, Schedule Project Kickoff meeting on Jun 15. 5/27/22 - BA - Conducted Kickoff Planning and Sponser Alignment meetings on May 25, Sent draft Kickoff Deck and Customer-Facing Leading Practices for customer review, Completed bundle installation without any issues, Followed up with Sales team to provide Blueprint document. 5/20/22 - BA - Conducted PM Introduction Meeting, Reverse Sales to CS KT session, Internal CS Consulting Team meeting, Conducted Getting Started session on May 20, Scheduled Sponser Alignment meeting on May 25. |  | Noya, Maria |  | Bazzani, Emiliano | Marchlewski, Holly |  | 144.25 | 2023-07-03 | 2023-01-13 | 126592419 |  |  |  | New Business | 1. Configure Buy-online Pick up in Store and Advanced Order Management. 2. Configure Avalara Tax extension for SuiteCommerce. 3. Customize Your instance of SuiteCommerce to build an extension that will display inventory based on the customer type of “consumer” or “business” | N? | N
J883204 | #SCA | #POS-NSPOS-ONLY | #SCA #POS-NSPOS-ONLY | University Books & More (Univ Wisconsin Oshkosh) Implementation Service - Fixed Bid | Stewart, Karyn | In Progress | 2023-08-01 | Revised | 267 | Joint | #SCA #CAMPUS #POS-NSPOS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) KStewart 2023/5/23 - NSPOS Customizations (in progress) KStewart 2023/5/15 - Go live has been delayed due to: Missing Integrations (Verba) , Adoption and NSPOS Customizations (in progress) KStewart 2023/5/8 - Go live has been delayed due to: Missing Integrations, Adoption and NSPOS Customizations. KStewart 2023/4/18 - GoLive has been moved to 6/1. CBORD is expected delivery to Greg the week of 4/17. Pinpad have been installed, Watchman's ETA is 5/1 KStewart 2023/3/27 - Changing to Yellow status due to the following: No Pinpad No dates from Watchmans No dates for CBORD KStewart 2023/3/21 - The customer notified the team of their decision to move the go-live date. KStewart 2023/3/8 - Delays with Pin pads and Watchman have impacted the timelines, extending to 5/1 KStewart 2023/2/6 - UAT Planning KStewart 2023/1/30 - ERP PW2 has been completed. KStewart 2023/1/23 - PW2 is in progress. KStewart 2023/1/210 - PW2 is on pace to start in Mid Jan2023, the project is trending yellow due to integration delays. KStewart 2022/12/29 - PW2 is on pace to start in Mid Jan2023 KStewart 2022/12/20 - Customer needs additional training, the EC has been contacted. AMO and Sales are still in discussions regarding the CO for CBORD. KStewart 2022/11/30 - Customer has requested detailed TBs be loaded< CBORD is not in scope. Sales and AMO are in contact with the customer. KStewart 2022/11/30 - Customer has requested detailed TBs be loaded< CBORD is not in scope. Sales and AMO are in contact with the customer. KStewart 2022/11/4 - Customer has requested detailed TBs be loaded, a CO will be required. KStewart 2022/10/24 - Customer has requested detailed transactions be imported, further discussions are needed. Stewart 2022/10/17 - Personalization sessions are in progress. Sales has been requested to provide the details needed for the CO to address the gaps between the PC and SOW. KStewart 2022/10/12 -Personalization sessions have been scheduled. DM is in process. KStewart 2022/9/19 -Intro/SOW review with the customer has been completed. KStewart 2022/9/13 - Initial Job Setup KStewart 2022/9/16 - Completed Team Introductions and Intro Call w/the customer. | 2022-09-28 | Phillips, Lauren | Bazzani, Emiliano | Bazzani, Emiliano | Raghavan, Vidhya |  | 177.25 | 2023-08-01 | 2023-03-01 | 133942948 | 0 | 0 | 239.35 | New Business | Set up and configure up to one (1) Pre-Built Connection: a. UPS; b. FedEx; or c. USPS. | Y | N
J767990 | #SCA |  | #SCA | Fabrication Enterprises, Inc. ¦#SCA Implement Service - Fixed Bid | Croy Jr., Stanley R | In Progress | 2023-12-04 | Revised | 1431 | Standalone | #SCA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 4/25/23 ¦SRC¦ Excellent progress is being made on all the items need to get SB3 ready for a pre-UAT test run and then the Mock Cutover in preparation for full UAT which is expected to begin in the August timeframe in preparation for a 12/4 Go-Live as of right now. 3/28/23 ¦FEI¦ - SCA FC conducted to review meeting on the outstanding Web Content that FEI was working on. It appears that they are in a very good position in that all of the content work was being done in the production account. They will be ready for UAT testing in June timeframe. Current Go-Live is 12/31 2/28/23 ¦SRC¦ Still waiting on update from FEI team on the outstanding items they need to address for the SCA content they need to complete before additional testing can take place. 2/8/23 ¦SRC¦ SCA TS iss still reviewing extensions so that further testing can take place. 1/9/23 ¦SRC¦ With the script issue resolved eComm testing can start back up and with Shiphawk ramping up expect that UAT testing can commence by end of January timeframe. 12/2 ¦SRC¦ FEI has signed the Extension CO and with the Overage approved the eCOMM TS team will begin to review Extensions and Pricing as needed. 11/2 ¦SRC¦ SCA technical team will need to review past configuration which will require a new Overage 09/02 ¦SRC¦ Walkthroughs have now been completed and the FEI team will begin UAT testing in preparation for a 10/4 Go-Live 07/05 ¦SRC¦ FC continues to work with FEI team in preparation for UAT and a 9/1 Go-Live 06/15/22 ¦SRC¦ FC will now be supporting FEI team during their UAT in preparation for a 9/1 Go-Live 05/03/22 ¦SRC¦ FC continues to work with FEI team in preparation for UAT and what they need to complete on the eCOMM side 03/29/22 ¦SRC¦ FC continues to work with FEI team in preparation for UAT and what they need to complete on the eCOMM side 2/28/22 ¦SRC¦ Joint testing continues with the SCA and ERP teams on the Special Pricing customization. Once completed then FEI can commence with their testing in advance of the actual UAT. 1/31/22 ¦SRC¦ SCA team is now testing use cases for Special Pricing. They have also prepared SB3 for UAT testing which should commence in the late February timeframe. 12.29/21 ¦SRC¦ SCA team is now working with the FEI team on outstanding items in order to get in a position to begin testing with ERP team. They are also replicating the SCA components in SB# which will be the UAT Sandbox all testing will be conducted in prior to Go-Live. 11/22 AJ - Overage for additional 50 hours entered per below. 11.19.2021.PJM : Transferred project to Stan Croy. Alfredo to work with Stan on next steps. Overage requested due to employee turnover. Email sent to Alfredo for follow up. 10/15 SJE-- - Requirements identified / cross referenced from SOW, requirements in NSCORP, and JIRA. Next step, meet with the customer to confirm understanding of requirements - ERP and SCA teams working in tandem on Special Pricing and Freight Profiles 10/8 SJE -- - Multiple issues identified during Special Pricing script testing, meeting w/ ERP on 10/12 to determine a fix and next steps - Need to submit an overage once SCA has determined outstanding work 10/1 SJE -- - Special Pricing Script Testing: in progress 9/24/21 SJE -- - PM transition to Sarah Erickson - Working with ERP to determine how to modify existing ERP scripts to function w/ SCA 2021 0907 SM - There's an error on the special pricing script that is blocking the SCA team from wrapping up this feature. We've been waiting for the script owner to fix this issue for 11 days. Shipping profiles and pacejet customizations need also work from the ERP before we can mark those as complete. Price affected by item options feature on the customer side, have been waiting for more than a month. Still need to request an overage but cannot estimate the length of the project due to the above mentioned issues. November go live date at risk. 8/6/21 SJE -- - ERP solution blocking work for SCA - Overage required to finish out the quarter 2021 0730 SM - An overage of 30 hours was requested today to cover this week's activities. 2021 0726 SM - ERP team working on the special pricing feature, they weren't taking into consideration SCA related use cases so had several meetings to explain what they will have to do on the script to support those. Until those cases are contemplated, this feature is on hold for SCA. Other features blocked by the ERP side are: Pacejet and Freight profiles, weak and strong contacts (blocked for same reason). SCA team currently working on the broda integration feature, last one in scope we can work on. Setting same go live date as the ERP side, no timeline nailed down until we hear back from ERP, who are still trying to define what's left on their side (due to the lack of information the old team shared with this new one). 2021 0715 SM - New ERP team working on the scripts. Currently trying to explain them how the scrips need to be tweaked to support SCA. The SCA features are complete except from the ones depending on the ERP side (pacejet and freight profiles, weak and strong contacts, custom pricing) and the wheel chair configurator that is under analysis. Anticipating an overage request. ERP go live is set to 11/1. Updating job record to reflect that. 2021 0608 SM - 18/22 features have been migrated and tested to the new version of SCA. Blocked by the ERP side on 2 of the remaining features. Need to review with the customer one requirement that still needs definition (and can be very painful to implement). There is no timeline set because of the dependencies on ERP side, still need to define the amount of hours to request as an overage. 2021 0519 SM - Restarting project. Had to set up latest version of SCA and currently migrating the completed features to that new version. Given the project had been on hold for long, new testing needs to be done. There are some features still to be completed, we are waiting for customer/ERP team to complete their tasks so we can continue. No go live date set so far (although working on nailing down project plan). Anticipating the need of an overage due to team turnover and rework on some features. 2021 0201 SM - Netsuite License expired since 1/27/2021, cannot extend SOW. AMO stated they are going to give a credit to customer for the license extension, no updates so far on that. No open engagement with ERP, ERP has not gone live. Sandbox expiring on 2/11 (risk of loosing work). Proyect still on hold. 2020 1217 SM: Project on Hold. There is no ERP open SOW, so no progress is being done on that front. 2020 1005 SM - SOW is expired and per customer record, License has not been renewed so far. Sent email to AMO asking for updates so I know when to request a SOW extension. This project is still on development, there are some customizations pending to be completed, but go live date gets moved because customer keeps on asking for new reqs or changes to current ERP ones. 20191127 - Development is ongoing. Next week will hand over the project to Sofia Michelini. 20191122 - Development is still ongoing. No changes this week. Requirements for Advanced pricing may have changed on ERP's end, we have a meeting to review them Monday. 20191115 - Development on SCA side is progressing smoothly. Still awaiting solution for advanced pricing from ERP. 20191108 - Development on SCA side is progressing smoothly. Still awaiting solution for advanced pricing from ERP. 20191101 - Development is still in progress. Still awaiting advanced pricing from ERP side. 20191025 - Currently still in development. Met with ERP team this week to discuss pricing blockers. 20191018 - Development is still in progress. ERP is working on the advanced pricing blocker. 20191011 - Development is progressing slowly this week as majority of resources are concentrating on Classic 20191004 - Development is ongoing this week. no major changes. 20190927 - Development is ongoing this week. Kicked off Pacejet with ERP and Pacejet team. 20190920 - Development is ongoing. Spoke this week to ERP team about advanced pricing blocker and to Pacejet to initiate ERP integration. 20190913 - Development is ongoing this week. Demo set for next week. 20190906 - Development is still in progress this week. Work is ongoing. 20190823 - Development is in progress this week. Met this week to discuss Google Feed and EDI feed needed for SCA and ERP. Also discussed which environment will be used. 20190816 - Development is progressing this week. Discussed possibility of needing Product Feed with the client. Also aligned on SB accounts with ERP team. 20190808 - Development is still ongoing this week. 20190802 - Development is in progress. Advanced Pricing work has to be redone because ERP has given us incorrect information while we were pricing out the Change Order. 20190726 - Development is progressing. Reviewing two additional PLP customizations with the client this week. 20190719 - Development is in progress this week. One of the customization has been completed and reviewed with the client this week (catalog segmentation) 20190712 - Development is ongoing this week. Set up weekly internal Dev calls. Met with QA manager to discuss when QA can begin. 20190703 - Customization began this week. Finalizing plan with additional Dev resources this week. #SCA-CUSTOMIZATION (TRACKING TAG - DO NOT DELETE) | 2018-09-06 | Komin, Alain |  | Villaverde, Alfredo | Villaverde, Alfredo |  | 287 | 2023-12-04 | 2020-01-02 | 59538820 | 0 | 0 | 1722.35 | AMO | A. Allow customers to download current inventory document under My Account section. B. Enable per user catalogue segmentation. C. Create a Quote for international billing and/or shipping address D. Enable different part numbers for each site by using the same item master. E. Filter data display on My Account section according to a starting date. F. Allow display of item options on Product List Page ("PLP") G. Display online catalogue of product H. Disallow Invoice payment via credit card I. Hide price value on items flagged as "do not display price" J. Check product specific terms, prior to allow users to add the product to the cart. K. Enable multiple products add to cart on the PLP L. Display manufacturer's suggested retail price ("MSRP") value for not-approved dealers. M. Allow a product's price value to be modified according to the item options selected N. Show the stock keeping unit ("SKU") next to each color option variation for a given product. O. Assist with PaceJet integration. P. Remove links to products on category menus. Q. Enable "weak" and "strong" roles for contact records. R. For items flagged as "with advanced pricing", calculate and display a tiered pricing. S. Remove stock status display on items flagged as "dropship". T. Up to one (1) review of required customizations by Functional Consultant resource ("FC") U. Up to one (1) Search Engine Optimization review. V. Up to one (1) Oracle Software Security Assurance ("OSSA") review. W. Up to one (1) site performance review | N? | N
J821933 | #SCA |  | #SCA | Call One, Inc. ¦ Consulting Time #SCA | Komin, Alain | In Progress | 2023-05-30 | Revised | 735 | Standalone | #SCA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 05/02/2023 AKOMIN: Requesting a SOW extension for 6 months. 11/14/2022 AKOMIN: All customizations completed. Customer testing in SB. Estimated Go Live moved to March 2023. 08/01/2022 AKOMIN: Estimated Go Live date set to December 5th, 2022. 1/18/22 TE -- FRD review is almost complete. Once complete, Trisha to create RoMs/COs. 12/17/21 TE -- Call One team has reviewed FRDs/microsite requirement documents and have questions for Alain - in progress. Once these are finalized, COs may be needed for some things. 11/30 TE -- Alain has completed FRDs. Reviewing with Call One team this week. 10/15 SJE -- - After reviewing FRD with dev we determined we need to break out the microsite solution into multiple FRDs, review again with dev, finalize solution with DX, and then confirm with the customer. Planning to meet with the customer to review FRDs week of 11/8 10/8 SJE -- - FRD to be reviewed by Dev and DX 10/1/21 SJE -- - FRD Creation: In-Progress 9/24/21 SJE -- - FRD Creation: In-Progress 9/17/21 SJE -- - Requirements Gathering: In-Progress - FRD Creation: Not Started 9/10/21 SJE -- - Requirements Gathering: In-Progress - FRD Creation: Not Started 9/3/21 SJE -- - Requirements gathering for microsite replacement in progress 8/20/21 SJE -- - Call One will need to purchase 2 additional licenses (Active with AMO) - Unknown how PS will re-create functionality that exists today as microsites - discovery/poc required 8/13/21 SJE -- - Waiting on licensing discussion - need the customer to purchase 2 additional licenses, AMO to provide 2 additional licenses via a CAR, or work in SB - Meeting with SR dev scheduled for: 8/18 8/6/21 SJE -- - Need 2 temporary licenses for upgrade - Requested a SR. developer to help with the analysis of the customizations on the existing site and how the microsites will be upgraded with the SCA upgrade - Meeting again on 8/23 to discuss next steps with the Call One team 7/30/21 SJE -- - Microsite review: 8/3 7/21/21 SJE -- - PM Intro: complete - Go live: w/ ERP - PaceJet is in scope 7/9/21 SJE -- - GR4C: 7/21 - Estimated go live is TBD until we have the GR4C meeting 7/2/21 SJE -- - GR4C: Postponed until 7/21 per the customer request - Estimated go live is TBD until we have the GR4C meeting 6/25/21 SJE -- - GR4C: scheduled for 7/1 - After our initial discussion there is a possibility we do not need two SCA sites - waiting to hear more from the customer on this point - Estimated go live date TBD based upon the above finding 6/18/21 SJE -- - PM/FC Intro: 6/22 - Waiting to provide an estimated go live date until we speak with the customer 6/11/21 SJE -- - KT scheduled for 6/14 | 2021-07-21 | Komin, Alain |  | Villaverde, Alfredo | Villaverde, Alfredo |  | 25 | 2023-05-30 | 2021-11-30 | 99615801 | 0 | 0 | 673.35 | AMO | Credit Card Processing Gateway for webstore – Up to one (1) | Y
J830387 | #SCA | #POS-NSPOS-ONLY | #SCA #POS-NSPOS-ONLY | The Curators of the University of Missouri ¦ Implementation Service - Fixed Bid | Raghavan, Vidhya | In Progress | 2023-11-06 | Revised | 663 | Joint | #SCA #POS-NSPOS-ONLY #CAMPUS (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2023 0518 VR: Internal meeting to plan next steps in terms of detailed walkthrough1. 2023 0508 VR: Onsite sessions. Walkthrough to be repeated. Awaiting Change Orders to be signed. 2023 0427 VR: Onsite sessions week of May 8. Integration strategy meeting on May 1 2023 0413 VR: Onsite sessions week of May 8. Integration strategy meeting to be scheduled. 2023 0322 VR: Customer ready to re-engage. Meeting with Sponsor scheduled for 3/28 2023 0104 VR: Contacted customer for a restart date. March is the tentative date. Internal assessment in Feb. Customer to inform NS following those meetings. 2022 1208 VR: Internal PM Transition. Athi A will be PM. 2022 1128 VR: Project on hold. 2022 1107 VR: Reached out to Project Sponsor regarding restart dates 2022 1011 VR: Project on hold 2022 0913 VR: Project on hold due to customer management change 20220908 MK ¦ Updating Practice Lead to Ryan Murphy 2022 0829 VR: PM & DL change. Customer informed NS on 8/25 about a potential pause to the project. Internal meeting scheduled to discuss next steps (8/29) 8/17: LW ¦ Timeline conversation completed on 8/15 that go live will likely occur April or May of 2023. Customer slow down this week and next due to fall rush. Vital Launch set up completed, Avalara Dev in progress. 8/3: LW ¦ UAT is in progress. SOW Has been extended. Go live to likely move to 2/1/2023 at the earliest due to watchman integration delays. 7/15: LW ¦ Customer has begun on UAT. List DM to be complete this week. CO's in progress for remaining integration needs. SOW extension date to be discussed next week. 6/27: LW ¦ Data migration and SCA dev ongoing. NS working through completing the CO's tied to new scope. 6/15: LW ¦ scoping of CO's for integrations in progress. Customer working on SCA and data while preparing for UAT. 6/1: LW ¦ Data migration and SCA work is ongoing. UAT planning session completed on 5/26. UAT to begin ~6/27. 5/12: LW ¦ Data migration progress ongoing. Demo for shelf tag, complete. CBORD scoping in progress. 4/29: LW ¦ Data migration in progress. CSVi testing underway. SuiteCommerce licensing in progress now that documents are signed. 4/20: LW ¦ data migration and integration exploration ongoing. 4/6: LW¦ Working through integration communication and data deliverables. NS working on scoping new requirements. 3/23: LW ¦ GO live shifted to 10/3 to account for open integration and issues with SCA licensing. 3/9: LW ¦ Integration issues ongoing. DM and Action item work ongoing. Timeline to be evaluated with customer based on required new scope. 2/24: LW ¦ PWT2 for ERP and POS complete. Ongoing challenges with SuiteCommerce provisioning. Integration issues ongoing. 2/10: LW ¦ PWT2 ongoing and to be completed for ERP and POS by 2/16. Go live timeline is in jeopardy due to ongoing integration issues. SCA licenses are almost ready for sign off. 1/25: LW ¦ Prep for PWT ongoing. SCA licensing approval almost completed. Ongoing communication for integrations. 1/6: LW ¦ PWT prep sessions to occur week of 1/24 and PWT 2 to occur start of feb. SC config still on hold. 12/28: LW ¦ SC configuration on hold until we have the proper licensing in place. 12/20: LW ¦ PWT for ERP and POS completed. SCA licensing in progress. 12/3: LW ¦ PWT for ERP and POS ongoing, CAR for SCA licenses in progress. CSER for POS tax use case created. 11/22: LW ¦ PWT to begin today. SuiteCommerce Licensing issue ongoing. 11/15: LW ¦ Engage checkpoint call completed. Overall customer is satisfied with delivery so far. 11/10: LW ¦ SuiteCommerce licensing is still an issue. Personalization sessions for Site 1 complete. PWT to begin 11/22. One tax use case for POS that will require a script. 10/25: LW ¦ Personalization sessions for ERP and POS complete. CSVi conversations to begin. SuiteCommerce sessions to begin later this week. 10/13: LW ¦ Personalization sessions in progress. Data Migration activities in progress. SuiteCommerce licenses are needed to be provisioned before we can move forward. 9/30: LW ¦ Personalization sessions are in progress, data migration is the main focus at the moment, with SSO and SCA getting started sessions complete this week. 9/16: LW ¦ Customer has completed training. Personalization sessions to begin 9/20. 9/10: LW ¦ Kickoff completed as of 9/10. GSS and intro call due to PM transition completed. Personalization sessions scheduled for the week of 9/20. 8/30 SP: Working internally on scheduling KT, KO, GSS, etc. Targeting KO next week 8/17 SP: Intro call last Thurs; reviewing SOW & Initial timeline today in preparation for KO targeted early Sept | 2021-09-10 | Bohus, Gregory M | Bazzani, Emiliano | Bazzani, Emiliano | Raghavan, Vidhya |  | 439 | 2023-11-06 | 2022-04-01 | 105157698 | 0 | 0 | 622.35 | New Business | Item pricing (Price Levels, Price Groups, Quantity Based). Item costing (First-In-First-Out (“FIFO”), Last-In-First-Out (“LIFO”), Average, Standard). | Y | N
J870507 | #SCA | #POS-NSPOS-ONLY | #SCA #POS-NSPOS-ONLY | Wilfrid Laurier University ¦ Implementation Service - Fixed Bid | Annamalaisamy, Athiappan | Monitoring - Post Go-Live | 2023-05-09 | Actual | 363 | Joint | #POS-NSPOS-ONLY #SCA #CAMPUS (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 05 May: There is a POS issue for which scripting is required. The product support/PS team is working on it and in the event of not getting fixed, the client is advised to defer going live and ARR. #ER35474 (PS) & # ERR35483 ( Client escalation) is raised. Moving the job - Client relationship & schedule as yellow. 27 Apr: UAT Is in progress 19 Apr: UAT is nearing complete. 96% of testing completed by WLU So far. 28MarAA: UAT support is in progress. 01MarAA: Customer is briefed on the risk for ecommerce, Integration, ERP & POS. Currently, customer team is targeting to start UAT from 13th March. 27Feb AA: Customer is briefed on the pending critical open items which need to be closed on time else risk of starting UAT On time. 15Feb AA: Revised UAT timelines is from 6th March. Readiness assessment in progress. 07FebAA: Customer demand to prepone the go live to May1st due to their pressing needs. Risks were discussed along with mitigation plan to start the UAT from 1st week of March. 01Feb AA: Ball Park no's shared with customer for TouchNet. Following up is with customer for action items. Agreed with DL that overage may be required. This is because total 316 hrs utilized for custom payment framework build compared to estimated 200 hrs. 31Jan AA: EC session on NetSuite Introduction & Training Strategy Follw-up completed. 25 Jan AA: Ball park estimates provided for Touch net integration. Customer looking for realistic figures for which discussion is facilitated with the Solution principal. Customer team is followed for completing the pending action items 12Jan AA: Action items discussed with customer. Revised go-live date is 01 Jun'23. Contract signed for Punchout2go . 2022 1208 VR: Internal PM Transition. Athi A will be PM. 2022 1128 VR: Go live pushed out due to delays with contracts with 3rd parties. 2022 1107 VR: ERP W/T 2 in progress. 3rd party contracts still being signed by customer. Additional COs being scoped - 1. Touchnet, 2. Punchout2go 2022 1011 VR: ERP W/T 2 to be scheduled. POS W/T 1 pending confirmation from customer. 2022 0929 HK: ERP walkthrough sessions continuing. POS sessions to be scheduled, but are delayed due to server setup issues. 2022 0913 VR: ERP walkthrough sessions continuing. 20220908 MK ¦ Updating Practice Lead to Ryan Murphy 2022 0829 VR: Walkthrough schedule being coordinated. Data in progress but behind schedule 2022 0815 VR: ERP personalization sessions completed. W/T to be scheduled. 2022 0728 VR: ERP personalization sessions in progress 2022 0718 VR: Personalization sessions ERP in progress 2022 0711 VR: Personalization sessions for ERP starting week of July 11. 2022 0630 VR: Project KO completed. Personalization sessions being organized. 2022 0615 VR: Intro call with customer held on 6/13. KO to be scheduled. GS scheduled for 6/16. 2022 0610 VR: Welcome email sent by DL on 6/8. Intro call scheduled with the customer for 6/13. Reverse KT in progress | 2022-06-27 | Bohus, Gregory M | Bazzani, Emiliano | Bazzani, Emiliano | Raghavan, Vidhya | 2023-05-09 | 144.75 | 2023-05-08 | 2023-03-01 | 128527752 | 316 | 316 | 332.35 | New Business | Configure third-party Verba Compete and Verba Collect integrations. | Y | N
J878221 | #SCA |  | #SCA | Lynx Franchising, LLC ¦ Implementation Service - Fixed Bid | Rae, Karen | Monitoring - Post Go-Live | 2022-10-03 | Actual | 300 | Joint | #SCA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 5/12/2023 KR: PGLS issues list received for SCA and phase 2 go live - working to resolve and communicated need to transition to support or engage in an ACS contract. Customer communicated that they will provide FA data for loading. Superior Fence go live plan will be communicated by customer. NS has provided all deliverables leading to Convert stage but internal politics at Empower have impacted ability to commit to a go live plan. superior is now in their busy period which does not help to promote a go live plan. Proposed that if customer can not plan an immediate go live, they can emgage in a new SOW for phase 2, Alternatively a T&M SOW, or engage in an ACS contract. 5/9/2023 KR: We/NetSuite have reserved budget for Superior cutover activities and Post Go Live Support (PGLS), however the ongoing support of all other operations is depleting the budget and this is exacerbated with the Superior Go Live being delayed several times since March. In this case PGLS has been ongoing since February and this is depleting the budget significantly. As you know, we typically wrap up a project with six weeks of PGLS and then transition to Advanced Customer Support (ACS) if purchased for ongoing optimization efforts and NetSuite Technical Support. We can also engage in a new Time and Materials SOW if this is a better approach. All that said, based on our discussion today, we have three main areas of focus to wrap up: 1. Fixed Asset Loads – We are waiting on the file from Cristin. a. We expect to receive the file this week from @Cristin L Smith, CFEin order to complete the loads the week of May 15th. 2. Various support issues related to the website, forms, invoice data loads. a. @Kenneth Johnsonwill provide a list of final issues by Friday May 12th. b. We will plan to wrap them up within the next month and/or transition to support 3. @Joshua Painterwill advise of the plan for Superior go live by next weeks’ status call. a. NetSuite has supported UAT b. Provided templates for cutover items c. Karen has reserved 15 to 20 hours for PGLS over a four week period. d. We can not continue to delay. e. Superior is now in their busy season. There are several options to consider. You may want to wait for Superior to get passed their busy season and we can plan to engage in a separate SOW to get them live at a later date. You can also consider engaging ACS for ongoing support which would be beneficial as Empower continues to grow and take on new business. You can do both options. 4/27/2023 KR: Customer was not available to report on status of testing inventory control processes. Customer will communicate their plan to wrap up testing and confirm a go live date for the Superior entity in order that we can plan to close and transition to support. Update will be available on May 2nd. 4/6/2023 KR: Superior GL was delayed to 4/3 due to customer delay in testing and providing feedback and action items for resolution surrounding inventory control processes. Peter August developing saved search and providing PWT's. Lynx has been slow to provide fixed asset data for final loads. SCA team working through support cases. Plan to transition to support May 12. 3/1/2023 KR: Phase 2 OLB PGLS go live in progress. Superior implementation has slipped and customer has been cautioned about setting/confirming go live to determine project end date as a 3 phased implementation is not in scope. Meeting March 7th to firm plan. 2/16/2023 KR: OLB delayed SCA go live to 2/16. Team was in Orlando and not available to support customers. Working through PGLS issues. Superior ops is not ready for go live . Communicated to Cristin (controller for Superior) that they need to finalize testing during week of 2/20. 2/2/2023 KR: SCA go live delayed to 2/6 due to delays in payment processor setup by customer and issues with workflows and data migration resulting from UAT. 1/27/2023 KR: UAT is ongoing for Superior and OLB - OLB delays due to data migration of matrix items and list data from OLB legacy account. Superior delays due to setup and confirmation of process for item groups. Cristin is confident that Superior will go live with some duplication/parallel with legacy. OLB go live at risk as OLB continues testing of SCA site/resolving issues. EMerchant account has not been confirmed for 2/1 yet. Back up plan for OLB - SCA site notice 'site down' on 2/1. Can continue to enter orders in legacy and manually update in new PRD account (10 orders per day). Customer team is at an offsite and travelling from 1/30 through 2/1. 1/10/23 KR: phase 2 go live pushed to 2/1/23 due to client readiness and matrix item configuration. Matrix items loaded. SCA testing in progress. UAT begins 1/10. On track for 2/1 go live. 12/30/22 KR: Phase 2 SuiteCommerce (SCA), OLB and Superior Fence – Go Live date has been moved to February 1, 2023. Project plan revised to reflect 2/1 go live.SANDBOX refresh will not take place on 12/30. Lynx does not want to override JP Morgan setup in SBX. We will discuss plan to refresh on 1/3 status call. Matrix items are now loaded in PRD (Quinn 12/30). Peter working on Item Groups for Superior. Josh requested csv integrator pricing to determine plan for Concur – Jared to provide. 12/12/2022 KR: LYNX UAT for SCA and phase 2 at risk due to requirement to have matrix items in account. 12/2/22 KR: Phase 2 SCA site migration on track. Phase 2 OLB implementation requires matrix items which is not provisioned to account. Working with AMO/Jared to determine how to enable in account. OLB has matrix items in place and this was not considered in new SOW nor NetSuite account. 11/11/2022 KR: Lynx team is working on wrapping up phase 1 go live action items for open transaction and HTB loads for JPI, CCDC and FRSTeam subs, FA data will follow. Phase 2 go live on track for 1/1/2023 - SCA plan is drafted and FRD has been delivered. Recommendation to move to new SCA version. Plan to migrate OLB website to new Lynx account by 12/1. SCA UAT planned 12/7 to 12/13. Phase 2 for OLB and Superior Fence in progress and working on static data loads including new matrix items. UAT for phase 2 to begin 12/7, SBX refresh on 12/6. 10/28/22 KR: Go live for Superior Fence and OLB, incl SCA, delayed to 1/1/23. Concur integration will be manual for go live. Planning UAT test cases. 10/17/22 KR: Additional licenses purchased; OSSA compliance in progress; Loading open transactional data; SCA implementation will determine SCA version; planning phase 2 initiatives. 10/3/2022 KR: LYNX is live on phase 1 project deliverables of all subs except Superior Fence and OLB. These two subsidiaries along with SCA will go live as phase 2. Phase 2 go live date TBD. 9/26/22 KR: Client preparing cutover items for 10/1 go live. EUT begins this week. Send UAT signoff. 9/12/22 KR: UAT in progress for Franchise Sub(s) go live on 10/1. Decision to move Superior go live to phase 2. SCA analysis/report due this week; Planning SCA and OLB phase 2 go live.8/30/22 KR: Daily data checkpoint calls are expediting data migration; Process Walkthroughs in progress this week. UAT strategy delivered 8/24; Plan to move to 2 week UAT starting 9/6. Go Live planned 10/1 for Lynx Franchisors and OLB will be phase 2 along with SuiteCommerce reimplementation. Following up with SCA team on analysis of environment/report. 8/17/22 KR - Inconsistencies noted in SOW to be reviewed on 8/18. ERP team moving data, forms, setup and configuration to new account. SCA team reviewing environment and customizations to determine effort and timeline. Preliminary integrated project plan in place. 8/3/2022 KR: Project staffed and scheduled. Continuation from J856011 in new Production account and additional of SuiteCommerce. Bundles requested and configuration to begin based on Personalizations from previous job. Plan SCA implementation which will likely become a phase 2 as must go live on based on prior personalizations. | 2022-08-25 | August, Peter |  | Bazzani, Emiliano | Peterson, Suzanne | 2022-10-03 | 182.75 |  | 2022-10-01 | 132238029 | 39 | 39 | 273.35 | AMO | Create custom record(s) and script(s) to support the migration in Section 2.G.2. for the record type(s) which are not available for import using CSV imports: a. Item Receipts. b. Item Fulfilments. c. Deposits. d. Cash Refund. e. Customer Refund. | Y | N
J837960 | #SCA |  | #SCA | Autocar Parts, LLC ¦ Implementation Service - Fixed Bid | Villa, Myr Angeli | Completed | 2023-01-30 | Actual | 602 | Standalone | #SCA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 3/17/23 MV - On going PGL support. Sent a request to extend the SOW to 4/31/23. 1/30/23 CG - Client now live. A few notes: 13k redirects roughly found during migration analysis. Only for JIT as GVW is closed. Client gave additional redirects for JIT and GVW. Agreed and understood we would not validate those being outside of the 95% we are targeting but would upload them. Once uploaded, noted there were circular redirects (a redirect that redirects to itself). The extra redirects were removed and sent back to client noting the issue which will need to be fixed. Client also went live without Cloudflare, redirecting from root domain to www with a preserved path. Seems to work ok. 11/8/2022: MLV: Client requested to push go live into 1/31/2023. UAT is still in progress. 9/23/2022: MLV: Pending on customer's signed SOW via Docusign. Sent a follow up as the SOW will expire by EOM. 09/14/2022 MLV: UAT is in progress. Requested a SOW extension to continue the implementation until the go live on 10/24. 04/29/22 MLV: SOW for additional scope sent to AMO for discussion and customer's sign off. Weekly sessions with customer is in progress. 3/16/22 MLV: Customer had started the site configuration and asset development. Weekly check-in meeting to start this week. 3/7/22 MLV: Took over job from Trisha as PM. To schedule a weekly meeting with the customers to guide them and provide demo during their offline configuration and asset development. 1/31/22 TE: Personalization sessions have been scheduled for 2/7, 2/10, 2/11. No update from the AMO regarding hours for 3rd, EPC site analysis. 1.11.22 TE: Personalization sessions have not been scheduled yet; waiting for some ERP data. Discussion in progress regarding 3rd EPC site (not in scope) and CO needed to perform an analysis. 12.6.21 TE: -Had a check-in call with customer to discuss their websites. Sales only scopes for 2 sites, but they want us to work on all 3. -Third site will need to be a customization. We're coordinating for a dev resource to discuss this further internally and with customer. 11.30.2021 TE: Took over job from Pat as PM. Had GR4C call. Check-in call scheduled to discuss themes and which one of their 3 websites they want to move forward with (we only have 2 SCA licenses). 10.29.2021.PJM : Took over as PM from Sarah. No updates on job as ERP has not scheduled kickoff. Looking at ERP job, this job may go on delayed status for awhile however, I will call out the risks that if any customization happens on the ERP side, it could affect the webstore so the SCA team should be aware of any gaps identified during ERP personalization sessions. 10/15 SJE-- - ERP KT scheduled for 10/19 10/8 SJE -- - KT scheduled for 10/12 | 2022-02-07 | Green, Chris |  |  | Bazzani, Emiliano | 2023-01-30 | -1.5 | 2023-01-31 | 2022-08-01 | 110001257 | 357 | 357 | 472.35 | New Business | Credit Card Processing Gateway for webstore – up to one (1). | Y | N
J870124 | #SCA |  | #SCA | Colony Tire Corporation ¦ #SCA | Atchison, Patrick | Delayed - Per Other Project | 2023-11-01 | Revised | 363 | Joint | #OPI-CHILD-ECOMM (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) #SCA #ACS Architect 02272023PMA: Reopened for Feb billing and then will be put in "Delayed" status until Phase II. 02072023PMA: Colony confirms SCA scope move to Phase II. Will go into delayed status 02012023PMA: Finalizing scope this by 2/5 and will then put in delayed status 01172023PMA:Identified for Phase II 12162022PMA:Onsite was successful and scheduled recap for 12/20. 12012022PMA: Colony decided to push suite commerce to a phase II post ERP go live 11172022PMA: Expect engagement to be pushed to Jan 2023 due to Colony bandwidth. 11032022PMA: WT2 (scheduling) recommenced. Fitment Search and FET SDDs are in progress / in internal review. Proposed architecture 75% designed and major data management decisions need to be made. Onsite tentatively scheduled for 12/12 and will confirm on next regroup on 11/7. Expect SC4S activities to be pushed into Dec. Project escalation submitted via Early Warning System. Colony currently unaware of major scope gaps discovered. -PMA 10182022PMA: WT1s paused until TS scope (fitment+) is validated after 3/3 TS solutioning sessions are completed on 10/20. Team will regroup on 10/24 to finalize plan going forward, including scoping onsite discussions. Colony requested to push eCOMM personalization engagement to mid Nov 22'.-PMA 09302022PMA: Colony requested to push eCOMM personalization engagement to mid Nov 22'.-PMA 09232022PMA: Go Live rescheduled to early Fall 23' circa 10/2/2023 to avoid "busy season" - PMA 09092022PMA: Began engagement on 09/08/22 Getting Started with SS4C - PMA |  |  |  | Villaverde, Alfredo | Haines, Jefferson R |  | 580.75 | 2023-11-01 | 2023-03-01 | 128496254 |  |  |  | New Business
J804285 | #SCA | #POS-NSPOS-ONLY | #SCA #POS-NSPOS-ONLY | Syracuse University ¦ Implementation Service - Fixed Bid | Raghavan, Vidhya | Monitoring - Post Go-Live | 2021-07-23 | Actual | 906 | Joint | #POS-NSPOS-ONLY #SCA #CAMPUS (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2023 0518 VR: SOW Extension shared with AMO. This is needed for CBORD Odyssey deployment. 2023 0508 VR: SOW extension reapplied. This is needed for CBORD Odyssey to be deployed 20230503 MK - Overage of 10 hours approved to support pending deliverable and sow extension. Approved by VL Meenakshi Krishnan, Job record has been updated. 2023 0427 VR: CBORD Odyssey dev completed. Awaiting POS server for Internal dev acct to be provisioned. 2023 0413 VR: CBORD still in progress. 20230411 MK - Overage of 35.5 hours approved to help with Job leveling and Technical development efforts. Approved by VL Meenakshi Krishnan. Job Record has been updated. 2023 0316 VR: CBORD still in progress. Coordinating with CBORD team to test. 2023 0306 VR: CBORD still in progress. Coordinating with CBORD team to test. 2023 0222 VR: CBORD still in progress. Coordinating with CBORD team to test. 2023 0124 VR: CBORD still in progress. Coordinating with CBORD team to test. 2023 0105 VR: SOW extension was rejected by contracts due to incorrect CO#. Revised CO was sent on 01/04 and received signed copy. Extension approved. CBORD testing in progress. 20221206 (TDC) - PM changed to Vidhya; Received signed ext document. 20221129 (TDC) - Emailed Roger regarding SOW ext - need to send Docusign to appropriate contact. 20221122 (TDC) - targeting CBORD completion some time in Dec. 25-Oct: Project handed over to Todd Chalmers by Zubair Raja. Todd is the new PM to lead the remaining work i.e., CBORD integration 20-Oct: SOW got extended till 1st November but needs to be extended to Feb 2023, which is not possible until the customer renews their software license, which is expiring on 30th Nov. Account manager is aware of it and working with customer to get this renewed ASAP. 07-Sep: SOW extension request delayed by customer 31-Aug: Revised SOW extension request sent to customer on 29th August as the first one didn't get signed. The revised SOW extension is also waiting for customer's signature and they are telling us that it would need legal review and that may take some time. 11-Aug: SOW extension request sent to customer (Roger), who has sent it to the University Council for approval. This may take a month or two, which would be of no use. The issue has been escalated to the Delivery Lead and we are trying to set u a call with customer to discuss it and get it resolved.. 06-Jul: SOW expired and extension request sent to customer for 60 days. Customer has approved for up to 60 days as they want to have this product before the beginning of the school year. ... 03182022 BU Job transafered to Z. Raja for CBORD integration and management. 12012021 BU: Customer in extended go live support as we work to correct SAM and payment issues. 08202021 BU: Product anticipates that Sam will be released for testing next week. 08122021 BU: All store and websites are up and running. 08052021 BU: Website is going live and store transactions are live. 08022021 BU: Website fully live and POS ERP transactions are running. 07232021 BU: Customer weent live with limited Web and POS. 07152021 BU: Bundling for ERP targeted for completion on 07/16 EOD. POS and SCA to start 07/19 07082021 BU: UAT completed with open items and SB to Production bundling to start 06302021 BU: UAT to complete 07/06 to meet cut over date for bundle to production and data migration. 06242021 BU: UAT Started and Book integration escalated with Verba. 06172021 BU: Blocker for Verba Still Need user credentials. UAT to Begin 06/18 06112021 BU: Still having delays with the Scoping and Estimates of GAPS from the TS and Sales group. Escalated to AMO. 06042021 BU: Integration Broker Setup Started by Ravi 06022021 BU: Change Order still not yet presented to customer. 05202021 BU: Customer still awaiting Scoping and Contract from Sales. 05122021 BU: Large CO in progress with new requirements for go live in scoping. 04082021 BU: Procure to Pay WT session customer canceled will need to reschedule. POS Continuation WT Sessions start up 04/13. Customer is not going to integrate RedShelf and will be using Verba. 04012021 BU: ACS Kick Off Intro letter sent to customer. 03262021 BU NSPOS Walk through session pushed out due to resources onsite for another customer POS scheduled for 04/12 - 04/16. 03/192021 BU Walk through 1 session have started and ERP should rap up by 03/30. 03082021 BU: Configuration by NS team has Started. 03012021 BU: All personalization calls are completed to include POS. 02232021 BU: All ERP personalization’s are Scheduled. 02092021 BU: User Adoption Kick Off Completed 020720201 BU: Personalize session in progress 02032021 BU. Weekly update schedule is in place and team is starting the personalization sessions. 01062021 BU: Customer Kick off call completed. Getting started call for connection scheduled for 01/11/2021 12102020 BU: PS Sales KT Session set for 12142020 12042020 BU: Open job and PSER review.. | 2021-01-06 | Serron, Sennon A | Bazzani, Emiliano | Bazzani, Emiliano | Raghavan, Vidhya | 2021-07-23 | 10 | 2021-07-23 | 2021-06-01 | 86331634 | 198 | 198 | 869.35 | New Business | Set up and configure up to one (1) Pre-Built Connection: a. UPS; b. FedEx; or c. USPS. | Y | N
J811425 | #SCA |  | #SCA | ACG, Inc¦ #SCA Implementation Service - Fixed Bid | Bertorelli, Yvonne A | In Progress | 2030-06-05 | Revised | 827 | Standalone | #SCA (TRACKING TAG - DO NOT DELETE) 5/2/2023 - YB - Customer has committed to testing but I have not heard from him since our last call. Been emailing to set up a regular call for check-ins. 4/21/2023 - YB - Met with customer today, he has been in an audit so has not started testing. He is no longer bringing in the third-party team and has hired another marketing person. He expects to be able to devote time next week to testing. 4/4/2023- YB - Met with customer he wants to get this project completed and will be bringing in a third-party consultant that they worked with previously to be onsite and assist him with testing. He has a lot of travel for the next two weeks but plans to start on 4/17. 3/30/2023 - YB - Meet with customer tomorrow to see how he is progressing with his testing of the new site. 3/8/2023 - YB - This customer continues to be non-responsive despite my multiple emails. SOW's are out for signature for the 5th time and although the AMO said he would be ready to start in March, the customer has given no timeline. AMO to call them today. 1/30/2023 - YB - Customer has not been responding to my emails, I have included the AMO and DL on those communications. 12/22/2022 - YB - Customer has not reached out, will touch base for an update at the beginning of the year. 11/21/2022 - YB - Customer has hired a new marketing person who he wants to be in charge of the site. This person is now taking the Webstore Administrator training in order for us to meet and do personalization sessions. 10/31/2022 - YB - Customer has had on delayed and has now hired a new marketing/web person. Last update is that he expects to have this tested within the next two weeks but has not indicated a date he would go live with all the changes. 9/22/2022 - YB - Emailed customer for an update on testing but have not received a response, will try again. 8/15/2022 - YB - Need to check-in with Chris to see if he has started testing the new site so we can set a go live date. 7/28/2022 - YB - Waiting on customer to review all customizations for upgrade to formalize a plan to migrate to production and cutover. 7/12/2022 - YB - Call with customer this week to review last customization 6/16/2022 - YB - Final customization has been sent for testing. 5.23.2022 - YB - Developers are working on the final customization that just came in via a different job 5.9.2022 - YB - CO has been signed, waiting on job to be assigned to meet with the developer and begin working on this last bit. 3/28/2022 - YB - Still waiting on CO. 3/15/2022 - YB - Still waiting on CO to go through the channels with AMO and SP on the additional work needed before they will even consider launching the upgraded site. 2/22/2022 - YB - Was given the impression that the delays for this job were all because the customer didn't have bandwidth but after meeting with the customer this is only partially accurate. There is a CO pending for work that was not originally part of the scope and is a major portion of their business. The CO is in the works and the LOE was scoped. Will need to follow up on this is the reason the project is stalled. 2/7/2022 - Just inherited this job and am awaiting introduction to customer, requested SOW extension out for 6 months. Need to meet with customer to determine if this job should go on hold or if we can set a new date for launch. 1/20/22-JAL-Implementation Partially On Hold due to Customer Readiness. The customer does not have enough staff to work on the SuiteCommerce-related tasks. 10/15 SJE-- - Customization development in progress - Additional scope identified on 10/14 - custom support case creation in the MyAccount section, gathering requirements to determine an estimate 10/8 SJE -- - Development: In Progress - Go Live date adjusted to 12/15 but ACG may push to 1/11 10/1 SJE -- - T&M CO signed by ACG - waiting on job creation to complete customizations. 9/24/21 SJE -- - Dev: In-Progress - CO creation in-progress for additional hours required to complete customizations - Offline Configuration: In-Progress 9/17/21 SJE -- - Discovered the customizations will take additional time than originally proposed in the CO. Meeting with ACG on 9/20 to discuss further and determine next steps 9/10/21 SJE -- - Development: In-Progress - Theme Chosen: Threads 9/3/21 SJE -- - FRD Creation in process - 3 FRDs approved by ACG - Development: In Progress 8/20/21 SJE -- - New go live date of 11/16 - Possible increase in scope from ACS - Personalization sessions: complete - FDD Review to be done before 9/1 8/13/21 SJE -- - 2 personalization sessions held - Waiting on SOW Extension job update in NSCORP 8/6/21 SJE -- - Change Order: in-progress - Personalization Sessions: 8/23 - Project Plan to be created once a developer is assigned and we can review their forecast 7/30/21 SJE -- - Intro to customer: complete - Personalization Sessions: Begin week of 8/23 - Project approach: NS PS to complete SCA upgrade and customizations, Jason B. to follow up with CO 7/21/21 SJE -- - PM Intro sent - Path forward for customizations --> change order on original SOW for customization development - Rafa to begin Personalization sessions once ACG is ready 7/16/21 SJE -- - Project PM responsibilities transitioned to Sarah Erickson 6/1/2021 - FL - Analyzing and creating documentation of current customizations for the migration from SC to SCA. 5/18/2021 - FL - Waiting for ACS to complete customizations before analyzing scope. 5/11/2021 - FL - Go live is set for August but is tentative to be moved as we are to analyze the current customizations to determine the effort. 3/26/2021 - FL - Kick off meeting done, next steps is to analyze current customizations with ACS |  | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 64 | 2030-06-05 | 2021-11-16 | 92413408 |  |  |  | AMO | Shopping Cart (enable/disable): a. Line-item options editing b. Shipping and tax estimator c. Recently viewed items d. Save for later action button e. Items display (upsell and cross-sell) f. Promo code/gift certificate input | N? | Y
J840121 | #SCA |  | #SCA | Mac Business Solutions, Inc. ¦ #SCA | Green, Chris | In Progress | 2023-07-03 | Revised | 577 | Standalone | #SCA (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 5/8/2023 AVV - Set status to In Progress to allow booked time to flow through OA integration 4/28 CG - Sent follow up to client along with Docusign to attempt to have them extend the project 3/31/23 CG - Followed up with client earlier this week regarding moving forward. Noted that a key stakeholder who was positioned to work on SCA project was no longer with company. Informed client of expired job. Following up today to sign extension ASAP. 2/10/CG - Customization to display customer logo in myaccount portal sent to client for review. Have not heard back from client on site config outside of this however. Follow up planned 9/21 CG - Client ready to proceed, met 9/13 to discuss plans for launching site, requesting extension for project 5/19/22 CG - client missed GR4C call first week of may. Attempting to reschedule but availability is tight with Yvonne and OOO time. Offered 6/8 timing. Also noted project needs extension and requested proper stakeholder 4/11/22 CG - client emailed with access needed to begin SC project | 2022-09-01 | Green, Chris |  |  | Villaverde, Alfredo |  | 181 | 2023-07-03 | 2022-08-02 | 112158214 | 0 | 0 | 266.35 | New Business | Setup and configure the following within the Web to Order process area, for one (1) ecommerce webstore, for a single instance with a pre-formatted template: | N? | N
J839346 | #SCA | #POS-NSPOS-ONLY | #SCA #POS-NSPOS-ONLY | University of Virginia ¦ Implementation Service - Fixed Bid | Raghavan, Vidhya | In Progress | 2023-06-20 | Revised | 584 | Joint | #SCA #POS-NSPOS-ONLY #CAMPUS (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2023 0518 VR: Job leveled. This job will not be used for anymore time entries. Keeping master job open till Go Live. 05172023 MK¦ Overage of 10.45 hours approved for job leveling. Approved by VL Meenakshi Krishnan. Job Record has been updated. 2023 0508 VR: Payment Framework test issues resolution in progress. 4/27/2023 MK - Overage of 250 hours approved to support additional efforts needed to complete CSPF work. Approved by VL Meenakshi Krishnan. Job Record has been updated. 2023 0427 VR: CSPF testing in progress 2023 0413 VR: CSPF testing in progress. 20230411 MK - Overage of 150 hours approved to support CSPF Tech rework with NSPOS and Ecommerce workstreams in addition to supporting UVA specific use cases. Approved by VL Meenakshi Krishnan. Job Record has been updated. 2023 0316 VR: CSPF WPS completed. FC testing in progress. 2023 0306 VR: CSPF work in progress. 2023/2/23 Mkrishnan - Overage of 250 hours approved to support reusability of Tech work around CSPF framework for Campus clients. Approved by VL Meenakshi Krishnan. Job Record has been updated. 2023 0223 VR: W/T 2 to be onsite - week of 3/6 2023 0124 VR: WPS dev nearing completion. WT 1 in progress. 2023 0105 VR: WPS dev in progress. Reengaged with the customer. W/T 1 being scheduled. 2022 1128 VR: WPS dev in progress. 2022 11 08 MK: Overage of 250 hours approved to support mis-scoped customization work. Approved by Vertical Lead Meenakshi Krishnan. Job Record has been updated. 2022 1107 VR: Payment frameworks dev in progress. Implementation to start in Jan. 2022 1011 VR: Change order with customer. Awaiting sign off. 2022 0913 VR: Change order review in progress 9/9, MS: Follow-up call with SP on Change Order to review updates needed on 8Sep and updated CO approved on 9Sep and ready for client. New CO sent to client by AMO. Also, had client meeting with current PM and DL and new VL, DL, and PM. 9/8/2022 MK ¦ Updating DL to Ryan Murphy. Client introductions email to new stakeholders completed. 9/7, MS: Call with new VL and new PM to review CO status and next steps. 9/6, MS: Call with SP to review current Change Order internal. Also, KT meetings this week with new PM along with follow-up emails to provide project key documents and status. 9/2, MS: Call with client scheduled to review Change Order wording specific to campus payment customization. 8/30, MS: Change Order drafted and approved by contracts although CO to PC mapping unclear while campus payment customization wording okay and plan to review with client as first step to introducing CO to client. 8/24, MS: Watchman-NS document updated and to be sent to client this week. Change Order needs for campus payment customization along with UVA specific payment customization and functional updates in progress and meeting with SP occurred yesterday. 8/10, MS: Meetings with client this week to confirm their understanding of joint Watchman-NS doc. Also mgmt approval given to do early payment customization evaluation of campus program approach including what program setup and design will look like. 7/29, MS: Watchman-NS doc sent to client last week and received client questions this week. Due to PTO of Watchman and NS, will organize meeting with client for mid-August with goal to have Change Order by end of August. 7/14, MS: Joint Watchman-NS doc expected late this week or early next week to send to UVA. Also, working with NS team on estimates to get client into UAT for non-payment customization work (core plus other customizations). Core project on hold while customization change order determined although job open for time entry as key stakeholders working on change requirements. 6/29, MS: Final discussion to nail down approach for payments between NS + WPS completed yesterday and now joint document being created to present to customer. 6/14, MS: More discussion with Watchman needed although key Watchman resource has COVID so discussion to be re-scheduled. 5/30, MS: Large re-design needed in collaboration with Watchman on both NS and Watchman side to accommodate several payment methods.. Discussion ongoing. 5/16, MS: Initial Watchman meeting with UVA-Watchman-NS. Next step this week is Watchman-UVA follow-up before NS-Watchman meeting and then larger group follow-up. 5/11, MS: Watchman engaged by UVA and also offline discussions with NS to determine path forward for UVA with joint solution of NS and Watchman critical to client requirements for Go Live. 4/29, MS: Estimation taking longer than expected although NS team suggested to be working with Watchman for them to provide some of the scope. Customer has engaged Watchman. Expect follow-up with NS + Watchman next week. 4/13, MS: Customer unplanned scope still being estimated. Expect feedback next week from internal team. 3/29, MS: Customer requested unplanned scope. Meeting with campus experts to discuss and request their help in path forward and ROM. 3/17, MS: Customer raising concern about payment methods and mis-understanding they had from Sales process. 3/2, MS: Customization requirements still in progress and expect further updates mid-March. 2/23, 2/8, MS: Customization requirements in progress. Customization tracker in OraDocs. 1/25, MS: WT 1 for ERP complete. WT 1 for POS planned. SCA Personalization planned. Customization tracker still being updated with some work started to nail down design. 1/11/22, MS: Customization tracker updated by team and next steps in progress to move towards nailing down requirements. 12/28, MS: Walkthrough 1 planned for January. 12/14, MS: Personalization completed. 11/30, MS: Personalization in progress until 12/8. 11/23, MS: First customer status. Personalization in progress with NSPOS to be planned. 11/16, MS: Kick-off and SOW Review on 11/10 and Personalization starts 11/16. 11/5, MS: Kick-off next week and then Personalization starts. 10/28, MS: Intro call occurred 10/26. Team planning scheduled for 11/1 and Reverse KT scheduled for 11/3. 10/22, MS: Welcome letter sent and new job assigned 10/21. | 2021-11-10 | Serron, Sennon A | Bazzani, Emiliano | Bazzani, Emiliano | Raghavan, Vidhya |  | 0 | 2023-06-20 | 2022-10-01 | 111274895 | 0 | 0 | 561.35 | New Business | Set up and configure up to one (1) Pre-Built Connection: a. UPS; b. FedEx; or c. USPS. | Y | N
J889938 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Ohio Taxidermy Supply, Inc. - Professional Services : Activation - SuiteSuccess fo | Estellano, Santiago | In Progress | 2023-05-29 | Revised | 209 | Standalone | #SC-PLUSCUSTOMIZATION job record tag: messages.nlcorp.531092778.afd6b5ba24@nlcorp.email.netsuite.com SE:17May23: item import file ready, sent over to the client for revision SE: 12May23: closed over 50% of action items. Images missing and items not yet imported still block UATs. SE: 21apr23: troubleshooting session with client. SOW extension to be requested for consulting time project. SE 12-apr-23: followed up with client; limited to no changes in web store. SE 13-mar-23: personalization sessions complete, moving to Drive Phase. Matrix items still not ready SE 06-mar-23: starting personalization session. Matrix items still not ready. Commerce category tree ready to upload SE 28-feb-23: deployment finished, personalization sessions scheduled. SE 22-dec-22: client working on commerce category structure and going through training course, kickoff postponed until finished. SE 20-dec-22: intro meeting with ERP consultant for setting up matrix items SE 29-nov-22: touching base with client prior to kickoff SE 18-nov-22: GR4C meeting with client | 2022-11-16 | Estellano, Santiago |  |  | Bazzani, Emiliano |  | 28.75 | 2023-05-29 | 2023-01-16 | 137176613 | 0 | 0 | 190.35 | AMO
J902366 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Classic Alaska Trading/Big Ray's Alaska, Inc. - Professional Services : Activation | Ueckert, Brant | In Progress | 2023-06-19 | Original | 125 | Joint | #SC-PLUSCUSTOMIZATION 02152023 BU: Job opened and Tasks assigned to PS team. RETAIL SITE |  | Noya, Maria |  | Bazzani, Emiliano | Conor, Katharine S |  | 49.5 |  | 2023-06-19 | 142157822 |  |  |  | New Business
J869422 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Wallace Farm, Inc. - Professional Services : Activation - SuiteSuccess for Commerce | Noya, Maria | In Progress | 2023-05-23 | Revised | 364 | Standalone | #SC-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) May 18th - this job will go live on Tuesday 23rd - we will close it on Frdiay April 21st 2023 - MN: Troubleshooting last issues that came up during UATs mainly related to the customization on BOPIS and then we will go live probably by beginning of May April 13th 2023 - MN: Troubleshooting last issues that came up during UATs and then we will go live probably end of April/beginning of May Feb 14th 2023 - MN: Offline configurations and started UATs. Working on BOPIS in a different job - consulting hours job. Jan 18th 2023 - MN: Offline configurations. Working on BOPIS in a different job. December 27th 2022 - MN: Offline configurations. Working on BOPIS in a different job. November 4th 20222 - MN: Offline configurations. Will have a new SOW for BOPIS October 17th 2022 - MN: Offline configurations. Working on finish defining scope for customizations. OCtober 2nd 2022 - MN: Working on offline configurations. Client is waiting for estimates to choose from keeping their original idea and having a site only for one location, doing a customization and having the site for both locations or having two separate sites, one for each location. September 18th 2022 - MN: Working on offline configurations. Client is waiting for AMOs estimates to choose from keeping their original idea and having a site only for one location, doing a customization and having the site for both locations or having two separate sites, one for each location. September 5th 2022 - MN: Working on offline configurations. Client is waiting for AMOs estimates to choose from keeping their original idea and having a site only for one location, doing a customization and having the site for both locations or having two separate sites, one for each location. August 18th 2022 - MN; Client is waiting for AMOs estimates to choose from keeping their original idea and having a site only for one location, doing a customization and having the site for both locations or having two separate sites, one for each location. July 29th 2022 - MN: Waiting on the client to figure out if they want all the products on the site or only one location July 16th 2022 - MN: Will have last personalization session and data import session this week. July 2nd 2022 - MN: Will kick off next week. June 18th 2022 - MN: Had Getting ready call, will have check in next Wednesday. June 5th 2022 - MN: Had Sales to PS KT on Thursday 2nd June. | 2022-07-08 | Noya, Maria |  |  | Bazzani, Emiliano |  | 4.75 | 2023-05-23 | 2023-02-28 | 128425059 | 0 | 0 | 321.35 | AMO
J883278 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Hi-Liner Fishing Gear and Tackle, Inc. - Diamond Fishing: Activation - Suit | Onkka, Brady | In Progress | 2030-08-31 | Original | 275 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) Job email: messages.NLCORP.525141801.426cf9a741@nlcorp.email.netsuite.com 5/5/23 - BO - DX and Performance checkpoints created. 4/14/23 - BO - PS3 finished on 4/4 and Drive phase started on 4/5/23. Work started on Hi-Liner, and has started the process of creating Matrix products for both Hi-Liner and Zacatak. Staging domains setup and active for all three sites. No ETA on Diamond. 3/7/23 - BO - Pending client response to confirm when this project will be initiated. I have reached out toTaylar for assistance in moving things forward. Client informed that all three jobs expire in August. 2/28/23 - BO - Client has run into multiple delays due to issues with ERP implementation. Reached out today for update on client readyness. 9/14/22 - Welcome Email sent; customer says they want to start no earlier than October, as they are still going live with ERP 9/6/22 - Sales to PS KT set |  | Onkka, Brady |  |  | Cristobal, Kevin S |  | 65.25 |  | 2030-08-31 | 133947732 |  |  |  | AMO
J883275 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Hi-Liner Fishing Gear and Tackle, Inc. - Professional Services : Activation - 1 | Onkka, Brady | In Progress | 2023-06-19 | Original | 275 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 5/18/23 - BO - Client was running into issues with matrix products this week. ACS successfully provided a solution for the clients Matrix concerns, and client has successfully tested some Assembly Matrix items. Client hopes to have all products setup and ready within the next week and a half. Current delays are linked to Product content and product images. 5/5/23 - BO - DX and Performance checkpoints created. 5/3/23 - BO - Client is experiencing significant issues with SMT. They are currently running into issues where they can not actually access or modify the Skins setting. Client is also running into challenges with Matrix Item setup, looking to create a single solution involving both Inventory and Assembly Items. Working with Support/ACS on the first and ACS on the second. 4/14/23 - BO - PS3 finished on 4/4 and Drive phase started on 4/5/23. Work started on Hi-Liner, and has started the process of creating Matrix products for both Hi-Liner and Zacatak. Staging domains setup and active for all three sites. Google is setup on Hiliner. All Hi-Liner products should be complete by month end. GO live targeted for early June. 3/7/23 - BO - Pending client response to confirm when this project will be initiated. I have reached out toTaylar for assistance in moving things forward. Client informed that all three jobs expire in August. 2/28/23 - BO - Client has run into multiple delays due to issues with ERP implementation. Reached out today for update on client readiness. 1/28/23 - Per Ed Gaw on 1/28/23 "Thank you for your persistence, but we need to slow this down, we still have some major issues with our ERP and WMS go live. We will contact you once we are prepared to move forward. I would anticipate the 3rd week of February. " Moving to Delayed per customer. 11/30/22 - BO - Reached out to client and AMO for updates. Last update from 10/25 from client was they were in the middle of a launch and would follow-up on 11/12 and I never heard anything. 9/23/22 - BO - Client reached out on 9/14 requesting October start, no further updates at this time 9/14/22 - met with the CPQ team. Welcome Email sent; customer says they want to start no earlier than October, as they are still going live with ERP 9/6/22 - Sales to PS KT set |  | Onkka, Brady |  |  | Cristobal, Kevin S |  | 43.25 |  | 2023-06-19 | 133947730 |  |  |  | AMO
J898147 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Infinity Sports, Inc. - Professional Services : Activation - SuiteSuccess for Comm | Krikau, Timothy | In Progress | 2023-08-01 | Revised | 160 | Joint | #SC-PLUSCUSTOMIZATION (tracking tag do not delete) 5/20/23 - TJK - Project schedule has been set to 8/1 as the drop dead date. Resource change has taken place for Functional Lead. 4/18/23 - TJK - Project schedule still at risk due to data issues - should be resolved at the end of the week. 3/13/23 - TJK - Project schedule risk realized due to employee turnover and data integrity issues. 1/18/23 - TJK - Project kicked off, actions assigned. | 2023-04-18 | Joshi, Aarti |  | Cristobal, Kevin S | Marchlewski, Holly |  | 43.25 | 2023-08-01 | 2023-04-03 | 140259506 | 0 | 0 | 37.35 | New Business
J862572 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Think Ink, Inc. - Professional Services : Activation - SuiteSuccess for Commerce | Villa, Myr Angeli | In Progress | 2022-11-28 | Revised | 402 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag) 4/26/23 - MV- UAT is in progress. Request a SOW extension. 4/13/23 - MV - UAT is in progress 9/12/22 - MLV - Go live will move to next month due to customer readiness. 7/25/22 - MLV - On going weekly session. New target go live is on Sep. 21 as discussed with client. 5/23/22 - MLV - GRC done. Created the data based on the design to build document. Client to validate and update the data if necessary. Also waiting for the client to accept the Terms of Service for specific features and bundles. 4/26/22 - Welcome email sent | 2022-06-28 | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 16.25 | 2022-11-28 | 2022-09-21 | 125863789 | 0 | 0 | 331.35 | AMO
J902868 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | 3xLOGIC, Inc. - Professional Services : Activation - SuiteSuccess for Commerce | Komin, Alain | In Progress | 2023-06-26 | Revised | 120 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 4/3/23 - KCRISTOBAL - No kickoff date yet, due to waiting for a staging domain on the customer side 2/17/23 - AKOMIN - GR4C meeting completed. 2/1/23 - AKOMIN - GR4C meeting scheduled for 2/16. 2/1/23 - AKOMIN - Sales to PS KT Done; welcome email sent |  | Komin, Alain |  |  | Cristobal, Kevin S |  | 49 | 2023-06-26 | 2023-05-15 | 142333046 |  |  |  | AMO
J889086 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Equator Coffees, LLC - Professional Services : Activation - SuiteSuccess for Comme | Blakely, Mike | In Progress | 2023-06-14 | Revised | 216 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 5/17/23 - mblakely - client should have been live, waiting customer access list - eta mid-June / site is functional 95% of it is ready to go, just need the b2b customer access list. 2/24/23 AVV: Set job status to in progress to allow time entries to flow through the OA integration before EOQ 1/23/23 mblakely - have solutioned the pcv, images ect for the client now they need to populate customer and item data to drive the personalized catalog views for their customers. 1-3-23 mblakely work is going well with the client - product images is the current project, scoping out customizations in early Jan to FRD and start dev work on. Welcome letter sent | 2022-11-21 | Blakely, Mike |  |  | Cristobal, Kevin S |  | 28 | 2023-06-14 | 2023-04-04 | 136951789 | 0 | 0 | 185.35 | AMO
J894679 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | United Motorsports Online, LLC - SS4C Activation | Lee, Julianne | Monitoring - Post Go-Live | 2023-03-02 | Actual | 174 | Joint | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 3/29/23 JL: Targeting mid-April golive for customization portion. Customer data issues holding up the implementation. 3/02/23 JL: Base webstore is live. Customization in progress. 2/15/23 JL: Current plan is to Go Live without the vehicle finder customization on 3/01. Customization will be deployed post-Go Live once fully tested. 1/05/23 (JL): Customer PM still pushing for Feb-1 go live and challenging SuiteCommerce delivery timeline; wants the SC resource to be more aggressive with tasks. Item search ERP customization will have to be redone and retested to be compatible with the website. 12/09/22 (JL): SuiteCommerce resource assigned; KT and GS meeting with Ray scheduled for next week. |  | Bertorelli, Yvonne A |  | Cristobal, Kevin S | Riccardi, David | 2023-03-02 | 10.75 | 2023-03-01 | 2023-02-28 | 138906914 | 0 | 0 |  | New Business
J874999 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Bull Outdoor Products, Inc. - Professional Services : Activation - SuiteSuccess fo | Onkka, Brady | Monitoring - Post Go-Live | 2023-03-14 | Actual | 329 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 5/19/23 - BO - Client has done initial review of checkout changes, testing was with an invalid product. Still pending further testing. PDP changes currently ready for internal testing. Will review on Monday 5/22. 5/5/23 - BO - Post Go Live performance checkpoint requested. Submitted Cart customization to client for final approval. Removed staging domain. Currently pending signoff on cart and client review of PDP to finish project. 4/12/23 - BO - Client went live on 3/14, post go live ends on 4/18/23 3/10/23 - BO - We have run into several launch delays tied to clients launch readiness. Client was sent over Performance recommendations beginning of the month and we have had several calls reviewing them before client finally decided to wave most of the issues. Email received and copied to job record noting they were not making changes. New launch date is 3/14 at 9am CST> 2/8/23 - BO - FRDs sent for in scope customization, and partial review on this weeks sync call. 12/2/22 - BO - Client is making slow progress on their site. Client didn't make any updates on their pages or products from PS3 until mid November. We are also running into issues with customization due to inconsistencies in Scope. 9/23/22 - BO - Personalization Session 1 concluded on 9/16, next session on 10/4. Reached out to start scoping process on desired customizations. Hoping to use downtime due to scheduling issues at Bull to initiate that process. 9/1/22 - BO - Client confirmed all but one bundle installed. Scheduling PS calls late this week or early next week. 8/19/22 - BO - GR4C call finished, Personalization targeting middle of September. 7/27/22 - BO - KT finished, pending ERP to finish WT 1 so we can set GR4C call. 7/14/22 - BO - Job reviewed, pending KT set for 7/15. 7/5/22 - KSC - Sales to PS KT set | 2022-09-16 | Onkka, Brady |  |  | Cristobal, Kevin S | 2023-03-14 | 10.5 | 2023-03-14 | 2023-01-04 | 130625577 | 179 | 179 | 251.35 | New Business
J895580 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Dugmore & Duncan, Inc. - Professional Services : Activation - SuiteSuccess for Com | Farsedakis, George | In Progress | 2023-07-05 | Revised | 176 | Joint | #SC-PLUSCUSTOMIZATION 4/21/23 - mblakely - we have been working with Jim weekly and Bob shows about once a month. We have categories structured, decided which items to matrix, and the next step is for them to decide their "final" go live selling assortment for the website. 7/5 go live is on track, and we are chipping away at it. 12/5/22- JRH- ERP welcome letter sent |  | Blakely, Mike |  | Bazzani, Emiliano | Haines, Jefferson R |  | 59 | 2023-07-05 | 2023-06-01 | 138996236 |  |  |  | New Business
J895965 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Turf Control LLC - Professional Services : Activation - SuiteSuccess for Commerce | Kayastha, Piyush D | In Progress | 2023-05-22 | Revised | 176 | Standalone | #SC-PLUSCUSTOMIZATION (adjusted) email tag messages.NLCORP.534886873.f638d404cf@nlcorp.email.netsuite.com 2/9/2023 - PK - Getting Ready for Commerce completed. 2/22/2023 - PK - Kickoff call completed 2/28/2023 - PK - Staging domain created 3/2/2023 - PK - Pre-Implementation Web Performance Checkpoint completed 3/3/2023 - PK - Personalization Sessions completed. 3/7/2023 - PK - CSER requested for customization around UPS label integration 3/10/2023 - PK - Data import call completed 3/16/2023 - PK - Process walkthrough call completed, DX follow up, also Case # 5102617 3/21/2023 - PK - Status update call 3/24/2023 - PK - Customer is bringing on employee to assist with SMT, website readiness 3/29/2023 - PK - Case # 5121853 for SMT issue 3/31/2023 - PK - Customer states payment processor should be ready week of 4/20. Potential UAT week of 4/24. Adjusting Go Live | 2023-02-22 | Kayastha, Piyush D |  |  | Bazzani, Emiliano |  | 19.5 | 2023-05-22 | 2023-03-22 | 139039012 | 0 | 0 | 92.35 | New Business
J883277 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Hi-Liner Fishing Gear and Tackle, Inc. - Zacatak Lures : Activation - 2 | Onkka, Brady | Delayed - Per Other Project | 2030-08-31 | Original | 275 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 5/5/23 - BO - DX and Performance checkpoints created. 4/14/23 - BO - PS3 finished on 4/4 and Drive phase started on 4/5/23. Work started on Hi-Liner, and has started the process of creating Matrix products for both Hi-Liner and Zacatak. Staging domains setup and active for all three sites. Karen starting work on Zacatack next week. 3/7/23 - BO - Pending client response to confirm when this project will be initiated. 2/28/23 - BO - Client has run into multiple delays due to issues with ERP implementation. Reached out today for update on client readiness. 9/14/22 - Welcome Email sent; customer says they want to start no earlier than October, as they are still going live with ERP 9/6/22 - Sales to PS KT set |  | Onkka, Brady |  |  | Cristobal, Kevin S |  | 77.5 |  | 2030-08-31 | 133947731 |  |  |  | AMO
J904554 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Classic Alaska Trading/Big Ray's Alaska, Inc. Implementation Service - Fixed Bid | Ueckert, Brant | In Progress | 2023-06-19 | Original | 125 | Joint | #SC-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) |  | Noya, Maria |  | Bazzani, Emiliano | Conor, Katharine S |  | 823.25 |  | 2023-06-19 | 142664761 |  |  |  | AMO
J917663 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Dillanos Coffee Roasters, Inc. - Professional Services : Activation - SuiteSuccess | Kayastha, Piyush D | Assigned |  |  | 28 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 5/4/23 - KSC - KT scheduled |  | Kayastha, Piyush D |  |  | Cristobal, Kevin S |  | 78 |  |  | 148017270 |  |  |  | AMO
J899466 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Blu Distribution LLC - Professional Services : Activation - SuiteSuccess for Comme | Joshi, Aarti | Monitoring - Post Go-Live | 2023-04-17 | Actual | 153 | Standalone | #SC-PLUSCUSTOMIZATION 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. Job Email: messages.NLCORP.539028249.aa56a4aa5d@nlcorp.email.netsuite.com April 17: Client went live on 17th April and post go live support has started. April 10 AJ: Client has pushed go live date to 17th April due to some new data which needs to uploaded and payment gateway integration. March 3 AJ: Client has started with offline configuration. Customization work is in progress. Feb 17 AJ : Personalization 3 completed. Client will have very basic website. Discussed the customization and Feng has started with work. Feb 08 AJ: personalization session 2 Completed. Feb 06 AJ: Personalization Session 1 Completed. Expected Go Live date is March 1st. Created DX task Feb 02: Client is working on action items and PS session 1 scheduled for 6th Feb. Jan 25 AJ: Had meeting with client to go over D2B document. Jan 20 AJ : GR4C meeting completed Jan 17: Welcome letter sent Jan 10 AJ: Sales KT completed | 2023-02-06 | Joshi, Aarti |  |  | Bazzani, Emiliano | 2023-04-17 | 12.5 | 2023-04-17 | 2023-03-08 | 140517525 | 70 | 70 | 108.35 | AMO
J866099 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | CBRC, LLC ¦ SuitCommerce Implementation #SC-CUSTOMIZATION | Prakash, Kiran | Delayed - Per Customer | 2023-05-31 | Original | 381 | Joint | #OPI-CHILD-ECOMM (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) #SC-PLUSCUSTOMIZATION (Tracking Tag. Keep at top of Exec Updates. DO NOT REMOVE) Please refer to Activation Job J865949 for Exec Updates and email communications for this project, as well as documentation files. 30December2022_KP : Job can be started after conclusion of AMO discussions with customer regarding customization SOWs 5December2022_KP : Status for job (J866099) has been updated to Delayed - Per Customer as the customer will need to approve the customization SOWs (ERP +SuiteCommerce), once AMO shares it with customer. 31October2022_KP : Project status changed to Delayed - Per Other Project as actual work on this job can be started only after completion of SuiteCommerce activation (i.e job # J865949 ) 2022/10/26 JDF 50 hours burned before script work, we need to start moving on this and stop having meeting to have meeting. 16Sepember2022_KP : Discussion regarding go live options done with customer. First go-live will be of Native ERP + Native Suite Commerce. Customization will be part of second go-live 22August2022_KP : Discussion done with Swetha Chitrapu (SP) for preparing ERP customization SOW 8August2022_KP : Overview of new customizations given to Leonardo Tuzzo (SP) for preparing SOW 19July2022_KP : List of new customization requested by customer shared with AMO to discuss next steps with customer 11 Jul 22- Internal call on the additional requirements by the customer is setup on 11 Jul. |  | Joshi, Aarti |  | Villaverde, Alfredo | Floyd, Jason D |  | 92 |  | 2023-05-31 | 127333757 |  |  |  | New Business
J902367 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Classic Alaska Trading/Big Ray's Alaska, Inc. - Professional Services : Activation | Ueckert, Brant | In Progress | 2023-06-19 | Original | 125 | Joint | #SC-PLUSCUSTOMIZATION 02152023 BU: Opened job and assigned hours tasks CORPORATE SITE |  | Noya, Maria |  | Bazzani, Emiliano | Conor, Katharine S |  | 50 |  | 2023-06-19 | 142157823 |  |  |  | New Business
J891661 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Get Spiffy, Inc. - Professional Services : Activation - SuiteSuccess for Commerce | Green, Chris | Monitoring - Post Go-Live | 2023-04-10 | Revised | 202 | Standalone | 4/10 CG Confirmed client UAT complete and taxes calculating. Site was transferred to go live domain. Client pending sending access emails internally but site live from implementation perspective 2/10/23 CG Personalization sessions complete. Client however slow to finish imports of item categorization and item master upload templates. Wanting to go live 3/1 ish however this is not likely. Has ongoing ERP as well, payment processing not setup, and an update was requested. Setting call to talk through dependencies for next week 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 11/22 CG - Kickoff call, client wants 2/1 go live 11/18/22 CG - Internal Sales KT, add'l scope only for Ava tax troubleshooting as necessary | 2023-02-06 | Green, Chris |  |  | Cristobal, Kevin S |  | 2.5 | 2023-04-10 | 2023-02-20 | 137768255 | 0 | 0 | 108.35 | New Business
J886253 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Trace3, Inc. - Professional Services : Activation - SuiteSuccess for Commerce | Onkka, Brady | In Progress |  |  | 239 | Standalone | #SC-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) Email tag: messages.nlcorp.527191676.8d503ceaab@nlcorp.email.netsuite.com 5/18/23 - BO - Client is still focused on SCMA, SCMA targeting a late June launch in production. Once this is launched we will be cycling back to this topic. all technical blockers for SCMA have been resolved, still technical blockers (customizations) needed for SS4C. 4/14/23 - BO - Project effectively on hold due to desired customizations and various SSO issues encountered. Customer is focusing on SCMA and most hurdles for that implementation have been addressed. Current concerns center around migrating to production and issues with transaction history. SSO issues appear resolved. 3/10/23 - BO - Due to customization issues/complications client has deprioritized this project. Client may revisit this later after SCMA site is active and in testing in Sandbox. 2/9/23 - BO - Client has 5 customizations they are looking at between ERP and eCom to make this project successful. Currently pending call with client and our dev teams. Once complete we can move straight to Enable/Testing. 11/30/22 - BO - Client has changed targeted customers. Customer has added SCMA to this project. That job is J892082. Client is currently testing PCV, and has run into various roadblocks internally pushing them off their timeline. 11/7/22 - BO - Entering Drive stage 10/20/22 - BO - Completed GR4C last week. Spoke with client this week regarding sandbox use and all main blockers addressed. Sandbox shouldn't be an issue given scope and no live orders. PS1 likely to be first week of November. | 2022-11-07 | Onkka, Brady |  |  | Bazzani, Emiliano |  | 22.25 |  |  | 135635692 | 0 | 0 | 199.35 | AMO
J882104 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Ceek Women's Health, Inc. - Professional Services : Activation - SuiteSuccess for | Joshi, Aarti | Monitoring - Post Go-Live | 2023-04-11 | Revised | 269 | Standalone | #SC-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) Email Tag: messages.NLCORP.523909957.8983aafbe0@nlcorp.email.netsuite.com 04/12/23 AJ : Customer went live on 11th April. Post go live meeting scheduled. 03/17/23: Payment gateway has been integrated and client will start UAT in next week and Go live in following week. 02/17/23: SuiteCommerce configuration is completed. Client is waiting for payment gateway integration to completed and start with UAT test Case 10/28/22 : SuiteDB implementation started and meeting every with team to get the update. Client is currently waiting for Payment gateway configuration to be completed to start the UAT. 09/29/22 AJ: Personalization sessions completed. Weekly meeting scheduled. Client is waiting for Payment Gateway configuration 09/22/22 AJ : Personalization session1 completed. 09/16/22 AJ: Welcome letter sent and sale KT scheduled. | 2022-09-22 | Joshi, Aarti |  |  | Bazzani, Emiliano |  | 9.75 | 2023-04-11 | 2023-01-02 | 133823788 | 0 | 0 | 245.35 | AMO
J868832 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Eternal Beverages, Inc. - Professional Services : Activation - SuiteSuccess for Co | Onkka, Brady | Monitoring - Post Go-Live | 2023-05-01 | Actual | 365 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 5/24/23 - BO - Created Post go live checkpoint, requested a rush as job closes tomorrow. Reached out to Steven and Madison on Onboarding Service, cleaned up staging domain, sent job closure email. *Update Client passed Post Go Live checkpoint. Client still has not responded, leaving relationship at yellow as a result 5/16/23 - BO - Reached out to Jonathan on 5/8 to see if any issues has arisen, with no response. Given clients history I will assume no response is good. Sent email today to note that I will be offically closing the Customization job on Friday and to be notified of any issues by Tuesday of next week as job ends on Thurs. Reached out to AMO and Onboarding to confirm status for that team becoming live. 5/4/23 - BO - Post Go Live Passed 5/1/23 - BO - Client went live today at Noon CST. Clients post go live period will end on job expiration. Client is doing a limited launch, opening up the site to a select number of existing customers to test and validate their setup. Client is debating a few possible phase 2 customization. This customization would add a total weight limit to each order placed. 4/18/23 - BO - As of last call, client noted that their Exec is requesting them to make additonal changes to site which may cause delays. 4/14/23 - BO - Primary contact has become responsive again. Currently targeting a mid May launch date due to last minute exec requested changes and payment provider issues.. 3/17/23 - BO - Spoke with client on 2/27/23, they confirmed the customization is working as intended, things moving forward on their side. Reached out today for an update and to confirm if date for launch known. 2/28/23 AVV - Setting to In Progress to allow time entries to flow through the OA integration 2/9/23 - BO - Client reached out earlier this week confirming he is back and reviewing the customization. hope to restart calls/move this prokect towards a final launch next month? 12/22/22 - BO - Reached out to client via email to confirm customization met requirements and setup new call. 12/16/22 - BO - Feng confirmed Dev work completed and I verified it met or exceeded FRD. Reached out to client to review 12/13/22 - BO - Noticed call schedule ended, reached out to reschedule and for status update 12/6/22 - BO - Client has approved FRD for customization. Passed on to Feng. 9/23/22 - BO - Client making progress on look and feel. Submitted two customizations to AM and requested Opportunity to have SPs finish scoping. First Drive checkpoint on 9/27/22 9/2/2022 - BO - Spoke with client to address their final pre-PS questions. Scheduled PS calls for week of 9/12 and 9/19. We are now back on schedule for launch. 7/27/22 - BO - Client finally responded via email. Waiting to figure out where they are at so we can setup PS1 and move into engage. 7/14/22 - Reached out several times to client to follow-up and confirm their status but no response. Reaching out to AMO. 6/28/22 - BO - We have received no updates from client. 6/17 - BO - Quiet week, leaving job open for other teams to get prep done. 6/9/22 - BO - KT and GR4C calls complete. Engage should be mid to late July 5/26/22 - KSC - Sales to PS KT set |  | Onkka, Brady |  |  | Cristobal, Kevin S | 2023-05-01 | 10.5 | 2023-05-01 | 2022-09-12 | 128323212 | 0 | 0 |  | AMO
J793455 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Jans Ltd ¦ Consulting Time #SC-PLUSCUSTOMIZATION | Rodriguez, Amber | In Progress | 2021-06-07 | Actual | 1014 | Joint | #SC-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 04/07/23 AM - SOW got extended so remaining development tasks can be completed. There is one script that continuously gives us issues that the developers have yet to find out why its not working so the project has been delayed until the issue is discovered. 08/05/22 AM - development ongoing - no issues have occurred 07/12/22 AM - waiting for confirmation from customer on development testing in order to move to production and close job 5/25/22 MKM - 70 hour overage approved SH 5/25/2022: Approved by DL SH 05/25/22: PM requested overage of 70 hours due to development could not proceed on a custom theme without mockups, hours that were not scoped/budgeted. Additionally, there were multiple requirements that were far more complex where the hours provided for the requirement was not enough. So multiple customization went over budget to complete the development of that task. AR 05/06/22: development ongoing - on last development task AR 11/29/21: ongoing development, last remaining dev work is being tested to migrate to production AR 7/21/21: last site went live on 6/7/21 and we are working on post go-live customizations AR 1/14/21: Product issue has been resolved and redo of UAT is underway. VVA go-live set for 1/18/21 and FW go-live may be the week following VVA go-live. AR: No update on case being resolved before 1/12 and go-live will not occur before the new year AR 11/05: Development is near completion for Phase I customizations. QA has already began testing and issues have been reported back to development team. There is one product issue that will currently impact go-live which was originally set for November 18th. AR: 09/22/2020:2 ACS devs and one PS dev has been assigned. There is some conflict on this decision which Martin is further discussing with upper management. we are aiming for FW go-live at mid-november AR: 09/01/2020: Dev assigned and first FRD in progress. QA has been assigned. AR 8/20/2020: SC License provisioned and DX team engaged AR 08/17: Project kickoff scheduled | 2020-09-01 | Rodriguez, Amber |  | Bazzani, Emiliano | Hernandez, Steven | 2021-06-07 | 12.6 |  | 2021-04-30 | 79048191 | 279 | 279 | 996.35 | AMO
J857099 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Banner Wholesale Grocers ¦ Activation - SuiteSuccess for Commerce | Villa, Myr Angeli | Delayed - Per Other Project | 2023-03-13 | Revised | 451 | Standalone | #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 3/29/23 KSC -Job has expired, but ERP is currently not live yet. Will close the job once the customer goes live, as the SuiteCommerce webstore is ready to go at any time. For now, any additional work (if needed) will be logged into the customization job 3/17/23 MV - Go live for ERP was supposedly last week. But according to the customer, they were not able to complete the cutover tasks and go live will probably move for a couple weeks. 2/28/23 - KSC - Go live moved to March 13 9/23/22 - MV - On going offline configuration and site development. UAT will start on Oct.3. 7/25/22- MV - In progress on "data ready" task by the client. ETC: July 28th. 7/15/22 - MV - Took over this job from Jayr. PS is completed. On going weekly session with client. Go live will move to Nov. 1st due to additional customizations that need to be implemented. 3/8/22 - KSC - Welcome email sent 3/3/22 - KSC - Sales to PS KT set | 2022-06-23 | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 17.75 | 2023-03-13 | 2023-01-13 | 122048603 | 0 | 0 | 336.35 | New Business
J807522 | #SC-PLUSCUSTOMIZATION |  | #SC-PLUSCUSTOMIZATION | Van Beek's Landscape Supply LTD. - PS: #SC-PLUSCUSTOMIZATION Activation | Onkka, Brady | Monitoring - Post Go-Live | 2023-04-26 | Actual | 883 | Standalone | #SC-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 23-May-2023 (MC) overage approved 5/19/23 - BO - Client call focused on issues linked to SEO and other performance/Customization issues. Client setting up of Sandbox is needed to address most of those issues. Emanuel should setup a call with me for Tuesday the 30th to resolve. 4/26/23 - BO - CLient went live at 4:30pm on 4/26/23. Post go live support ends on 5/2/23 4/7/23 - BO - Joel confirmed on todays call that our pending customizations are looking good and shouldn't be a blocker for launch. Updated www to take the second https, and waiting for client to provide SSL certificates. Launch is confirmed for 8am CST on the 11th. 24-Mar-2023 (MC) Overage approved 3/10/23 - BO - Shipping customization is pending partner review to address an issue before we can move forward with UAT. Client is moving forward on SEO prep for launch. Pending launch date to be determined in next 2 weeks once Shipping and API testing has completed. 12/2/22 - BO - Focus has shifted to customization job. We are currently working on finalizing the scope and getting agreement on FRD. 9/30/22 - BO - Main focus right now is Customization for shipping. Gonzalo suspects 3 weeks for Analysis phase. 9/23/22 - BO - Shipping job received. Most work will be done on that job, Gonzalo has KT'ed with Seba and now needs to review NeScore documentation. 9/2/22 - BO - Client has multiple additional customizations being requested. this may change us from SC to SCA. Moving client to Red as they are getting progressivly more escalated over delays in shipping and other customization delays. 8/16/22 - BO - Client is currently reviewing if SCA would be a better solution given all the customizations they want/need. 6/26/22 MKM overage approved; Requesting additional hours for this project due to recently discovered issues with Netscore Shipping Solution and changes tied to Inventory requirements causing additional delays. Site Launch still unknown. 6/24/22 - BO - Client is currently in direct talks with Mary and Mary. I am working with them to create a new shipping solution to replace what Netscore was unable to accomplish. 5/20/22 - BO - Waiting on call with Netscore. Moving forward on FRD for new customization. 5/13/22 - BO - We are running into scope creep due to Netscore issues and client changing subsidaries. Look and feel of site is good, all issues appear backend. 4/26/22 MKM - 30 hour overage approved; requesting for overage due to launch being delayed due to ERP complications, NetScore complications, and newly discovered complications with Subsidiary change. 4/25/2022 - BO - Client go live date in limbo due to issues with NetScore (missed setup on their side) and client assumptions due to how SuiteCommerce works. SuiteCommerce does not currently support multi-subsidary accounts. 4/4/22 MKM - overage approved; Client has pushed out release date due to complications with ERP requesting new Personalization Sessions, need hours to cover additional calls/troubleshooting. 4/1/22 - BO - Client concerned over current ERP launch and condition of Shipping and Payment setup. 3/25/22 - BO - Client is requesting a repeat of Personalization Sessions, Client confirmed additional issues and requested to delay launch by 4 weeks 2/25/22 - BO - Client requested we push the launch date out due to delays on their side getting products and other items updated. New date 3/31/22 23-FEB-2022: CS Ops: To update the CS Expiry from 6 term in months to 12 months to align with ToS 2/23/22 MKM - overage approved We are requesting for an overage of 40 Hours to continue working on this project. When it was handed over to us, it only had 15 hours left. We need the hours to: *Continue meeting the customer on a weekly basis. *Work on open issues. *Prepare them for go-live. *Assign DX resources the hours they need to reengage with the client. 2/11/22 - BO - Addressed BOPIS issues with client. Weekly Sync. 1/20/22-JAL-PS has just recently started working with client again. Implementation now on going. 05/17/2021 FL - Job set as "delayed per customer" as we had no response from the last updates requested 04/12/2021 FL - VB’s wants to push Go Live out from 5/3 to fall due to it being their busy season. I have updated the new Go Live to 10/1 but it could be 9/1. We need to set an ecomm meeting to see if we need to push the PDP calculation futher or we can proceed. 03/11/2021 FL - DX team engaged, performance team will be engaged at a later phase as ERP its still being implemented 03/10/2021 FL - Kickoff meeting schedule for march 10th, and personalization sessions to start after this meeting 02/22/2021 FL - Customer working towards Getting ready , once Van Beek´s action items have been completed (SC Web Store Administration training, commerce category tree, item, images), currently we are aiming for a Project Kickoff call for March 2nd 02/01/2021 FL - Welcome letter sent on 1/5, waiting on customers answer, KT with sales completed, ERP starting implementation. Sent email following up on the implementation as customer did not respond. 01/13/2021 FL - Welcome letter sent on 1/5, waiting on customers answer, KT with sales completed, ERP starting implementation. |  | Onkka, Brady |  |  | Cristobal, Kevin S | 2023-04-26 | 4.75 | 2023-04-11 | 2021-10-03 | 88759053 | 0 | 0 |  | New Business
J911844 | #SC-PHASE |  | #SC-PHASE | Honey Stinger ¦ Implementation Service - Fixed Bid | Bertorelli, Yvonne A | In Progress | 2023-06-14 | Original | 64 | Standalone | #SC-PHASE2 5/10/2023 - YB- Development is underway. 4/25/2023 - YB - Met with customer and developer work will begin this week, it is expected that this will take at least 3 weeks for developer work. 4/21/2023 - YB - Customer meeting is set for Monday, there are insufficient hours on this project to complete the work needed, DL, AMO and SP are all aware. 4/4/2023 - YB - Customer wants to get moving per AMO. Currently in the midst of Punchout2Go with this customer on another job. Trying to find time on Leo's calendar for a sales KT, not much information on the job or cs engagement. | 2023-04-24 | Bertorelli, Yvonne A |  | Bazzani, Emiliano | Bazzani, Emiliano |  | 27.75 |  | 2023-06-14 | 145756294 | 0 | 0 | 31.35 | AMO
J897207 | #SC-PHASE |  | #SC-PHASE | G & G Distribution, Inc. dba Ryan’s Pet Supplies ¦ Consulting Time | Bertorelli, Yvonne A | In Progress | 2023-05-24 | Revised | 168 | Standalone | #SC-PHASE2 messages.NLCORP.535652997.e669a4f447@nlcorp.email.netsuite.com 5/24/2023 - YB - Code has been moved to production and customer is performing final smoke test before releasing to their Destination Pets customer. 5/2/2023 - YB - Customer has been testing with Coupa. NetSuite Administrator out on PTO this week so this will delay the go live. He was to provide access to production so we could move the code and get ready for smoke testing but didn't. This will likely add an additional week to the proposed go live. 4/25/2023 - YB - Customer and Coupa are still testing - go live had to move as Richard is out the week of 5/1. 4/21/2023 - YB _ Destinations Pet have tested and call on Monday is to determine when we can move the code to production and plan for launch. 3/31/2023 - YB - Customer is waiting on destination pets to test the functionality. 3/17/2023 - YB - Customer is in the process of testing internally before allowing their actual customer test on their side. 2/15/2023 - YB - We are now at the point where the customer can begin testing the integration. 1/26/2023 - YB - Working with customer and Trade Centric on setup to be able to start testing. | 2023-01-19 | Bertorelli, Yvonne A |  |  | Bazzani, Emiliano |  | 24.75 | 2023-05-24 | 2023-02-28 | 139572477 | 0 | 0 | 126.35 | AMO
J887743 | #SC-PHASE |  | #SC-PHASE | Jersey Wholesale Tire Corporation ¦ Implementation Service - Fixed Bid | Villa, Myr Angeli | Completed | 2023-01-31 | Actual | 226 | Standalone | #SC-PHASE2 (tracking TAG DO NOT DELETE) 3/7/23 MV: Customer confirmed all work is complete and the job can be closed. 2/28/23 MV: Solution has been deployed in production last 1/31. Waiting for customer's sign off. 11/2/22 MV: Done on requirements gathering session. Started FRD and will have a follow up meeting to review the FRD this week. 10/19/22 - Sent welcome email to customer | 2022-11-02 | Villa, Myr Angeli |  |  | Cristobal, Kevin S | 2023-01-31 | 0 |  | 2023-01-31 | 136238515 | 91 | 91 | 204.35 | AMO
J893445 | #SC-PHASE |  | #SC-PHASE | Parts Midwest, Inc. ¦ Implementation Service - Fixed Bid | Kayastha, Piyush D | In Progress |  |  | 185 | Standalone | #SC-PHASE2 (tracking tag DO NOT DELETE) Related SC job: J893446 5/3/2023 - PK - Follow up with customer on readiness or need to utilize this job for customizations. | 2023-01-31 | Kayastha, Piyush D |  | Cristobal, Kevin S | Cristobal, Kevin S |  | 43.75 |  |  | 138540441 | 0 | 0 | 114.35 | AMO
J880420 | #SC-PHASE |  | #SC-PHASE | Golden Supply, Inc. ¦ Consulting Time | Kayastha, Piyush D | In Progress |  |  | 279 | Standalone | #SC-PHASE2 (tracking tag - DO NOT DELETE) Job Email: messages.NLCORP.523639598.394661cc28@nlcorp.email.netsuite.com 8/29/22 - KSC - KT Done. Reached out to RMO for a developer 8/31/2022 - PK - Development task created and assigned to Ilan 9/6/202 - PK - Reach out to POC to request NS access 9/7/2022 - PK - Main POC request clarification on NS access request. 9/12/2022 - PK - Initial call with client and Ilan 9/14/2022 - PK - NS access provided. TradeCentric contacts introduced. 9/15/2022 - PK - Nico informs team of a reusable solution in the works. 9/16/2022 - PK - TradeCentric provides a technical questionnaire that they require us to fill out as they will be assisting us with integration for Golden Supply. Dev team has advised that reusable solution will be potentially ready in 3-4 weeks. Advised client/TradeCentric. 9/19/2022 - PK - TradeCentric advises that Kickoff call can only be scheduled once their Questionnaire is filled out and provided back. Followed up with the team. 10/10/2022 - PK - TradeCentric follows up for update on technical questionnaire. 10/11/2022 - PK - Followed up with Dev team. 10/14/2022 - PK - Ilan advises us that solution is still in UAT with no ETA. 10/17/2022 - PK - Follow up with Nico on status of solution UAT. 10/19/2022 - PK - Nico advises more time is needed for UAT. Informed TradeCentric/Client that we need more time. 10/20/2022 - PK - Customer expresses they do not have a Sandbox environment for us to implement solution. Impacts explained. 10/31/2022 - PK - TradeCentric followed up on status of Questionnaire. 11/2/2022 - PK - Follow up with Nico. 11/3/2022 - PK - Nico advises we will be able to implement on Production with no impact to user experience on the website. Solution is still not yet ready. 11/17/2022 - PK - Follow up with Nico/team. Ilan advises he no longer will be part of the dev team implementing the solution and that we will need to find another resource. Kevin to work with RMO on assigning new Dev resource. 11/21/2022 - PK - Nico advises solution is getting closer to readiness but is on leave soon. We agreed to touch base in December. 11/28/2022 - PK - TradeCentric follows up again on the status of the questionnaire. Advised them that progress is ongoing but the team is on PTO and we will touch base with them in early December. 11/29/2022 - PK - Nico advises solution is ready to be migrated to Production but that they are waiting on 3rd party signoff on UAT. Nico has committed to becoming the main resource for development as a new resource has not been secured. Proposed internal call to align and address TradeCentric questionnaire. 2/28/2022 - KSC - Still working on solution 3/3/2023 - PK - Customer meeting completed. Customer has signed SOW extension, uploaded. 3/10/2023 - PK - Per Nico, I know our reusable solution will not work 100% because it is not compatible with Aconcagua, (SCA version), the part that needs to be reviewed is the extension code only. 1- 100% confirmed the extension needs adjustments to work with SCA Aconcagua. 2- there was a known issue in their sandbox with Aconcagua but it was solved by updating the Extension Management bundle. Nico is currently working on the adjustments for the SCA Aconcagua extension |  | Kayastha, Piyush D |  |  | Cristobal, Kevin S |  | 21.5 |  |  | 133361870 |  |  |  | AMO
J863883 | #SC-ONLY |  | #SC-ONLY | E A GLOBAL TRADING, INC. - Professional Services : Activation - SuiteSuccess for C | Villa, Myr Angeli | Completed | 2022-11-21 | Actual | 391 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2/23/22 KSC: Reaching out to AMO to see if they've heard from the customer. Will be closing the job once I've confirmed client has no other concerns/not responding 10/27/22 MLV: Go live date will move to Nov.2 due to client readiness. 10/25/22 (MC) Overage approved 10/17/22 MLV: UAT is in progress 9/12/22 MLV: Go live will likely move to next month due to client readiness. 7/22/22 MLV: On going weekly sessions, offline configuration and site development. Target Go Live date: 9/26 5/23/22 MLV: GRC call, bundle provisioning and creation of staging website have been completed. To schedule the 1st personalization session by next week. | 2022-06-27 | Villa, Myr Angeli |  |  | Cristobal, Kevin S | 2022-11-21 | -12.5 | 2022-11-21 | 2022-10-31 | 126449776 | 148 | 148 | 332.35 | AMO
J782317 | #SC-ONLY |  | #SC-ONLY | BioStem Technologies Inc - PS: #SC-ONLY Activation - SS4C | Lim, Jerick | Closed - Lost (Rev Rec by Finance) | 2020-11-20 | Actual | 1182 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 12/03/21 - KSC - Customer debooking. Engagement with the customer was good, until a product defect was found that turned the customer off from continuing with implementation 10/21/21 - JAL - Awaiting development to be finished (mL requirement); And fixing some open issues 9/13/21 JAL NS team suggested out-of-the-box features/extensions to make their website look better. Samples were configured in the system. 14 Mar 2021 29 Jan 2021(FC - RR) Customer postponing post go-live meetings 12 Jan 2021(FC) *no movements 28 Dec 2020(FC) *PGL meeting 2 moved to January 14(due to re-scheduled website launch) 8 Dec 2020(FC) *PGL meeting 1 moved from Dec. 8 to Dec 15 20 Nov 2020(FC) *went live at https://portal.biostemtechnologies.com *post go live DX and Performance case created 9 Nov 2020 (FC) *go live scheduled to Nov 17th 30 Oct. 2020 (FC) *Awaiting go-live date from customer 14 Sept. 2020 (FC) *Customer(Matt and Alex) being unresponsive to pending action item follow ups *ERP progress blocking SS4C progress(item updates, change in customer PMs, payment processors) *SC missing commerce categories, items, images, payment processors. *SC PM changed from Pua, Jan to Arellano, Jericho as advised by Kevin(DL) 12 June 2020 (FC) RAG: GREEN Tentative Kickoff: July 13, 2020 12 June 2020 (FC) RAG: GREEN Kickoff will have to be moved to a later date since Jason and ERP team has to do some updates with the items. 10 June 2020 (FC) RAG: GREEN Site is deployed on the staging domain: http://biostem.production.na1.netsuitestaging.com/ 23 April 2020 (DL) RAG: GREEN Adrianne (PM) reported that BioStem wants to complete ERP implementation before their business ramps up again (business slowed down due to COVID). Plan is to start ERP work mid-May. 26 Mar 2020 JJP (PM) RAG: GREEN ERP to kick off this week, waiting for DL to send welcome letter. customer target go live is 2nd week of July | 2020-07-14 | Lim, Jerick |  |  | Cristobal, Kevin S | 2020-11-20 | 10 | 2020-12-01 | 2020-09-01 | 71011407 | 130 | 130 | 1045.35 | New Business
J899275 | #SC-ONLY |  | #SC-ONLY | CPI Card Group Inc. - Professional Services : Activation - SuiteSuccess for Commer | Farsedakis, George | Delayed - Per Other Project | 2023-11-30 | Original | 154 | Joint | #SC-ONLY (tracking tag DO NOT DELETE) 2/15/23- JRH- Welcome letter sent 1/10/23 - Sales to PS KT Set |  | Joshi, Aarti |  | Cristobal, Kevin S | Haines, Jefferson R |  | 79 |  | 2023-11-30 | 140508673 |  |  |  | New Business
J896028 | #SC-ONLY |  | #SC-ONLY | Dana K Newsom DBA The Pinched Pleat - Professional Services : Activation - SuiteSu | Blakely, Mike | In Progress | 2023-09-11 | Original | 176 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. 5/15/23 mblakely - we have the custom lists/item fields setup for dana to load matrix items for her configurable drapes. We will see if she can price and load items. Still concerned that this client signup for more than she can do, she has recently had back surgery and is out of office. 5/1/23 mblakely - in the dozen meetings scheduled with client - Dana has cancled on half of them, the other half we are always re-hashing matrix item setup, it's the only way without CPQ for her to sell drapes in various fabrics, lengths, widths and charge the proper price for them. She has her components loaded as inventory items, now she needs to load the curtains which are matrix and priced by fabric ect. Pricing the drapes via length, width, and fabric is not something Dana has been able to produce (critical to selling drapes online). Will keep pushing client. 1/23/23 mblakely - Client is ecommerce aspirational (not currently selling online) - their project is very complicated (configurable drapes and shades) - this one is likely going to take a long time, and I will express my concern that the ROI with SuiteCommerce might be dificult for this client to attain in year one or two. 12/19/22 - Welcome email sent; Got an automated reply saying that Dana is out until January 2. 12/16/22 - Sales to PS KT Set | 2023-01-26 | Blakely, Mike |  |  | Cristobal, Kevin S |  | 61.5 |  | 2023-09-11 | 139041224 | 0 | 0 | 119.35 | New Business
J887426 | #SC-ONLY |  | #SC-ONLY | Blue Thunder Technologies, Inc. - Professional Services : Activation - SuiteSucces | Onkka, Brady | Monitoring - Post Go-Live | 2023-04-26 | Actual | 231 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 5/12/23 - BO - Call this week, client commented on issues linked to Faceted searches showing up in Google indexing. Recommended client go with Facets as URL parameters. This should resolve that issue. Enabled on 5/12 per request. They are still working with Anchor Group on the DX issue. 5/5/23 - BO - Requested Post go live performance checkpoint. Client failed DX checkpoint due to Anchor Group customizations. Had a call with client and Anchor Group. Anchor Group was finally able to replicate the issue and are working to address. Issue only appears to occur when on HTTPS/Single Secure Domain, if we revert to Dev domain issue goes away. 4/26/23 - BO - Client went live on 4/26/23, reached out to Onboarding to initiate transition. Will request post go live checkpoints tomorrow. Post go live support ends on 6/1/23. 4/10/23 - BO - Moving Go Live back from Red to Yellow as client officially entered Testing phase late March and we officially have a go live date of 4/18 scheduled. 3/16/23 - BO - Client confirmed on todays call that they have received signoff internally on the site but they still have a few steps left before we can trigger performance checkpoint and set launch date. Current holdups is training staff (CS), Correcting some image issues, setting up the redirects on their server, and adding all meta descriptions. 3/7/23 - BO - Currently waiting on Blue Thunder to finish creating all versions of products to sell on the website. Biggest holdup are Matrix and Kit items. They are also reviewing/addressing SEO requirements for their pages. 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. 2/27/23 - BO - Client confirmed they do not have a estimated go live date yet. Running into Pricing and Product creation issues, working with Support to address. Updated Relationship to Yellow to reflect go live delays and client cancelling all calls between 1/30 and 2/27/23. We should know updated go live status on 3/6 or 3/13 call. /2/23/23 AVV: Setting to IN PROGRESS to allow time entries to flow through OA integration 1/5/2023 - BO - Client noted that the may keep some informational pages and only give NS the product/shop pages. Will know more next week. 12/12/22 - BO - Client is running into some internal delays on concerting products to Matrix. As of todays call they have confirmed that Beginning of February is most likely launch window. Updated job. 12/2/22 - BO - Things progressing slowly. Client is finalizing their Matrix look and feel and has been shown how to create Facets. Payment Provider has been setup but not tested. 11/21/22 - BO - Client has finally decided on Manor theme after debating between several different themes 11/9/22 - BO - Personalizaton Sessions finished 10/20/22 - BO - Gettingh Ready For Commerce call held 10/10/22 - KSC -Sales to PS KT set - | 2022-11-04 | Onkka, Brady |  |  | Cristobal, Kevin S | 2023-04-26 | 16.25 | 2023-04-26 | 2023-02-06 | 135975623 | 173 | 173 | 202.35 | AMO
J917139 | #SC-ONLY |  | #SC-ONLY | Washington Diamond - Professional Services : Activation - SuiteSuccess for Commerce | Bertorelli, Yvonne A | In Progress |  |  | 29 | Standalone | #SC-ONLY Email tag: messages.NLCORP.551487061.5261fe7a52@nlcorp.email.netsuite.com |  | Bertorelli, Yvonne A |  |  | Bazzani, Emiliano |  | 78.5 |  |  | 147930534 |  |  |  | AMO
J894085 | #SC-ONLY |  | #SC-ONLY | Bolts Plus Incorporated - Professional Services : Activation - SuiteSuccess for Co | Allaham, Bassel | In Progress | 2023-08-08 | Original | 183 | Joint | #SC-ONLY (tracking tag DO NOT DELETE) 4/7/2023 - YB - Customer has made great progress on the site and we are just waiting on item data to be able to progress further. Customer has 16 stores but BOPIS does not work with scriptable cart so they will need how to move forward with rating on shipping. AMO/PM - need to discuss with customer his options. 2/13/2023 - Had GRC with customer today and they have 16 stores with the expectation to use BOPIS but there are no additional hours in place to work with them on this. They also intend to use PaceJet, no hours for assist with that either. Checked with sales they said SOW was prepared but they did not recall why it was not delivered. This is an OPI project so hoping the PM has some hours to spare in his SOW. | 2023-01-26 | Bertorelli, Yvonne A |  | Cristobal, Kevin S | Conor, Katharine S |  | 52.75 |  | 2023-08-08 | 138675921 | 0 | 0 | 119.35 | AMO
J899468 | #SC-ONLY |  | #SC-ONLY | Striker Brands LLC - Professional Services : Activation - SuiteSuccess for Commerce | Shea, Patrick | In Progress | 2023-07-11 | Original | 153 | Joint | #OPI-CHILD-ECOMM #SC-ONLY (tracking tag DO NOT DELETE) 5/12 PS: Aarti working with Mark to continue with client requirements and continue set ups. 4/21 PS: Pwr Aarti, starting up in May 4/7 PS: Aarti had kickoff with client on 4/6 to begin SuiteCommerce implementation. 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. 3/24 PS: Aarti awaiting reply to schedule kickoff. 3/10 PS: Introduced Aarti to client PM now that WT1s are scheduled. 2/3 PS: See Implementation - Fixed Bid (J899439) for updates. 1/10/23 - Patrick set a Sales to PS KT | 2023-01-30 | Joshi, Aarti |  | Cristobal, Kevin S | Lopez, Faraon |  | 68.25 |  | 2023-07-11 | 140517526 | 0 | 0 | 115.35 | New Business
J900528 | #SC-ONLY |  | #SC-ONLY | Brennan Industries, Inc. - Professional Services : Activation - SuiteSuccess for C | Krikau, Timothy | In Progress | 2023-10-02 | Original | 145 | Joint | #SC-ONLY (tracking tag DO NOT DELETE) 5/22/23 - TJK - SCA CO should be completed and provisioned this week. 4/18/23 - TJK - Change Orders/New SOWs still pending to update to SCA. 3/31/23 - TJK - Scope Misalignment with SuiteCommerce Requirements - Change Orders / New SOWs are pending to go to SCA. 1/10/23 - Sales to PS KT Set | 2023-02-02 | Bertorelli, Yvonne A |  | Cristobal, Kevin S | Marchlewski, Holly |  | 56.25 |  | 2023-10-02 | 140803773 | 0 | 0 | 112.35 | New Business
J843482 | #SC-ONLY |  | #SC-ONLY | Omar Medical Supplies, LLC - Professional Services : Activation - SuiteSuccess for | Joshi, Aarti | In Progress | 2023-06-05 | Revised | 554 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 24-FEB-2022: CS Ops: To update the CS Expiry from 6 term in months to 12 months to align with ToS 05/04/23 AJ: Customer notified the SOW expiry date and have not heard back anything form them also there is not update on action items. 04/21/23: Customer is working on action items and they third party to work Site Content. 04/13/23 AJ : Customer is live with ERP and would like to focus on SuiteCommerce now. They have not worked on any action items so far even after following up multiple times. SOW expiry date has been communicated to them. They are not joining the scheduled meeting as well. Meeting scheduled for 14 April for sync and speed up on this project. 02/23/23 AVV: Setting to IN PROGRESS to allow time entries to flow through OA Integration 02/21/2023 AJ : Client is working on ERP project and would not be focusing on SuiteCommerce as this is not their priority. Currently Inventory is also not uploaded so they want to make sure everything is working fine on EPR side before working on SuiteCommerce Side. Project Status set - Delayed per customer 02/17/23 AJ: All the personalization sessions are completed. Client has to work on all the action items and did not see any progress on action items. 08/25/2022 AJ: Despite numerous follow-ups, I have yet to receive a response from the client. 07/12/22: AJ , Sent mail to install bundles and enable features. Followed up multiple times to schedule PS# session but have not received any response yet. 06/16/2022 AJ: Reached out to customer again and resent the instructions mail. Client does not have training link , hence requested to training team to assist. 05/30/22: Followed multiple times with client to schedule PS sessions but no updates from them. 05/12/22: Discussed with client about next step. Shared all the documents again and waiting for their response to schedule Personalization session. 04/25/2022 AJ: Meeting client on 28th April to discuss the next step. 29 March AJ: Followed-up with client to start the PS# sessions. Waiting for client's response. 2.21.22 VD: got introduced and scheduled GRFC 1.16.22 VD: checking status with ERP team 12.24.21 VD: waiting for ERP to set project plan 12.2.21. Contacted ERP team, waiting pending alignment |  | Joshi, Aarti |  |  | Bazzani, Emiliano |  | 39 | 2023-06-05 | 2030-01-01 | 114743683 |  |  |  | New Business
J869108 | #SC-ONLY |  | #SC-ONLY | Optimum Foods LLC - Professional Services : Activation - SuiteSuccess for Commerce | Joshi, Aarti | Monitoring - Post Go-Live | 2023-04-10 | Revised | 365 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 04/12 : Customer went live on 10th April and post go live meetings are scheduled. Client has ACS 03/01/2023 AJ client is still working on offline configuration and will take sometime. it's been notified to then that SOW will expire on 05/25. 02/17/23 AJ: All the personalization session are completed. Client is working on offline configuration and weekly meeting is scheduled. 10/28/22 - AJ - Website setup is completed and Personalization session scheduled for next week. 9/20/22 - AJ - Getting ready instruction mail has been sent and requested for Bundle Provisioning. 9/16/22 - AJ - GR4C meeting completed. 9/12/22 - KSC - Sales to PS KT set. Welcome Letter sent, as customer said they can engage this week 8/31/22 - KSC - No response from the customer on when this can start 5/31/22 - KSC - Customer wants to start engagement no earlier than July | 2022-10-31 | Joshi, Aarti |  |  | Cristobal, Kevin S |  | 4.5 | 2023-04-10 | 2022-11-30 | 128379956 | 0 | 0 | 206.35 | AMO
J883000 | #SC-ONLY |  | #SC-ONLY | Premier Manufacturing Products, LLC - Professional Services : Activation - SuiteSu | Estellano, Santiago | In Progress | 2023-03-20 | Revised | 267 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) SE: 03-May-23: Client sourcing payment processor. SE: 12-Apr-23: Followed up with client regarding project timeline. Created pre go live checkpoints, account ready for UATs. SE: 25-mar-23: meeting with client, new resource considering project discontinuation. ARR Early warning submitted SE: 28-feb-23: implementing shipping rules customization. UATs will follow customization QA. AV 01/31/2023 - Setting to In progress status to allow time entry to flow through OA SE: 22dec22: informing of DX resource change. Following up with client regarding SOW sent for a side customization. SE: 28nov22: action items complete. Will meet with client for update. SE: 25nov22: client claims non-OOB functionality around Shipping Restrictions was demoed as part of the sales cycle. Internal meeting scheduled to address this SE: 31oct22: client still working through action items SE: 17Oct22: finished personalization sessions. Starting Drive Phase SE: 10Oct22: started personalization sessions. SE: 03Oct22: kickoff delayed due to force majure. SE: 23sep22: had GR4C meeting, sent status report with action items outstanding. DX and performance checkpoints done. Bundles provisioned. SE 06Sep22: changing status to In Progress. Scheduling Sales to PS KT meeting | 2022-10-11 | Estellano, Santiago |  |  | Cristobal, Kevin S |  | 15 | 2023-03-20 | 2023-01-02 | 133935046 | 0 | 0 | 226.35 | New Business
J824097 | #SC-ONLY |  | #SC-ONLY | Golden Max LLC dba Optimal - Professional Services : Activation - SS4C #SC-ONLY | Green, Chris | Completed | 2021-12-07 | Actual | 727 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 24-FEB-2022: CS Ops: To update the CS Expiry from 6 term in months to 12 months to align with ToS 1/7 CG - Client reached out with question around saved search. No major issues to report to date 12/7 CG - Client live after figuring out small issue with converting production domain to webstore and checkout 11/24 CG - SOW extension approved, sent to client 11/23 CG - Check in call with client. Client would like to go live by 12/6. 11/18 CG - Followed up with client on whether there were any questions with tracking number modification I provided. Client needs to populate the new field with a workflow. Also checked on questions with quote issue resolution and requested SOW extension 11/9 CG - Work to attempt to change the tracking number that is pulled into the account center and replace with a field populated within the item fulfilment record of the sales order. Attempted to use sourcing to populate this field, however this will not works since IF record is not selected in SO form. Created a field intended for client to push the data into and informed of potential to do it via workflow 10/22 CG - Met with client to review remaining deliverables. Client had question on why quote requests wouldnt work with non inventory items. Looking into this. Provided UAT doc for client review 9/24 CG - Follwed up with Chris and team on info needed to answer a question regarding lead time 9/13 CG - CSS adjustments to page and testing as requested from client via email. Client requested various items be removed from account center including fields in SO, links for transaction history and others 9/2 CG - Worked on way to remove recent purchases from Overview page and add purchase order detail to purchase history table 8/31 CG - Call with PaceJet AM and Client to review functionality needed to setup PaceJet on webstore. Confirmed client will look into PaceJet extension for SC to enable functionality. PaceJet team to take point on config. 8/20 CG - resolved a few configuration issues around PCV working with contacts attached to a customer record, and checkout page loading as intended. Client nearly ready for UAT. 8/6 CG - P session 3 today. Ran into issues with site configuration which required assistance from Patrick. Fixed config but was unable to cover extensions in SMT. Client to begin working on site assets, and should be confirming any extensions they will have a particularly important use for to ensure we review specific functions. 8/3 CG - P session 2 held today, action items sent in follow up 7/28 CG Personalization session1 held today. Action items sent in follow up 7/26 CG - Held kickoff, noted client had some misunderstandings around timelines and how prepare phase is structured requiring completion of providing specific assets before starting project. Client very adamant on hitting early Sept go live. Revised delivery to provide "working" rendition of site in early August. Client understands some assets will not be ready for final go live and is ok with this. 7/21 CG - Client rescheduled kickoff session to Friday but unable to accommodate. Proposed Monday 7/14 CG - Client replied noting they are 70% done with web admin training. Noted webstore domain to be optimalmax.com. Set pre kickoff call checkpoint today to confirm they dont want to use subdomain and answer any questions with D2B requirements. 7/9 CG - Client has not responded in some time. Missed first Kickoff window. Need to confirm domain for DX audit. Needs follow up. Needs project plan. 7/6 CG - Pre-Implementation checkpoint requested. Admin provided to Max Vazquez. Still waiting to confirm domain from client for DX checkpoint. Client also likely pushing kickoff date due to not providing this detail and completing web admin training 6/25 CG - Completed bundle/extension install, wssr creation, linked ssp apps to dev domain, create fieldsets, activated summit theme and extension 6/24 CG - Bundles have been provisioned. Emailed client to install. Cient noted issues accessing training. I provided learning portal link and they will let us know if they have further trouble 6/17/21 CG - Kickoff call today, sent follow up including theme guide | 2021-06-17 | Green, Chris |  | Villaverde, Alfredo | Villaverde, Alfredo | 2021-12-07 | 1 | 2021-12-06 | 2021-08-26 | 100255219 | 174 | 174 | 707.35 | AMO
J807015 | #SC-ONLY |  | #SC-ONLY | The Key Dot Company LLC - PS : #SC-ONLY Activation - SS4C | Lim, Jerick | Closed - Lost (Rev Rec by Finance) | 2021-04-23 | Original | 883 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE-KEEP AT TOP OF EXEC UPDATE) 8/14/21 EJA - Customer decides to not move forward with SC given the amount of work needed to configure with SC 7/23/21 EJA - New Tentative Go-Live date: Aug 17 7/6/21 - KSC - customer still setting up items 6/14/21 EJA - SoW Extension Signed 6/10/21 EJA - Ecommerce still waiting for Item Setup 5/26/21 EJA - Customer still working on their Items, new checkin scheduled for next week 4/12/2021 - EJA - Weekly Checkin 3/31/2021 EJA - Data Migration Session 3/30/2021 - EJA - Personalization Session 3 3/29/2021 - EJA - Personalization Session 2 3/24/2021 - EJA - Personalization Session 1 3/23/2021 - EJA - Kickoff Call 3/11/2021 - EJA - Progress Meeting done, scheduled Kickoff for March 23 3/4/2021 - EJA - Getting Ready for Commerce Call done 2/25/2021 - EJA - Sales to PS KT done | 2021-03-23 | Lim, Jerick |  |  | Cristobal, Kevin S |  | 26.75 |  | 2021-04-23 | 88364753 | 0 | 0 | 793.35 | New Business
J882606 | #SC-ONLY |  | #SC-ONLY | BTek Holdings LLC - Professional Services : Activation - SuiteSuccess for Commerce | Kayastha, Piyush D | Delayed - Non Responsive | 2022-11-28 | Original | 267 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 4/11/23 - KSC - EWS made due to non-responsive customer 4/3/23 - KSC - reaching out to the account manager to see if they've heard from this customer 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. 9/1/22 - KSC - Sales to PS KT Done 9/2/202 - PK - Follow up with ERP PM to gauge client and integration readiness and confirm potential ERP Go Live timeframe 9/6/2022 - PK - Follow up with ERP PM again. 9/15/22 - KSC - Welcome letter sent 9/19/2022 - PK - GR4C completed. Bundle Provisioning in Progress. DX task creation in progress. Kickoff call tentatively scheduled for 9/27/2022 9/27/202 - PK - Web Performance Pre Implementation Analysis requested 9/30/2022 - PK - Customer affected by Hurricane Ian and lost power. Reschedule Kickoff. 10/3/2022 - PK - Customer affected by Hurricane Ian and lost power. Reschedule Kickoff. 10/5/2022 - PK - Customer affected by Hurricane Ian and lost power. Reschedule KIckoff. 10/11/2022 - PK - Kickoff call completed. Customer has experienced delays due to Hurricane Ian that has set back their ERP Go Live as well as VersaPay implementation. Progressing normally otherwise. 10/20/2022 - PK - Personalization Sessions completed. Client needs more time to get their Items into NetSuite. Data Import session pending. Status Update call scheduled for 10/25/2022 10/27/2022 - PK - Client still not ready for Data Import session. Rescheduled. 10/31/2022 - PK - Follow up with customer on proposed time slot. 11/2/2022 - PK- Follow up with customer. 11/7/2022 - PK - Status Update call 11/9/202 - PK - Customer still not ready for Data Import session. 11/11/2022 - PK - Follow up with customer. 11/17/2022 - PK - Follow up with customer. 11/21/2022 - PK - Follow up with customer. Customer advises they may be more ready by tomorrow. 11/23/2022 - PK - Follow up with customer, copy AMO. 11/26/2022 - PK - Customer has provided first draft of Commerce Categories. However, items are not yet loaded in NetSuite. 11/28/2022 - PK - Commerce Categories being loaded. Follow up with customer. 12/1/2022 - PK - Requested GTM/GA Access for new DX resource. 12/5/2022 - PK - Follow up with customer on Items readiness for webstore. 12/6/2022 - PK - Follow up with customer 12/8/2022 - PK - Follow up with customer 12/16/2022 - PK - Follow up with customer 1/3/2022 - PK - Follow up with customer 1/6/2022 - PK - Follow up with DL/AMO 1/13/2023 - PK - Meeting with customer 1/18/2023 - PK - Follow up with DX 1/20/2023 - PK - Follow up with customer 1/23/2023 - PK - Follow up with customer 1/31/2023 - PK - Follow up with customer, copy AMO/DL 2/1/2023 - PK - Follow up with customer, copy AMO/DL 3/8/2023 - PK - Engage AMO and DL to help us reach out to non-responsive customer. | 2022-10-11 | Kayastha, Piyush D |  |  | Cristobal, Kevin S |  | 14.75 |  | 2022-11-28 | 133887294 | 0 | 0 | 226.35 | New Business
J864412 | #SC-ONLY |  | #SC-ONLY | E A GLOBAL TRADING, INC. - Professional Services : Activation - SuiteSuccess for C | Villa, Myr Angeli | Completed | 2022-11-21 | Actual | 391 | Standalone | #SC-ONLY (tracking tag - DO NOT DELETE) 10/27/22 MLV: Go live date will move to Nov.2 due to client readiness. 10/6/22 MLV: Website walkthrough and UAT Prep discussion done. Client will start on UAT (10/6). 9/12/22 MLV: Go live will likely move to next month due to client readiness. 7/22/22 MLV: On going weekly sessions, offline configuration and site development. Target Go Live date: 9/26 5/5/22 - Sales to KT done; Welcome email sent | 2022-08-29 | Villa, Myr Angeli |  |  | Cristobal, Kevin S | 2022-11-21 | -1.5 | 2022-11-21 | 2022-10-31 | 126564384 | 85 | 85 | 269.35 | AMO
J918366 | #SC-ONLY |  | #SC-ONLY | Hunter's Reserve, Inc. - Professional Services : Activation - SuiteSuccess for Com | Kayastha, Piyush D | In Progress |  |  | 27 | Standalone | #SC-ONLY email tag:messages.NLCORP.551916010.07af52e1e8@nlcorp.email.netsuite.com |  | Kayastha, Piyush D |  |  | Bazzani, Emiliano |  | 70.5 |  |  | 148097619 |  |  |  | AMO
J812434 | #SC-ONLY | #POS-NSPOS-ONLY | #SC-ONLY #POS-NSPOS-ONLY | UC Santa Cruz ¦ Book Implementation - Fixed Bid | Raghavan, Vidhya | Monitoring - Post Go-Live | 2022-01-01 | Actual | 819 | Joint | #SC-ONLY (TRACKING TAG - DO NOT DELETE) #POS-NSPOS-ONLY #CAMPUS (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2023 0518 VR: POS Server provisionng still not complete. 2023 0508 VR: Waiting for POS server to be provisioned. Following up daily with the POS Prod team. 2023 0427 VR: CBORD Odyssey dev completed. Awaiting POS server for Internal dev acct to be provisioned. 2023 0413 VR: CBORD still in progress. 2023 0316 VR: CBORD still in progress. Coordinating with CBORD team to test. 2023 0306 VR: CBORD still in progress. Coordinating with CBORD team to test. 2023 0222 VR: CBORD still in progress. Coordinating with CBORD team to test. 2023 0124 VR: CBORD still in progress. Coordinating with CBORD team to test. 2023 0105 VR: Extension approved. CBORD testing in progress. 20221206 (TDC) - PM changed to Vidhya 20221122 (TDC) - CBORD work assigned to Ilan Daniel. Ilan will be advising on target completion date. 20221028 (TDC) - Put in job extension request. CBORD work is commencing. 20220908 (TDC) - Marking as delayed - waiting word on CBORD 20220616 (TDC) - keeping job open for CBORD 20211012 (TDC) - Met with Doug. They are resource challenged. Agreed to move go-live to Dec 1 to allow them more time for data loads and testing. 20211004(TDC) - Client is to be starting UAT but delayed. Planning for Nov 1 golive 20210429 (TDC) - Walkthrus in progress. Team is working on the integration next steps. They were lagging on data, but we discussed actions needed. | 2021-03-24 | Gibson, Donald H | Bazzani, Emiliano | Bazzani, Emiliano | Raghavan, Vidhya | 2022-01-01 | 56 | 2022-01-01 | 2021-07-01 | 92914593 | 283 | 283 | 792.35 | New Business
J875586 | #SC-ONLY |  | #SC-ONLY | Stern Real Estate LLC - Professional Services : Activation - CAT | Komin, Alain | In Progress | 2030-06-13 | Revised | 326 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 05/19/2023 AKOMIN: Site is delayed waiting for the new Job to expose an external form to register users but not grant them access. 5/1/23 - BO - Moved Schedule to yellow as we currently don't have an expected launch date 5/1/23 - BO - Client noted on todays call that they are running into issues locating the correct access controls for this site. We are currently reviewing these requirements to locate the correct solution. GO live cant be scheduled until this issue is addressed. 3/7/23 - BO - New launch date is set for 5/9 due to the non SuiteCommerce issues noted below. 2/27/23 - BO - Client noted that due to delays / complications they have run intro migrating one of their partner tools to NetSuite from Magento. Tradecenter requires a custom API to be built and they cant fully migrate off Magento until thats migrated. CAT hosts all their Magento setups, hence the delay. Should know by EOD today if delayed from 2/28/23 to May 23 1/17/23 - BO - Client confirmed this will be the last site to launch. Set right now for 2/22, but if any other site causes delays this will be pushed back. | 2023-01-13 | Onkka, Brady |  |  | Bazzani, Emiliano |  | 57 | 2030-06-13 | 2023-02-28 | 130905481 | 0 | 0 | 132.35 | AMO
J881629 | #SC-ONLY |  | #SC-ONLY | Solar Cellz USA LLC - Professional Services : Activation - SuiteSuccess for Commer | Joshi, Aarti | In Progress | 2023-07-24 | Original | 271 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) Job email: messages.NLCORP.524373622.df80ef0ae8@nlcorp.email.netsuite.com 4/17/23 MV: Offline configuration and site asset development is in progress. 3/17/23 MV: Personalization Sessions done. Weekly meeting checkpoint will start next week. 2/10/23 MV: Took over job from Aarti. Set up a meeting with the customer by next week to discuss the project updates. AJ: Bundle has been installed by customer and sub domain received. AJ: GR4C meeting completed 9/7/22 - KSC - KT done; welcome email sent 8/31/22 - KSC - Sales to PS KT set | 2023-03-17 | Joshi, Aarti |  |  | Cristobal, Kevin S |  | 31.5 |  | 2023-07-24 | 133755686 | 0 | 0 | 69.35 | New Business
J888318 | #SC-ONLY |  | #SC-ONLY | YourGreen2Go, Inc. - Professional Services : Activation - SuiteSuccess for Commerce | Crabtree Blair, Allexis | In Progress | 2023-10-04 | Original | 217 | Joint | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 5/18/23 - mblakely client (David) is now suggesting a slow cut over for ERP - the ERP job is really taking a long time per the client. The client is bringing in a partner to help on the ERP implementation. 5/8/23 mblakely David is still very slow, I have helped to get customers and items ready for ERP imports, but we are still just waiting on erp data setup. 3/17/23 mblakely still waiting on client (David) to get further in ERP setup - site will require some PCV, but client is veyr slow to implement erp/load items. |  | Blakely, Mike |  | Bazzani, Emiliano | Seth, Pooja |  | 65.25 |  | 2023-10-04 | 136579567 |  |  |  | New Business
J914290 | #SC-ONLY |  | #SC-ONLY | Sparton of Canada, Limited ¦ Activation - SuiteSuccess for Commerce | Villa, Myr Angeli | In Progress |  |  | 55 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 4/17/23 - KSC - Welcome Email sent |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 78 |  |  | 146304237 |  |  |  | AMO
J895196 | #SC-ONLY |  | #SC-ONLY | C.D.S. Moving Equipment, Inc. - Professional Services : Activation - SuiteSuccess | Blakely, Mike | In Progress |  |  | 177 | Standalone | 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. #SC-ONLY (tracking tag DO NOT DELETE) 5/18/23 mblakely - working well with Eddie (project lead) - going back to green on everything but schedule. 5/4/23 mblakely - had intro call, client wants to do quite a bit with PCV and not showing/showing prices, also calling concern for multi location inventory and fulfilment. Client has a closed lost ss4c job from 2021-2022 where 50 hours was done, so we will see what we can reuse. But calling concern for scope/product with SC vs SCMA possibly. 5/3/23 mblakely Pat no showed for our intro call, rescheduling (low confidence given how hard this job has been to get started) we will push but Summer and Fall have to be very productive to get client live in October. 5/1/23 mblakely holy smokes Pat Higgins responded intro call secheduled for 5/2 it's a May 1st miracle! 5/1/23 mblakely - I have called and emailed the client a dozen times, and unable to set up the intro call, being very transparent with Aaron & Pat at CDS that we are five months into a year project, and need to get it going. 4/5/23 mblakely Aaron Barwick has given me the contact phiggins@cds-usa.com to engage on the project, Pat Higgins has not responded in a week. Emailing again. 3/13/23 mblakely engaging AMO as Aaron Barwick has gone radio silent 3/1/23 mblakely engaging Aaron Barwick again to restart project 1/23/23 mblakely emailed and had a phone call with Aaron Barwick - they do not have a resource on their team to take on the project, they need to hire someone, so it likely won't happen as fast as expected in the sales cycle, but pushing client to start working on it. 12/16/22 - Sales to PS KT Set |  | Blakely, Mike |  |  | Cristobal, Kevin S |  | 75 |  |  | 138972048 |  |  |  | AMO
J878469 | #SC-ONLY |  | #SC-ONLY | NUOVA DISTRIBUTION U.S.A., L.L.C. - Professional Services : Activation - SuiteSucc | Zafe, Ivy Marie | In Progress | 2023-06-01 | Revised | 297 | Joint | #SC-ONLY #OPI-CHILD-ECOMM (tracking tag DO NOT DELETE) 4/27/23 IEZ - Nuova is waiting for Anchor Group to complete three tasks: -Upload the website design/layout/template -Remove the reviews section -Fix a specific detail with product photos 4/25/23 - BO - Moving job to In Progress to log my hours for a call with client back on 4/14/23 4/06/23 IEZ Client requested to just have 2x a month call as they are having their consultation with Anchor group 3/3/23 IEZ Client would like to place project on hold. But will retain a bi-monthly status call for alignment. 2/8/23 IEZ Julian, Client EVP, mentioned they recently engaged with Anchor Group. NS PM set up Sponsors meeting to align with expectations. NS Sponsor and AMO will be joining the call on Feb 9th 1/31/23 IEZ Client POC for SuiteCommerce already in contact with 1/19/23 IEZ Ongoing UAT. Clinet would like ERP to golive with SuiteCommerce, deferring ERP go-live date 1/13/23 IEZ Ongoing UAT issues resolution. Clinet would like ERP to golive with SuiteCommerce, deferring ERP go-live date 1/5/23 IEZ Marcus, Nuova's PM, resigned. Kyle and Julian, EVP for sales to take over. IEZ already requested available dates/times from Brady to be proposed to client 12/30/22 IEZ Project on hold 12/20/22 IEZ Project on hold 12/1/22 IEZ Project on hold. Client hasn't confirmed resumption on this implementation for this year 11/17/22 IEZ Project on hold. Marcus on medical leave 10/17/22 - BO - Ivy confirmed project ready to move forward. Reached out to client to schedule GR4C Call. 10/03/22 IEZ Project on hold per Other Project. 9/16/22 IEZ Project on hold per Other Project. 8/26/22 IEZ Project on hold per Other Project. 8/19/22 IEZ Project on hold per Other Project. 8/10/22 IEZ Project was transitioned to another PM. Following up previous resource on notes to KT, but no response yet 8/3/22 - Sales to PS KT Set |  | Onkka, Brady |  | Cristobal, Kevin S | Vidhyarthi, Lohit |  | 57.5 | 2023-06-01 | 2023-04-03 | 132267140 |  |  |  | New Business
J868518 | #SC-ONLY |  | #SC-ONLY | Fit Supply, LLC - Professional Services : Activation - SuiteSuccess for Commerce | Noya, Maria | In Progress | 2030-01-01 | Original | 367 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) May 18th - MN: Unresponsive customer - will be closed at expiration May 23rd April 13th 2023 - MN: The customer is working on their categories, item category association and filling out the custom fields we created. The customer is very slow, they don't have a lot of help and doesn't give priority to the website. March 13th 2023 - MN: Resumed implementation. Finding workarrounds to suggest the other version of each items. Feb 14 2023 - MN: Resuming implementation this week Jan 18th 2023 - MN: waiting for SOW from SC and ERP for changes needed on items - matrix items and warranty options December 27th 2022 - MN: weekly status. Delayed implementation because customer needs matrix items and a customization and they are getting estimates from partners. Nov 4th 2022 - MN: weekly status, still scoping customizations - delayed because change in AMO October 17th 2022 - MN: having weekly sessions. Offline configurations. Scoping some customizations. October 2nd 2022 - MN: had all personalization sessions, data import sessions. Offline configurations. Started weekly status sessions. September 18th 2022 - MN: Kicked off and had first 2 personalization sessions. We will have the third session and data import session the upcoming week. September 5th 2022 - MN: Client is working towards becoming data ready. We will kickoff in the next two weeks. August 18h 2022 - MN: Client is working towards becoming data ready. We will kickoff beginning of September. July 29th 2022 - MN: Waiting for the client to be data ready. July 16th 2022 - MN: Waiting for the client to be data ready. July 2nd 2022 - MN: Waiting for the client to be data ready. June 18th 2022 - MN: Waiting for client to be data ready. June 5th 2022 - MN: Had KT and Getting ready call the past week. Will kickoff in 2 weeks. | 2022-09-13 | Noya, Maria |  |  | Bazzani, Emiliano |  | 21.5 |  | 2030-01-01 | 128244005 | 0 | 0 | 254.35 | AMO
J825072 | #SC-ONLY |  | #SC-ONLY | Featherstone Foods Inc. - Professional Services : Activation - SuiteSuccess for Co | Blakely, Mike | Closed - Lost (Rev Rec by Finance) | 2022-11-15 | Revised | 725 | Standalone | #SC-ONLY (tracking tag) 9/13/22 - KSC - job has expired. Working on a new CO that will allow us to continue with implementation (in addition to a new CO for customization) 8/29/22 - mblakely - erp keeps getting delayed, delayed, delayed on 4th change order for project – estimated November ERP go live. Client is having some Suitecommerce customizations scoped with Leo. Overall the project is just going no where fast, and client has never done eCommerce before. Action – filling an extension. 8/23/22 - mblakely - client is not yet live on erp, filing an extension, client hopes to be live in November with ERP - going to phase out SuiteCommerce starting with "My Account"/Bill Pay then fast follow full ecom. Client does zero ecommerce today so it will be a learning curve. 7/21/22 - mblakely - been meeting with client weekly - we have an intern working on item titles, images are still a concern, Lisa Stefanoff is a rockstar, but the catalog is not her show - Lisa Saltzman is responsible for catalog and she's hard to pin down. 6/17/22 - mblakely - client often cannot make meetings - has not been able to get any product images for six weeks. 4/29/22 - mblakely - working on the site, client has been focused on ERP implementation 3/31/22 - mblakely - imported categories, and enabled products, showing site to client 3/31 3/11/22 - mblakely erp delayed till May, stating to work with client end of march on calendar 24-FEB-2022: CS Ops: To update the CS Expiry from 6 term in months to 12 months to align with ToS 2/3/22 - mblakely client erp is not expected to go live to march at earliest in a holding pattern 1/17/22 - setting schedule to yellow because erp implementation delayed a quarter will be close to a year for go-live. 1/7/22 - KSC - go-live delayed due to ERP not yet ready for go-live 12/6/21 - mblakely 1st schedule go live is tomorrow, client is not live on erp yet, setting for 90 days out 12/3/21 mblakely - met with client had intro- client needs payment processor - 11/17/21 RR - KT with Trisha 11/10/21 RR - customer leaning towards not having matrix items 10/28/21 RR -progress meeting with customer on Nov 3 10/26/21 RR - GRFC part 2 on Oct 27 10/22/21 RR - GRFC 10/12 - RR completed KT with Jacob. To reach out to customer to set GRFC. 8/30 - JD - Coordinating KO with customer team 6/24/21 - KT done; Has an ongoing ERP job; Will reach out to ERP PM for updates on their end 6/21/21 - Sales to PS KT set; |  | Blakely, Mike |  |  | Cristobal, Kevin S |  | 41 | 2022-11-15 | 2021-12-07 | 100334439 |  |  |  | New Business
J871999 | #SC-ONLY |  | #SC-ONLY | Holosun Technologies, Inc. - Professional Services : Activation - SuiteSuccess for | Mohammed, Riyazuddin | Monitoring - Post Go-Live | 2023-05-30 | Revised | 359 | Joint | #OPI-CHILD-ECOMM (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 5/17 Waiting on customer to complete open items from his end. 5/1 Customer is working on Open tasks 4/8 Working sessions in progress with customer 3/29 Working sessions in progress with customer 3/17 weekly connect schedule to complete open items 3/13 follow up call on 3/14 will decide action items on this call 2/27 customer informed they are only available during march 14 to work on questions/ open points call scheduled Once the action items completed from customer, we would do WT2 and UAT 2/13 Customer is working on action items Santi is back and taken over the job Aarti doesnt have bandwidth hence santi will continue This change would or may go for little over age 1/31 Customer requested few weeks to work on Open items Once done UAT will start weekly 30 misn follow up 1/23 Resource change Introduction today and Planning for next steps Aarti has scheduled a call 1/9 Resource change - scheduled KT Session 12/27 Customer will start this in 3rd week of Jan - However requested a call in 1st week of Jan to understand open questions . 12/12 Putting this on Hold since customer requested to complete EPR and WMS First and will take care of this later in next few weeks 11/23 - This will start after Go Live from dec 1st week 11/4 This will be taken care post Go Live 10/24 • Suite Commence – We will be Live with Suite Commence After ERP/WMS Go Live after 11/1 • Configuration DKIN – Sean to follow up on this and update NS Team • XPS – Sean to reinstall in Sandbox and Prod • Sandbox refresh by @Ronald Ric Diaz by 10/15 • UAT – 10/17 start date. UAT in Progress - WMS to start from 10/24 10/10 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Completed, Santi is working on Dev work now, Santi sent email to customer asking for pending config from Holosun and waiting for update . Target date 9/30 Customer wants to check if he can Go Live with this or can do Post ERP and WMS Live in NS. Santi to join weekly connect to discuss on it. 9/26 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Completed, Santi is working on Dev work now, Santi sent email to customer asking for pending config from Holosun and waiting for update . Target date 9/30 9/12 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Completed, Santi is working on Dev work now, Santi sent email to customer asking for pending config from Holosun and waiting for update . 9/2 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Completed, Santi is working on Dev work now 8/19 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Session will be scheduled by Santi from Aug 3rd Week of August based on Customer request 8/12 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Session will be scheduled by Santi from Aug 3rd Week of August based on Customer request 8/5 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Session will be scheduled by Santi from Aug 2nd week 07/28 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Session will be scheduled by Santi from Aug 2nd week 07/14 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Session will be scheduled by Santi. 07/11 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Kick off call completed with customer Update - PS Session will be scheduled by Santi. 06/23 Recent Accomplishments : Internal meeting with ERP and Suitecommerce team. Update - Introduced Santi over ERP Kick off call, Informed customer would have short kick off call on SuiteCommerce as requsted by Santi Next Steps : Kick off call next week 06/27 week | 2022-06-23 | Estellano, Santiago |  | Bazzani, Emiliano | Gosnell, Steve |  | 11.5 | 2023-05-30 | 2023-04-03 | 128725598 | 0 | 0 | 336.35 | New Business
J813489 | #SC-ONLY |  | #SC-ONLY | Par One Inc - PS : #SC-ONLY Activation - SS4C B2B | Noya, Maria | Completed | 2030-01-01 | Revised | 814 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) September 5th 2022 - MN: Pending client answer on going live or new job to go live once SEO error is fixed. Still: *Missing manual SSL certificate (sent several certificates - none with the conditions on SuiteAnwsers) *SEO issue - caused by a third party integration August 17th 2022 - MN: Client has everything ready for go live except for two things: *Missing manual SSL certificate (going to get one) *SEO issue - caused by a third party integration Other than that they are ready for go live. They don´t want to go live without fixing the issue but we are near SOW expiry date. IMPORTANT : SOW expiry date is September 1st. July 29th 2022 - MN:working on last adjustments from DX and WP. Will go live the second week of August. July 16th 2022 - MN: Working on pre go live DX and Web performance checkpoints recommendations. July 2nd 2022 - MN:Final configurations. Working on customer doubts through email. Waiting for the customer to feel ready for go live. June 18th 2022 - MN: Final configurations. Working on customer doubts through email. Waiting for the customer to feel ready for go live. June 5th 2022 - MN: Final configurations. Working on customer doubts through email. May 22nd 2022 - MN: Waiting on client to be ready May 9th 2022 - MN: Answering customer doubts through email April 25th 2022 - MN: Answering customer doubts through email April 7th 2022 - MN: Answering customer doubts through email 25/03/2022 - MN: Answering customer doubts through email Status update: Overall project status: Yellow Schedule - More than one year from active date 14/03/2022 - MN: Job transferred from JAL to MN. Answering customer doubts through email while waiting for the customer to define if they will include more integrations or customizations. 24-FEB-2022: CS Ops: To update the CS Expiry from 6 term in months to 12 months to align with ToS 1/20/22-JAL-Customer is planning to put in more integrations and customizations. 10/21/21 JAL - Working on remaining action items. The customer is also working with NetScore on customizations 9/20/21 JAL Go-live will be moved. Awaiting CPQ(Customization) from NetScore. 8/26/21 EJA - Signed SoW Extension doc uploaded 8/25/21 EJA - SoW Extension sent to Jackie 8/21/21 EJA - SoW Extension filed today 8/18/21 EJA/JAL New Tentative Go-Live date is 9/13/2021 8/4/21 EJA - New Tentative Go-Live date is August 24 7/28/21 EJA - Tentative go-live date is August 11 6/28/21 EJA - Scheduled Shipping Option meeting 6/10/21 EJA - All Personalization Sessions done; Going through weekly check-ins; tentative go-live date June 25th 5/11/2021 - KSC - kickoff tomorrow 3/31/2021 - EJA - Progress Meeting 3/24/2021 - EJA - GRFC Call 3/16/2021 - EJA - GRFC Call Scheduled for next Wednesday 3/15/2021 - Sales to PS KT done; Welcome letter sent to client |  | Noya, Maria |  |  | Cristobal, Kevin S |  | 5.5 | 2030-01-01 | 2021-05-24 | 93240840 |  |  |  | AMO
J895797 | #SC-ONLY |  | #SC-ONLY | S4 Lights, Inc. - Professional Services : Activation - SuiteSuccess for Commerce | Graham, Sean | In Progress | 2023-07-10 | Revised | 176 | Joint | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 5/22/23 - mblakely setting this job to "all yellow" item setup is taking forever, coupled with missing the pim in the sales cycle, and just general client sentiment, this project isn't going great. 5/11/23 - mblakely still waiting on items to get loaded **5.6.23 WP overage 35 hours item configuration with SuiteCommerice and standard D2B recommendations added to this overage ** 5/4/23 - mblakely we have been TALKING about item setup for over two months, this week we finaly gave the client a matrix item import template. We have struggled to get S4 to the matrix item decision, now they need to load items. 4/28/23 - mblakely we have burned a ton of hours on this job - a) reselling the client and scoping the miss during the sales cycle around the clients PIM. (~10hours), then 20 hours have been back and forth on item setup (matrix and UOM related) - we are six months in on the job and have about 20 test items loaded. 4/14/23 - mblakely we have spend a ton of time discussing and weighing the decision to use matrix items or not to support UOM (unit of measure) this has become a month long debate - we are close to a decision but it's been a long road to get here as part of OPI - and this will be reuasble guidance for a "leading practice" but it's taken a bunch. Putting this project on the watchlist - client is asking connector questions thinks SuiteCommerce is expensive, not having a great implementation experience between this and the PIM debacle. Let's discuss this one. 3/24/23 - mblakely setting early warning scope to yellow - because the PIM just keeps comming up. (At the moment the plan is for S4 to keep their PIM Plytix) - but the needs/integration was not covered in the sales cycle so I'm left advising figuring out how to bridge the gap with the client. ERP's arn't PIM's and PIM's arn't ERPs - we are going to need a change order or partner to integrate the two. 1/25/22 - mblakely had a fact finding session with Mary Ried on PIM/DAM needs concerned NetSuite can't meet these needs. 12/14/22-SDG SuiteCommerce KT will begin after ERP solution more mature | 2022-12-19 | Blakely, Mike |  | Bazzani, Emiliano | Martin, Richard |  | 61.75 | 2023-07-10 | 2023-05-29 | 139008974 | 0 | 0 | 157.35 | New Business
J903016 | #SC-ONLY |  | #SC-ONLY | The Spice & Tea Exchange Distribution LLC - Professional Services : Activation - S | Nassar, Frank | In Progress | 2023-06-20 | Original | 120 | Joint | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) ****Please See J902999 The Spice & Tea Exchange Distribution LLC for updates**** 4/7 - Client provided initial samples of categories and item categorization. Small issues noted. Sample files imported. Client may not be doing web admin training based on certain questions they are asking 3/31 - Prepare phase check in held today. Noted lack of progress on categories, item updates, and images. Almost decided on theme 3/10/23 CG - GRFC held today |  | Green, Chris |  | Bazzani, Emiliano | Murphy, Ryan |  | 4.5 |  | 2023-06-20 | 142382540 |  |  |  | New Business
J872159 | #SC-ONLY |  | #SC-ONLY | Way To Be Designs, LLC - Professional Services : Activation - SuiteSuccess for Com | Onkka, Brady | In Progress | 2023-08-21 | Revised | 359 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 5/16/23 - BO - Call last week didn't happen. Will provide a fuller update tomorrow. 5/3/23 - BO - Client is targeting and August go live date, and confirmed that none of the customizations noted under J872026 are needed. Stock functionality can be used to accommodate all their requests given planed changes in site. Yvonne worked with DL and others to get approval to use J872026 as the implementation job when this job expires. 4/7/23 - BO - Client has finished all Personalization sessions and entered Drive this week. Client is planning to have everything complete and ready for lauch by 5/31 but due to other projects will not be ready for launch by that date. 3/10/23 - BO - Personalization Session 1 completed on 3/8/23, PS2 and 3 will be next week. Project finally moving forward, we may or may not complete before job end. Due to long periods of delay I moved relationship to yellow. 11/30/22 - BO - Client requested on 11/10 for a weekly checkpoint call. Requested dates and times, never heard back on it. Reached out to requesting GTM/GA access and have not heard back. Emailed today for updates. 9/30/22 - BO - GR4C complete. PS1 will be in early Nov 9/12/22 - BO - Reached back out to AMO and Client for an update as we have heard nothing to date. Need to review if this qualifies for closed - lost - Non responsive client. 8/5/22 - BO - Received confirmation from AMO that client was looking to start. Reached out and waiting on response. 6/24 - BO - Followed up with DL and AMO as we have not received a response from client. KT has been completed. 6/7/22 - KSC - Sales to PS KT set |  | Onkka, Brady |  |  | Cristobal, Kevin S |  | 41.5 | 2023-08-21 | 2023-01-30 | 128737793 |  |  |  | AMO
J884597 | #SC-ONLY |  | #SC-ONLY | Highland Supply Inc. - Professional Services : Activation - SuiteSuccess for Comme | Villa, Myr Angeli | Delayed - Per Customer | 2022-12-01 | Original | 251 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 4/11/23 - KSC - EWS made due to non-responsive customer 4/3/23 - KSC - reaching out to the account manager to see if they've heard from this customer 3/17/203 MV - Put this project to delayed status. No response from the customer. 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. 10/6/22 - MV: GRC done 10/6 |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 71.5 |  | 2022-12-01 | 134962868 |  |  |  | AMO
J864621 | #SC-ONLY |  | #SC-ONLY | Brown's Partsmaster, Inc. - PS: Activation - SS4C | Anderson, Peter M | In Progress | 2023-07-03 | Revised | 391 | Joint | #OPI-CHILD-ECOMM (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) #SC-ONLY (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) 5/4/23 - PMA - The SOW has expired; working with Ops and the AMO to get an extension. Main blocker for BPI was understanding how to manage Roles & Permissions. We reviewed that with them today, and they will make updates and assign appropriate roles to their users before moving forward with PW2. Need to capture any gaps from PW2 and complete all updates to the SuiteCommerce site before moving into UAT. SuiteCommerce SOW has also expired, and there is an active CO that is being scoped. This is also being reviewed with the AMO. MN: 21April23: The customer is going through UATs, looking for SSL certificates and a CNAME flattening provider. The customization is being tested by the customer. The job won't go live in time because the ERP implementation won't be ready before the expiry date. We are working internally on how to move forward- - this is still in progress - the PM for this project changed. MN: 13April23: Inherited job from SE. The customer is going through UATs, looking for SSL certificates and a CNAME flattening provider. The customization is being tested by the developers before handing it to the customer to test. The job won't go live in time because the ERP implementation won't be ready before the expiry date. We are working internally on how to move forward. SE: 02Nov22: Finished deployment. Scheduled personalization session kickoff for Nov 10th SE: 03Oct22: Requesting installation of bundles and enablement of features SE: 30Sep22: GR4C meeting done SE: 21Sep22: Introduction to the client. Scheduled GR4C meeting and shared agenda and action items 6/16/22 - BA - Discuss Tasks & Target Dates meeting with BPI team on Jun 13, Cara Garcia-Jones has been assigned as a new Project Manager for Brown's Partsmaster project, Knowledge Transfer & Handover session with Cara, Review Project Kickoff Deck with PM and Delivery Lead on Jun 14. 6/10/22 - BA - Review & Update Project Plan, Update Kickoff deck and request customer's inputs, Review eCommerce SOW & Job Record meeting on Jun 8, Review SS4C Requirments with ERP Consultants meeting Jun 9. 6/03/22 - BA - Review Kickoff Deck & Project Plan meeting, Schedule Project Kickoff meeting on Jun 15. 5/27/22 - BA - Conducted Kickoff Planning and Sponser Alignment meetings on May 25, Sent draft Kickoff Deck and Customer-Facing Leading Practices for customer review, Completed bundle installation without any issues, Followed up with Sales team to provide Blueprint document. 5/20/22 - BA - Conducted PM Introduction Meeting, Reverse Sales to CS KT session, Internal CS Consulting Team meeting, Conducted Getting Started session on May 20, Scheduled Sponser Alignment meeting on May 25. | 2022-11-10 | Noya, Maria |  | Bazzani, Emiliano | Marchlewski, Holly |  | 17.5 | 2023-07-03 | 2023-01-13 | 126592828 | 0 | 0 | 196.35 | New Business
J871671 | #SC-ONLY |  | #SC-ONLY | Iowa State University of Science and Technology - Professional Services : Activati | Noya, Maria | In Progress | 2023-03-13 | Actual | 359 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) April 21st - MN: The customer is still in post go live support - it will end by end of the month. No issues with the new store so far. Customer is estimating a new customization. April 13th - MN: The customer is still in post go live support - it will end by end of the month. No issues with the new store so far. Customer is estimating a new customization. April 3rd 2023 MK - Overage of 45 hours approved for additional PS efforts and issue with website escalation. Approved by VL Meenakshi Krishnan. Job Record has been updated. Feb 14th 2023 - MN: working on DX and Web Performance recommendations and a couple of support cases. Target go live date is March 1st Jan 18th 2023 - MN: UATs December 27th 20222 - MN: UATs November 4th 20222 - MN: working on offline configurations October 17th 2022 - MN: had data import session. Working on offline configurations. weekly status session. October 2nd 2022 - MN: had personalization sessions. Will have data import session next week. September 18th 2022 - MN: Kicked off, scheduled personalization sessions. September 5th 2022 - MN: Client is ready for kick off will schedule personalization sessions soon. August 17th 2022 - MN: Client has the new subsidiary ready and is finishing the training and getting data ready. Requested Pre-implementation Web Performance checkpoint. July 29th 2022 - MN: Checked in. Client is finishing the training and getting data ready. July 16th 2022 - MN: Checked in. Client is finishing the training and getting data ready. July 2nd 2022 - MN: Had Getting started session. Waiting on client to finish setting up the new subsidiary and get data ready. | 2022-09-12 | Noya, Maria |  |  | Bazzani, Emiliano | 2023-03-13 | -3 | 2023-03-20 | 2023-03-01 | 128679667 | 182 | 182 | 255.35 | AMO
J899570 | #SC-ONLY |  | #SC-ONLY | Jade Scientific, Inc. - Professional Services : Activation - SuiteSuccess for Comm | Villa, Myr Angeli | In Progress | 2023-06-26 | Original | 164 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 4/17/2023 MV: Site asset development is in progress. Reach out to the AMO about the new requirement that would need a customization. 2/10/2023 MV: On going offline configuration and site asset development. ETC: 2/28 1/6/2023 MV: Extension to an old job (J837411 ). On going personalization session until next week. | 2023-01-05 | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 17.5 |  | 2023-06-26 | 140526545 | 0 | 0 | 140.35 | AMO
J891717 | #SC-ONLY |  | #SC-ONLY | All From 1 Supply, Inc. - Professional Services : Activation - SuiteSuccess for Co | Joshi, Aarti | In Progress | 2023-12-04 | Revised | 202 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 03/01/23: Client is working on offline configuration. Not much progress on action items as they are also working with ERP team. Currently they are working on Matrix item setup. 02/23/23 AVV: Setting job to In Progress to allow time entries to flow through OA integration 02/17/23 AJ: All the personalization session are completed. Client is working on offline configuration and weekly meeting is scheduled. There is no target go Live Date. They will going live with EPR in April and if website is all set then will be to go live together. SE: 20dec22: DX task created and assigned. Performance Checkpoint created. Bundles provisioned and installed. Starting deployment SE: 15dec22: GR4C meeting SE: 09dec22: followed up with DL. No response from the client. SE: 02Dec22: followed up with DL regarding GR4C meeting. Client has provided access to the instance, but not a date for the meeting 11/18/22 - KSC - Sales to PS KT set; Welcome email sent | 2023-02-13 | Joshi, Aarti |  |  | Cristobal, Kevin S |  | 51.75 | 2023-12-04 | 2023-03-15 | 137781478 | 0 | 0 | 101.35 | New Business
J869104 | #SC-ONLY |  | #SC-ONLY | Comed Medical Specialties - Professional Services : Activation - SuiteSuccess for | Kayastha, Piyush D | In Progress | 2023-04-24 | Revised | 359 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 6/6/2022 - Sales to PS KT completed 6/15/2022 - PK - Customer Welcome follow up 6/28/2022 - PK - GR4C completed. 6/28/2022 - PK - New AMO assigned, Nick Rhoad 6/30/2022 - PK - Internal KT with new AMO 7/18/202 - PK - Followed up with new AMO on client's concerns on payment processor selection, etc. 7/20/2022 - PK - Followed up with AMO again. 7/28/2022 - PK - Followed up with AMO again. 8/12/2022 - PK - Followed up with client on readiness for kickoff. 8/22/2022 - PK - Followed up with customer on readiness for kickoff. 8/23/2022 - PK - Customer is not ready for kickoff. Customer complains that they feel mislead about what's expected to engage the implementation. Informed AMO and inquired with client on delaying project. 8/25/2022 - PK - Customer states they will be ready by September 13th. 9/13/2022 - PK - Kickoff call 9/14/2022 - PK - DX engagement 9/15/2022 - PK - DNS issues for testing sub domain 9/16/2022 - PK - DNs issues on client's end 9/19/2022 - PK - DNS issues resolved. 9/20/2022 - PK - Personalization Session #1 9/21/2022 - PK - Personalization Session #2 9/22/2022 - PK - Personalization Session #3. Client has requested that they need more time to finish training, work on the commerce category tree and get their items ready for webstore. 9/30/2022 - PK - Follow up with customer. 10/14/2022 - PK - Customer follow up 10/21/2022 - PK - Customer follow up 10/28/2022 - PK - Customer follow up 11/4/2022 = PK - Reached out to AMO due to customer becoming unresponsive, again. 11/4/2022 - PK - AMO states customer focused on a different project and facing a difficult renewal. No other timelines or details provided. 11/22/2022 - PK - Followed up with AMO 11/28/2022 - PK - Overage request submitted. Once rejected time is settled, we will most likely need to set job to Delayed - Per Customer 11/30/2022 - PK - Amo advises that client will be pausing the project until Spring. 3/7/2023 - PK - Customer has a GHX integration they are focusing on and have pushed SuiteCommerce until Spring. 3/31/2023 - PK - Follow up with AMO on customer readiness. 4/17/2023 - PK - Follow up with customer, AMO copied again with DL copied. | 2022-08-30 | Kayastha, Piyush D |  |  | Bazzani, Emiliano |  | 24.25 | 2023-04-24 | 2022-10-03 | 128379952 | 0 | 0 | 268.35 | AMO
J865102 | #SC-ONLY |  | #SC-ONLY | BOVA Industries, LLC D.B.A. Norbco - Professional Services : Activation - SuiteSuc | Holt, Jonhenry | In Progress | 2023-06-16 | Revised | 390 | Joint | #OPI-CHILD-ECOMM (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 24 MAY- Customer has extended their license for Suitecommerce. Customer has access to their sandbox per a request from week of 26 May. 10 MAY- We had a call on Monday to cover Action Items and another one scheduled for 10MAY. 2 things remain -- Action Items and Implement Suite Tax in Prod (from Sandbox) 19APR- Scheduled 1v1 with customer. Suitecommerce expiration to be discussed. April 13th 2023 - MN: have not kicked off yet. Wont be able to start before exiration date. The customer got caught up with the ERP implementation. It is only one person taking care of all the implementations in top of the day to day job. 4/7/23 BD - PM Handoff conducted. SuiteTax WT1 completed and open action items being worked on. Limitation on SC schedule communicated to client who has since been unresponsive. 3/24/23 BD - SuiteTax Enabled and KO conducted. WT1 for ST scheduled 3/27. Shooting for 5/1 Go Live for ERP Portion and Suite Commerce to be prioritized after ERP Go Live 2/24/23 BD - Customer still has not signed CO which expires 2/28. Followed up. AMO and DL had individual 1on1's this week to help reinforce decision making process. 2/10/23 BD - Customer has stilled not signed CO for SuiteTax and additional hours. Followed up again. 01/31/23 BD - SuiteTax demo complete. CO verbally approved and out for signature. Will resume project activities once received. 01/20/23 BD - SuiteTax Demo scheduled with Client. If sign off of CO following demo will resume project activities. 01/06/23 BD - Customer unresponsive after being sent CO. Following up regularly. 12/23/22 BD - SuiteTax + additional hours (80 total) CO out for signature as of 12/16. 12/9/22 BD - WT2's have 1 more session. Conducted restart meeting for SC. SC will go live after ERP. Waiting on SuiteTax solutions team to submit SOW/CO. Conducted D2B Worksheet call and set timeline for image renaming and worksheet submittal. 11/30/22 BD - WT2's 50% complete. SC kicking back off 12/1. SuiteTax CO waiting on Customer; being done separate from SuitePeople SOW. 11/23/22 BD - Customer satisfied with action items. WT2s started. SuiteTax/Suite people CO in progress. Customer still dragging feet on SC progress. Had to reassign Tech Consultant due to delay and resource capacity 10/28/22 BD - Conducted 1 of 2 action item call. Temporary workaround for tax issue demo'd. Customer will be evaluating SuiteTax long term. Second Action item call rescheduled due to FC sick day. Trying to have that call and start project back up next week. 10/18/22 BD - Progress on Action items. Evaluating tax workaround and solution. Should resume progress this week. 9/30/22 BD - Some Progress on action items but not moving forward yet. Reassess weekly to schedule WT2s 9/23/22 BD - Some Progress on action items but not moving forward yet. Reassess weekly to schedule WT2s 9/16/22 BD - Customer does not want to move forward until WT1 action items are figured out. 9/7/22 BD - Still working on action items. Scheduling addtl. calls as needed. 8/30/22 BD - Extended time on action items. SC side stalled out due to customer business. Attempting to schedule WT2s for start by second week of Sept. 8/17/22 BD - Working on SC Data templates and theme customization. Customer slow to respond on SC deliverables. 8/7/22 BD - SC KO/FRD Completed. Reviewed themes and customization requirements. 7/28/22 BD - WT1s almost complete. SC KO and FRD review Scheduled. 7/21/22 BD - ERP still delayed but in WT1. Delay communicated with DL and customer 7/11/22 BD - ERP implementation delayed in DM. Follow up completed and additional follow up scheduled 6/27/22 BD - Checkup conducted on SC web training and selection of Theme/payment Vendor. Follow up scheduled 6/17/22 - BD - SC Kick-off Conducted 6/14/2022 - BD - Tech Resource assigned waiting on SC config. 5/4/22- JRH- Welcome letter sent |  | Noya, Maria |  | Bazzani, Emiliano | Haines, Jefferson R |  | 52.75 | 2023-06-16 | 2022-08-15 | 126649339 |  |  |  | New Business
J902456 | #SC-ONLY |  | #SC-ONLY | Edmundson, Inc. – DBA – Arbor Valley Nursery - Professional Services : Activation | Noya, Maria | In Progress | 2030-01-01 | Original | 125 | Standalone | #SC-ONLY April 21st 2023 - MN: Finished personalization sessions and had data import session - moving to offline configurations April 13th 2023 - MN: Had kickoff and first 2 personalization session. We are waiting on the subdomain to have the third one and resume the implementation. March 13th 2023 - MN: Waiting on the customer to be data ready. Feb 14th 2023 - MN: Had KT, Getting started session with customer and a follow up. Waiting on the customer to be data ready. | 2023-03-27 | Noya, Maria |  |  | Bazzani, Emiliano |  | 44.75 |  | 2030-01-01 | 142163761 | 0 | 0 | 59.35 | AMO
J893735 | #SC-ONLY | #POS-NSPOS-ONLY | #SC-ONLY #POS-NSPOS-ONLY | Auburn University ¦ Implementation Service - Fixed Bid | Loh, Chileng | In Progress | 2023-10-03 | Original | 184 | Joint | #SC-ONLY #POS-NSPOS-ONLY #CAMPUS (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 5/11 completed one NSPOS session. Scheduling ERP WT2 for 5/30--6/29. CO being presented by AMO for Rusty to review. 4/28 ERP WT1 completed. no significant gap. CSER to add redshelf and SSO in progress. filed esc on NSPOS defect as it blocks config and WT1 4/19 WT1 on track to finish 4/26. No gap to-date. POS has a defect being solved by Support. Has workaround in the meantime by manually placing the files onto the database. 4/13 decided on using Watchman. Working on Item book data extracting from Ratex which is a common challenge for campuses. WT1 starting 4/14. 3/21 critical decision around watchman is pending. To discuss Avalara with team at next status call to have clarity on direction. awaiting DNS to start SCA config sessions. WT1 schedule need confirmation. Team (Raamiz) to send Walkthrough guide by 3/31. Completed pers, and integration strategy meeting and published the doc. Completed two 2 NSPOS pers sessions. Maria transitioning to Missy tomorrow To schedule checkpoint call for early April; 3/13 O2C pers. in progress. Added Jeremiah to partner with Nick. 2/28 completed P2P pers. Spring break pause a week then finish up O2C. Current dir of store last day today. 2/21 SCA getting ready session set for 2/24. 0210 cloh: add Daniele for POS customization. ERP pers expected to complete 3/15; POS pers 3/20-3/24 020323 cloh: completed R2R and CRM pers. Other to be resch/confirm for Feb 22 onwards due to PTO/ICBCA on both Auburn and NS teams. Filed task for AMO to discuss SSO w client. 012023 cloh: onsite not happening due to it being a budget surprise. KO planned 1/23. Published Personalization guide; sessions timing has to be finalized. 1228 cloh: client on winter break. ToS not yet accepted as client wants Oracle to sign an addendum. AE explained the SOW already included what terms required by AU/Alabama. To reconvene in meeting next week. 1208 cloh: added Melissa Pooch, Jess Filardi, Hannah; Customer responded to meeting request. Set for 12/14 2022 1205 VR: Welcome letter sent. Switching project status to "In Progress" | 2023-01-23 | Phillips, Lauren | Bazzani, Emiliano | Bazzani, Emiliano | Raghavan, Vidhya |  | 1407.25 |  | 2023-10-03 | 138605376 | 0 | 0 | 122.35 | New Business
J865012 | #SC-ONLY |  | #SC-ONLY | Power Wholesales Management, Inc. ¦ Implementation Service - Fixed Bid | Holt, Jonhenry | Delayed - Per Other Project |  |  | 391 | Joint | #OPI-CHILD-ECOMM #SC-ONLY (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) 31January2023_KP : Since customer is not responding regarding SOW extension, status for this project has been updated as Delayed - Per Customer. 20January2023_KP : Reminder email shared with customer for SOW extension . 12Jan Ankit- This project is delayed per other SuiteCommerce Activation project. SOW extension has been shared multiple times with the customer. 7January2023_KP : SOW extension again shared with customer 29November2022_KP : Mail shared with AMO for help since even after repeated reminders – customer has not signed the SOW extension 27November2022_KP : Even after repeated reminders, customer is not responding regarding SOW extension. Status for this project has been updated as Delayed - Per Customer 15November2022_KP : Reminder email shared with customer for SOW extension 28October2022_KP : Discussion done with customer over call to answer their queries regarding SOW extension 27October2022_KP : Resend the SOW extension document to customer 26October2022_KP : Reminder email shared with customer for SOW extension 15October2022_KP : Mail shared with customer for SOW extension 11October2022_KP : Work on this job can be started after completion of SuiteCommerce Activation job (J884637). Hence status for this project has been updated as Delayed - Per Other Project 17September2022_KP : Customer has agreed to pay for Suite Commerce Activation. AMO is working on signing of SOW 29August2022_KP : As advised by Kiko, Change order cannot be processed for SuiteCommerce Activation. New order with activation SKU is needed. Andrew Passo & team are discussing with customer to resolve this 18August2022_KP : Since CAR approval is taking time, CSER request raised for processing change order for SuiteCommerce Activation 8/10/2022 - PK - Follow up with ERP pm on status of project 7/28/2022 - PK - Follow up with ERP pm on status of project 15June2022_KP : Status changed to Delayed - Per Sales 14June2022_KP : Somehow Activation is missing. SalesRep is coordinating with AMO to get Activation added. 10June2022_KP : In internal discussion it was discussed that Lead Consultant will implement native SuiteCommerce and prepare list of customizations required by the customer within budgeted hours (79 as mentioned in CSER) 7June2022_KP : Mail shared with Solution Principal highlighting that SuiteCommerce implementation (as per current SOW) may not meet customer expectations. SP was advised for SOW updation. 6June2022_KP : Consultant reviewed and indicated that sample website has customizations which do not seem to get mapped to current SOW. 3June2022_KP : Solution Principal shared sample website indicating customer preference for SuiteCommerce implementation. 25May2022_KP : Introduced SuiteCommerce Functional lead consultant (Piyush) to customer. Also discussed with customer that SuiteCommerce implementation can begin after ERP implementation has matured to a certain degree 17May2022_KP : Reverse Sales to CS KT done. 17May2022_KP : During initial discussion, it was identified that Blueprint is not available for this implementation. Solution Principal shared that this was not a typical alignment / sales cycle. Customer has changed licenses multiple times |  | Estellano, Santiago |  | Cristobal, Kevin S | Gupta, Ankit |  | 369.25 |  |  | 126640266 |  |  |  | New Business
J833544 | #SC-ONLY | #POS-NSPOS-ONLY | #SC-ONLY #POS-NSPOS-ONLY | University of Toronto Press ¦ Implementation Service - Fixed Bid | Snyderman, Michael | Delayed - Per Customer | 2022-06-13 | Actual | 636 | Joint | .##POS-NSPOS-ONLY #CAMPUS (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) #SC-ONLY #CAMPUS (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 4/21, 4/12, MS: Still pending input from RMT. 3/31, 3/17, 3/3/23, MS: Planning to close job once Change Order work completed for PubNet. See PubNet job for details. 2/27/23, MS: SOW extended one final time for PubNet UAT support to end of March (CO006, fifth SOW extension). 2/17/23, 2/3/23, MS: PubNet UAT in progress. UTP finally starting to do more testing. 1/27/23, MS: SOW extended for PubNet UAT support to end of February (CO005, fourth SOW extension). 1/25/23, 1/11/23, MS: Planning to close job once Change Order work completed for PubNet. 12/30/22, MS: Holiday time over last week or so and not much client activity; NetSuite doing some investigation on two reported issues although will need to continue to investigate. 12/16, MS: SOW extended to end of January (CO004, third SOW extension) to allow for two issues raised by UTP to be investigated (not used fields, bill in advance of receipt). 12/2, MS: UTP began testing Oct 2022 and is ongoing although beyond scope of normal practice. 3 decisions/actions from UTP slowed down testing: * UTP elected to test using PubNet Production (different than NetSuite instance) when typically PubNet Sandbox (different than NetSuite instance) is used. * UTP did not coordinate with their vendors to as following the Canada standard. * UTP did not turn off their legacy system until recently which interrupted the flow and made it difficult and timely to troubleshoot. 11/18, 11/2, MS: UTP began testing Oct 2022 and is ongoing although beyond scope of normal practice. 10/19, 10/5, MS: UAT in progress of PubNet. SOW to be extended to end of December (CO003, second SOW extension) to allow for PubNet UAT to wrap up. 9/21, 9/7, MS: PubNet delivered end of August. On hold until client does UAT in early October. 8/24, 8/10, MS: PubNet to be delivered by end of August by Tech due to clarification needed regarding PubNet in Canada. SOW will be extended to end of October to allow for testing (C002, first SOW extension). 7/29, MS: Post Live Support completed 20Jul except for TCard Watchman check balance enhancement and PubNet. TCard Watchman check balance delivered and verified by client. PubNet in progress by NS Tech team. 7/14, MS: Post Live to complete 20Jul except for TCard Watchman check balance enhancement and PubNet. 6/30, MS: Post Live in progress until mid-July pending budget. 6/14, MS: Achieved Go Live on 13-Jun. Cutover Items attached to 10-Jun status report. 5/30, MS: Client still lagging on UAT testing although has hard date for Go Live of 13Jun. Expect to achieve with extra effort early in Post Live. 5/17, MS: Sponsor meeting today. Emphasized to client need to complete custom cases and sign off on data in data tracker. Client seems reluctant to do more UAT. Next sponsor meeting on 19May to determine if Go Live target of 24May needs to be pushed until mid-June. 5/16, MS: Standard UAT cases almost 80 percent complete although client has not created custom cases other than NSPOS. Integrations expected to be delivered this week for Watchman and Willo. OTT Pay expected to be delivered 23May. Client having NSPOS issues and escalating to get more attention on NSPOS. 5/11, MS: Client has been doing UAT since mid-March with very slow progress until last 1.5 weeks. 24May Go Live appears at high risk. 4/29, MS: UAT in progress although only about one third of cases complete which is concerning for 5/24 go love target. Have 3 check-ins planned for next week on both UAT status and UAT questions. 4/13, MS: Customer slow on UAT progress. POS consultant back so pending customer questions can proceed with resolution. Also expecting client to sign OTT Pay for AliPay and WeChat customization next week. 3/29, MS: Initial round of UAT in progress. Go Live target established as 24-May. Customer wants estimate for new customization for connecting with OTTPay and AliPay and WeChat which should be presented by 4-Apr. 3/17, MS: Client looking to start UAT. 3/2, MS: Continuing following up with tech team on customization completion and client on question and answers. 2/23, Following up with tech team on customization completion and client on question and answers. 2/8, MS: March 1 go live moving since both client and NS not ready. Tech work being evaluated for when can be completed. Met with DL and sponsor and customer PM along with CFO on 2/4 and plan to again on 2/14. 1/25/22, MS: Transition of PM from Tony to me started mid-Jan. Taking ownership this week and evaluating team overall progress. 1/19/22 (TB) - Most Technical Services scope still in progress. PWT 2 is currently in process. UAT is tentatively scheduled to begin on January 31. Project has been formally transitioned to Michael Snyderman. 12/22/21 (TB) - PWT 2 has been scheduled and confirmed to begin during week of January 10. 12/3/21 (TB) - Engage Checkpoint completed on 12/2. ERP PWT 1 will be completed today. PWT 1 for NSPOS is scheduled for next week. SCA PWT 1 is scheduled and confirmed on 1/6/22. Internal Technical Services Alignment meeting held on 12/3 to discuss status and due dates for in-scope Technical Services items. 11/19/21 (TB) - PWT 1 for ERP and NSPOS began on 11/16 and will continue through mid-December. All sessions have been scheduled/confirmed, meeting invites sent. Some Technical Services items are dependent upon the completion of PWT 1. 11/5/21 (TB) - Issues with CEI and OTT Pay have been mitigated and resolved. For CEI Integration, UTP has agreed that auto-generated codes will suffice. SC Personalization is supposed to begin next week pending client confirmation of proposed schedule. ERP and NSPOS PWT 1 begins the week of November 15 and is currently being scheduled. Project continues to stay on track for target go-live. 10/25/21 (TB) - Personalization for ERP and NSPOS will be complete on Tuesday, October 26. SuiteCommerce Personalization Sessions will be scheduled during the week of November 8. PWT Series 1 is tentatively scheduled to begin during the week of November 15. Currently trying to mitigate an issue with the CEI integration since it does not currently work with pre-generated codes which is something that is required by University of Toronto Press. Also, client is concerned about Wechatpay and Allipay integrations since Oracle NetSuite did not end up partnering with OTT Pay who was also required by the University of Toronto Press. Working with Sales to determine a solution. 10/8/21 (TB) - Started weekly project status meetings with the client on Thursday, October 7. All Personalization Sessions for ERP and NSPOS have been scheduled and confirmed. The Getting Started with Commerce call was completed on Wednesday, October 6. Personalization Sessions for SuiteCommerce still need to be schedule but may be further out in the schedule due to several dependencies on ERP and NSPOS. ERP Personalization Sessions begin during the week of October 11. 9/27/21 (TB) - The Project Kickoff Meeting was completed on Wednesday, September 22. The Data Migration Strategy Session was completed on Friday, September 24. Personalization is currently scheduled and confirmed to begin on Wednesday, October 13, and estimated to continue through the end of October. Only a few remaining Personalization Sessions need to be scheduled. 9/16/21 (TB) - The SOW Review was completed with the customer on Thursday, September 16. 09/02/2021 MK - Initial Intro Call with Client sponsors 8/31/2021 MK - Welcome Letter Sent | 2021-09-22 | Serron, Sennon A | Bazzani, Emiliano | Bazzani, Emiliano | Krishnan, Meenakshi S | 2022-06-13 | 11.25 | 2022-06-13 | 2022-03-01 | 107411221 | 264 | 264 | 610.35 | New Business
J892627 | #SC-ONLY |  | #SC-ONLY | The Sykes Group, LLC - Professional Services : Activation - SuiteSuccess for Comme | Blakely, Mike | In Progress | 2023-06-21 | Revised | 190 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) Email tag: messages.NLCORP.533201521.b5aab4156f@nlcorp.email.netsuite.com 5/17/23 - mblakely we are ready to go just waiting on client to launch their broader website in June 3/17/23 - mblakely working towards getting client setup - between two other partners, actual client is pretty hands off, all products are drop shipped, catalog is a bit confusing as it's the same product sold by three different brands, should be live in early April | 2022-12-15 | Blakely, Mike |  |  | Bazzani, Emiliano |  | 30.25 | 2023-06-21 | 2023-03-01 | 138242173 | 0 | 0 | 161.35 | New Business
J898182 | #SC-ONLY |  | #SC-ONLY | The Learning Experience Corp - SuiteCommerce Activation | Ware, Liza | In Progress |  |  | 160 | Joint | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 5/24: LW ¦ waiting on customer progress. 5/12: LW ¦ DX activities to begin, 5/2: LW ¦ personalization sessions are complete. 4/20: LW ¦ Personalization sessions in progress 4/10: LW ¦ customer to complete training before sessions begin. 3/23: LW ¦ consultant change.. customer to work through initial AI's. 3/9: LW ¦ Intro call completed - AI's assigned. 2/27: LW ¦ scheduling of intro call pending. 2/10: LW ¦ Aarti to schedule initial SC call w Rey. 1/26: LW ¦ Initial SC tasks to begin. 1/19:LW ¦ KO w ERP completed on 1/12. ERP personalization sessions to begin next week. SC tasks to follow. |  | Estellano, Santiago |  | Bazzani, Emiliano | Peterson, Suzanne |  | 45.75 |  |  | 140262429 |  |  |  | New Business
J856449 | #SC-ONLY |  | #SC-ONLY | Fleetspec ¦ Implementation Service - Fixed Bid | Noya, Maria | In Progress | 2023-05-15 | Original | 434 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) April 13th - MN: Customer is still setting up multilanguage. We are working on the distributor locator in the main job, what is remaining for go live. Feb 14th 2023 - MN: Currency ready. Started on multilang - waiting on subdomain for French Jan 18th 2023 - MN: Currency ready, working on multi-language. December 27th 2022 - MN: Currency ready, working on multi-language. October 17th 2022 - MN: Currency ready, working on multi-language. October 2nd 2022 - MN: The currency configuration is ready; we will start working on multilenguage this week. September 15th 2022 - MN: The currency configuration is ready September 5th 2022 - MN: The currency configuration is ready; August 18th 2022 - MN: client was on hold for a copule of weeks for personal reasons. The currency configuration is ready; we will start working on multilenguaje. July 29th 2022 - MN: we´ll start in the next couple of weeks July 16th 2022 - MN: we´ll start in the next couple of weeks July 2nd 2022 - MN: waiting to finish personalization sessions to start. June 18th 2022 - MN: waiting to finish personalization sessions to start. June 5th 2022 - MN: waiting to personalization sessions to start May 22nd 2022 - MN: getting data ready. May 9th 2022 - MN: getting data ready. April 25th 2022 - MN: getting data ready. Pending training because it was not provided yet. April 7th 2022 - MN: getting data ready. Pending training because it was not provided yet. 25/03/2022 - MN: Had getting ready call. Waiting to start with customizations. 14/03/2022 - MN: Had Sales KT to PS This week the "getting ready" call is scheduled. | 2022-03-11 | Noya, Maria |  |  | Bazzani, Emiliano |  | 16.5 |  | 2023-05-15 | 121966052 | 0 | 0 | 440.35 | AMO
J900261 | #SC-ONLY |  | #SC-ONLY | Good Stuff Distributor Inc. - Professional Services : Activation - SuiteSuccess fo | Villa, Myr Angeli | In Progress |  |  | 146 | Standalone | #SC-ONLY email: messages.NLCORP.540217577.f524178dd6@nlcorp.email.netsuite.com 05/18/23 MV: Customer cancelled our upcoming meetings. They decided not to move forward with SuiteCommerce. 04/12/23 MV: Took over job as FC from Aarti. Customer requested to schedule a sync up call next month due to their availability. 03/01/23 AJ : Reached our to customer for status update and did not receive any response yet. 02/24/23: Sent instruction mail to client 02/20/23: created web performance checkpoint 1 02/17/23: GR4C meeting completed. Follow-up on next week. | 2023-03-03 | Villa, Myr Angeli |  |  | Bazzani, Emiliano |  | 72.5 |  |  | 140735105 | 0 | 0 | 83.35 | AMO
J918576 | #SC-ONLY |  | #SC-ONLY | B & G Trading LLC - Professional Services : Activation - SuiteSuccess for Commerce | Kilbane, Mary | In Progress |  |  | 26 | Joint | #SC-ONLY (tracking tag DO NOT DELETE) 5.11.2023 - mkilbane ¦KT scheduled for week of 5/22. 5/5/23 - KSC - Welcome letter sent. KT done. Ebo pointed out some integration work that will be done by ACS. Client still working with Cybersource to get their payment gateway set up. |  | Villa, Myr Angeli |  | Cristobal, Kevin S | Small, Bonnie |  | 77.5 |  |  | 148103305 |  |  |  | New Business
J899879 | #SC-ONLY |  | #SC-ONLY | Aliquantum International Inc. - Professional Services : Activation - SuiteSuccess | Estellano, Santiago | In Progress | 2023-07-01 | Original | 149 | Joint | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) SE: 27Apr23: exploring item setup options internally SE: 25Apr23: Item setup considerations, meeting with client and ERP team to review issues SE: 17Apr23: Starting personalization sessions SE: 04Apr23: SCS deployed, personalization sessions scheduled for Apr 17th SE: 09Mar23: GR4C kickoff meeting complete. SE: 27Feb23: reached out to client requesting availability for kickoff meeting. DL to send Welcome Letter shortly. 2/13 AA: Suite commerce consultant brought on to assist with Ecommerce questions. |  | Estellano, Santiago |  | Bazzani, Emiliano | Gosnell, Steve |  | 34 |  | 2023-07-01 | 140681073 |  |  |  | New Business
J860566 | #SC-ONLY |  | #SC-ONLY | Smith's Consumer Products, Inc. ¦ Implementation Service - Fixed Bid | Desimini, Peter N | In Progress | 2023-06-01 | Revised | 421 | Joint | 7/22/22 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) #OPI-CHILD-ECOMM #SC-ONLY (tracking tag - DO NOT DELETE) #OPI-WMS (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) 2023 0524 - PND - End to End testing continued. Go live set for 6/1 if customer can complete 3rd party testing.. Customer working through end to end testing and issues and 3rd party /NetSuite working to resolve. 2023 0503 - PND - End to End testing continued. Go live pushed to 6/1. Customer working through end to end testing and issues and 3rd party /NetSuite working to resolve. 2023 0417 - PND - End to End testing in progress. Trying to make 5/1 go live but 3rd party delays will likely push to 6/1 golive. 2023 0317 - PND - . UAT restarted 3rd party/customer delays in setup and config of software.. 3rd party integrators confirmed they are working towards go live of 5/1. 5/1 is the current go-live date. 2023 0306 - PND - . UAT paused and restarting on 3/6 due 3rd party/customer delays in setup and config of software.. 3rd party integrators confirmed they will not be ready for go live until 5/1 at earliest. 5/1 is the current go-live date. 2023 0213 - PND - ERP/WMS WT2s and follow up meetings completed . UAT started on 2/13. 3rd party integrators confirmed they will not be ready for go live until 5/1 at earliest. 5/1 in new target go-live date. 2023 0202 - PND - ERP/WMS WT2s and follow up meetings completed by 2/7/2023. UAT to start by end of next week. Customer would like to target 3/1/2023 and we will push to make this date but it is not likely achievable since 3rd party integrations are not complete, testing will start next week. 5/1/2023 is a more realistic go-live date. 2023 0131 - PND - ERP/WMS WT2s and follow up meetings completed by 2/6/2023. UAT to start by end of next week. 2023 0118 - PND - ERP WT1s completed. WMS WT1s completed. WT2s delayed and started in mid January per customer request due data not being available for loading. UAT to start in early Feb. 2022 1012 - PND - ERP WT1s in progress. WMS WT1s to start 10/20. 2022 1003 - PND - Walkthrough 1s Started, expected to complete by 10/25. 2022 0921 - PND - Walkthrough 1s Scheduled to begin next week. Data migration and import continued. Project is continuing to progress slowly per Customer Request. No major issues. WMS WT1 scheduling in progress. 2022 0722 - PND - Personalization Sessions completed. WOrking through data import issues and will be scheduling WT1s within next 2-3 weeks. Customer wants to take the project slow. | 2022-06-13 | Emira, Ossama |  | Cristobal, Kevin S | Conor, Katharine S |  | 195.5 | 2023-06-01 | 2023-02-01 | 124390794 | 0 | 0 | 346.35 | New Business
J890366 | #SC-ONLY |  | #SC-ONLY | Nspire Wireless, Inc - Professional Services : Activation - SuiteSuccess for Comme | Estellano, Santiago | Monitoring - Post Go-Live | 2023-04-03 | Actual | 209 | Standalone | 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. #SC-ONLY (Tracking TAG DO NOT DELETE) SE: 19MAy23: Post Go Live Support period ended. Sent Closing email. SE: 21Apr23: questions around locking in customer info on MyAccount. Pending confirmation to use CSS and hide containers SE: 03Apr23: Go live complete. Requesting post go live checkpoints SE: 31mar23: Finished UATs. Pre go live checkpoints completed. Ready for go live SE: 28feb23: client finishing action items. Starting UATs as soon as action items are finished. SE: 30dec22: requesting change of CPM SE: 21dec22: following up on some requests from clients regarding ACH compatibility with Threads Theme, manual payment processors and a potential Phase 2 customization SE: 16dec22: started personalization sessions SE: 06dec22: domain still missing DNS configuration, reached out to client SE: 21nov22: GR4C meeting 11/18/22 - KSC - Sales to PS KT Done; Welcome Email sent | 2022-12-16 | Estellano, Santiago |  |  | Cristobal, Kevin S | 2023-04-03 | 0.25 | 2023-04-03 | 2022-12-15 | 137248123 | 108 | 108 | 160.35 | AMO
J914294 | #SC-ONLY |  | #SC-ONLY | Wallace Electrical Systems L.L.C._Activation - SuiteSuccess for Commerce | Shea, Paul | In Progress |  |  | 55 | Joint | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) |  | Estellano, Santiago |  | Bazzani, Emiliano | Mohanty, Rajesh |  | 73 |  |  | 146304541 |  |  |  | New Business
J893446 | #SC-ONLY |  | #SC-ONLY | Parts Midwest, Inc. - Professional Services : Activation - SuiteSuccess for Commer | Kayastha, Piyush D | In Progress | 2023-05-22 | Revised | 185 | Standalone | #SC-ONLY(tracking tag DO NOT DELETE) 11/30/2022 - KSC - Welcome Letter sent 11/29/2022 - PK - Internal Sales to PS KT completed. 12/5/2023 - PK - Getting Ready for Commerce completed 12/9/2023 - PK - Customer confirms they're not going to use Payment Processor at this time. Invoice only 1/4/2023 - PK - Kickoff call completed 1/12/2023 - J893445 customization job assigned 1/16/2023 - PK - subdomain created by customer 1/19/2023 - Pk - subdomain DNS entry pending by customer 1/23/2023 - PK - Customer opts out of DX services 1/26/2023 - PK - Customer not ready for beginning any efforts on customization project J893445 1/27/2023 - PK - subdomain DNS entry resolved 1/31/2023 - PK - Personalization Sessions completed 2/8/2023 - PK - First Data Import session completed 2/15/2023 - PK - Second Data Import session completed 2/17/2023 - PK - Carousel image issue Case # 5158016 2/20/2023 - PK - CTA buttons issue Case # 5059791 2/23/2023 - PK - Status Update call 2/28/2023 - PK - Process Walkthrough call 3/6/2023 - PK - Email Communication to use SMT, updated Categories, associate Items, etc 3/10/2023 - PK - Some of customer's team has been on PTO. Customer progressing with customer tasks and still preparing for UAT. 3/21/2023 - PK - Customer requesting additional guidance for Data import 3/29/2023 - PK - After additional calls and emails, customer is still not complete with Data import. 03-Apr-2023 (MC) overage approved 5/3/2023 - PK - Customer is struggling to complete UAT in it's entirety before reaching out with "issues" and requesting changes to standard SuiteCommerce website. | 2023-01-04 | Kayastha, Piyush D |  |  | Cristobal, Kevin S |  | 15.75 | 2023-05-22 | 2023-02-06 | 138541799 | 0 | 0 | 141.35 | AMO
J884637 | #SC-ONLY |  | #SC-ONLY | Power Wholesales Management, Inc. - PS : #SC-ONLY SS4C Activation | Estellano, Santiago | In Progress | 2022-12-31 | Original | 251 | Standalone | #SC-ONLY (Tracking tag - DO NOT REMOVE) Job email: messages.NLCORP.525741258.1b6c18b038@nlcorp.email.netsuite.com SE: 05-May-23: client woriking on action items. They forecast all action items to be finished by May 16th SE: 12-Apr-23: Followed up with client again. Met with the client, informed about time remaining in project. Client requested escalation to change Expiry date. Set tentative action plan to get customer live by May 31st SE: 05-Apr-23: Followed up with client regarding implementation. Client informed about time remaining in the job record for completing the project. SE: 15Mar23: Client has delayed project, no progress since Dec 2022. Follow-ups have not been replied to. Followed up again with client. 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. SE: 21dec22: finished Personalization Session 4. Client to confirm availability for last personalization session once the extensions are decided and installed SE: 29Nov22: finished deployment, ready for personalization sessions SE: 16Nov22: client has re-engaged. Changing status to In Progress SE: 07Nov22: changing status to Delayed - Per Customer SE: 31oct22: touched base with the client re: action items in Prepare Stage, no response SE: 17Oct22: touched base with the client re: action items in Prepare Stage SE: 11Oct22: touched base with client. There are concerns from client regarding SCS functionality. Addressed in conjunction with SP. SE: 27Sep22: GR4C meeting SE: 23Sep22: sales to PS KT meeting held. Changing GR4C meeting as per customer request. SE: 21sep22: introduction to ERP & SC customization team. Changing project status to In Progress | 2022-11-29 | Estellano, Santiago |  |  | Villaverde, Alfredo |  | 25 |  | 2022-12-31 | 134969429 | 0 | 0 | 177.35 | AMO
J870359 | #SC-ONLY |  | #SC-ONLY | Veritas Supply Chain Solutions, LLC - Professional Services : Activation - SuiteSu | Noya, Maria | In Progress | 2030-01-01 | Original | 363 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) May 18th - MN: we will close on the 27th - expiry date April 21st 2023 - MN: Customer is working on getting assets, it is taking longer than expected - we will be very tight with time since the SOW expires May 27th April 13th 2023 - MN: Customer is working on getting assets, it is taking longer than expected - we will be very tight with time since the SOW expires May 27th Feb 14th 2023 - MN: Had getting started session. Waiting on the customer to be data ready. December 27th 2022 - MN: Waiting on client or AMO for updates to have the getting started session. Will follow up next week - beginning of the year October 17th 2022 - MN: Waiting on client or AMO for updates to have the getting started session. October 2nd 2022 - MN: Waiting on client or AMO for updates to have the getting started session. Will follow up this week. September 18th 2022 - MN: Waiting on client or AMO for updates to have the getting started session. September 5th 2022 - MN: Waiting on client or AMO for updates to have the getting started session. August 17th 2022 - MN: Waiting on client or AMO for updates to have the getting started session. Will follow up end of August. July 29th 2022 - MN: Waiting on client to answer email for tentative time slots. AMO will follow up. July 16th 2022 - MN: Waiting on client to answer email for tentative time slots. July 2nd 2022 - MN: Waiting on client to answer email fr tentative time slots. June 18th 2022 - MN: Had Sales to Ps KT, waiting on client to suggest time slots. | 2023-03-13 | Noya, Maria |  |  | Bazzani, Emiliano |  | 50.75 |  | 2030-01-01 | 128508644 | 0 | 0 | 73.35 | AMO
J899274 | #SC-ONLY |  | #SC-ONLY | CPI Card Group Inc. - Professional Services : Activation - SuiteSuccess for Commer | Farsedakis, George | Delayed - Per Other Project | 2023-11-30 | Original | 154 | Joint | #SC-ONLY (tracking tag DO NOT DELETE) 2/15/23- JRH- Welcome letter sent 1/10/23 - Sales to PS KT Set |  | Joshi, Aarti |  | Cristobal, Kevin S | Haines, Jefferson R |  | 75.5 |  | 2023-11-30 | 140508672 |  |  |  | New Business
J900111 | #SC-ONLY |  | #SC-ONLY | The Princeton University Store ¦ Implementation Service - Fixed Bid | Green, Chris | In Progress | 2023-04-27 | Original | 154 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 2/10 CG - Kickoff call complete, client working on staging domain and installation of SCA bundle 1/30/23 CG - Kickoff scheduled for later this week | 2023-02-01 | Green, Chris |  |  | Cristobal, Kevin S |  | 18.75 |  | 2023-04-27 | 140722012 | 0 | 0 | 113.35 | AMO
J899345 | #SC-ONLY |  | #SC-ONLY | Medical Innovations Inc. - Professional Services : Activation - SuiteSuccess for C | Joshi, Aarti | In Progress | 2024-01-01 | Original | 154 | Standalone | 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. #SC-ONLY (tracking tag DO NOT DELETE) 05/15/23 AJ : Client is working with third party for UOM and other customization. They will touch base with SC team once it's completed. 04/21/23: AJ Completed personalization session and items has been uploaded in the system. Next steps Client will work with third party for UOM customization and schedule a meeting with SC team if needed. 03/01/23 AJ : Had a meeting with client and discussed the next step. Client has provided the requested details. Deployment is complete. PS session to be scheduled next week. Client is looking for PCV feature and advanced sign up. 02/23/23 AJ : Project is in engage phase and PS session are not started yet hence Kick off date is blank. 02/17/23: GR4C meeting was completed. They went live with ERP last week and good to start with SC implementation. 1/10/23 - Sales to PS KT set | 2023-03-10 | Joshi, Aarti |  |  | Cristobal, Kevin S |  | 61.75 |  | 2024-01-01 | 140511038 | 0 | 0 | 76.35 | New Business
J921200 | #SC-ONLY |  | #SC-ONLY | Tigris Fulfillment Partners, LLC - Professional Services : Activation - SuiteSucce | Joshi, Aarti | In Progress |  |  | 10 | Standalone | #SC-ONLY Email Tag: messages.NLCORP.553144085.ade0b00fd9@nlcorp.email.netsuite.com |  | Joshi, Aarti |  |  | Bazzani, Emiliano |  | 79 |  |  | 149061619 |  |  |  | AMO
J824387 | #SC-ONLY |  | #SC-ONLY | Sturbridge Yankee Workshop - Professional Services : Activation - SS4C #SC-ONLY | Green, Chris | Completed | 2022-01-03 | Actual | 727 | Standalone | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 24-FEB-2022: CS Ops: To update the CS Expiry from 6 term in months to 12 months to align with ToS 1/10 CG - Client needs to provide updated 301 redirects file. Also noted an issue where some customers had their email address stored as info.sturbridgeyankee.com during checkout. Submitted support case for issue. No further instances of this since 1/7. 1/3/22 CG - Client is live! 12/30 CG - Uploaded completed SOW extension doc 12/21 CG - Noted extension approved, sent along to team 12/13 CG - Re-requesting SOW extension after approval of overage 12/9/21 MKM - approved in addition to existing 20 hours for total of 28 hours 10/27 DG: I approve. Requesting 8 FC hrs to complete deliverables for project due to large amount of time spent on customizing webstore with various custom fields, CSS adjustments to customize presentation of extensions, troubleshooting issues with shipping items not producing correct values, and various reviews of functionality with client 11/25 CG - Overage requested in Oct hasn't been completed. Pinged DL again who approved 10/27 11/18 CG - Project in holding pattern due to internal delay with go live timing. Requested extension 10/27 but awaiting overage approval. Pinged DL after noting delay in overage approval 9/30 CG - discussion with ERP team around workflow to autopopulate a field upon submitting advanced sign up form, and client email around SSL cert, internal discussion around SSL cert requirements given they are migrating domain, and root domain is not currently present in google per SSL doc 9/28 CG - pre go live checkpoint request and review of results from previous checkpoint with Angel to get an understanding of requirements for go live. Review of SSL setup to determine next steps for client 9/28/21 MKM - approved per reason below DG 9/28: I approve. There's collaboration with ERP that caused higher workload on the consultant. Requesting 20 FC hrs for collaboration with ERP project, attending internal and external meetings with client 9/27 CG - Check in call on progress toward deliverables and follow up. Client confirmed working on item record updates. Also confirmed happy with shipping solution on webstore side 9/24 CG - Finalizing content for site and adjustments regarding how shipping is handled. Reached out to McCall on ERP side to confirm ability to remove a price tier in shipping item displaying on webstore incorrectly. Pinged Dara on ERP side regarding a workflow for filling in a date when their catalog request form is submitted 9/8 CG - Had call with support team to discuss matrix item issue, Joined ERP Walkthrough call which I was required to attend due to overlap from ERP and SC with relation to ERP D2B. Had additional call with Deborah to review questions she had with updates to item option list and item image structure 9/7 CG - Emailed with support and ERP PM regarding call to discuss next steps with matrix item error issue, walkthrough 1 call with client to review current look and feel of store. Implementation of a number of changes requested during walkthrough including removal of quotes and store locator in header,additon of categories, creation of landing pages, footer color adjustments and footer link redistribution, css for for item images adjustments on PDP 9/1 CG - Emailed WD FC to assist with upcoming walkthrough on WD project and provide prospective to overlap areas with SC. Worked on adjustments to size list to ensure proper function with matrix items. Provided client with required changes 8/20 CG - completed psession 2. Client had a number of adjustments requested which will be worked through next week. Requested they complete their item update, and item categorization updates before 8/25 to stay on track with ERP schedule 8/9 CG - Completed WSSR setup with staging domain. Client has not delivered images they are asking me to review for proper formatting. Also wants to have us allow for larger images than the theme doc notes supporting. Looking into workarounds. 7/28 CG - Met with client 7/20 to discuss readiness for kickoff call. Client confirmed they were not ready to kickoff for 7/23. Answered a number of questions at the time. Client emailed today to ask a few remaining questions and tentatively set kickoff for next week 07/07/21 ABJ: the client has installed the SS4C configuration bundle and suite commerce bundle. i have also wrapped up installing bundles for the client. We are going to proceed to field sets. i am also confirming with the client on what theme they are wanting to use. 06/23/21 ABJ: today we had our getting ready for commerce meeting. the client is going between the summit theme and the threads theme. they are leaning towards summit. sturbridgeyankee.com is their current domain that is hosted through network solutions. #SC-ONLY | 2021-08-03 | Green, Chris |  |  | Villaverde, Alfredo | 2022-01-03 | 2.5 | 2022-01-03 | 2021-09-07 | 100263458 | 154 | 154 | 660.35 | New Business
J882343 | #SC-ONLY |  | #SC-ONLY | S.M.G. Supply Inc. - Professional Services : Activation - SuiteSuccess for Commerce | Farsedakis, George | In Progress | 2023-06-01 | Revised | 268 | Joint | #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2022/11/01 JDF Notes on main job | 2023-03-03 | Joshi, Aarti |  | Bazzani, Emiliano | Floyd, Jason D |  | 67 | 2023-06-01 | 2023-03-01 | 133862439 | 0 | 0 | 83.35 | New Business
J902806 | #SC-ONLY |  | #SC-ONLY | K.A. Sims Construction Company, Inc. - Professional Services : Activation - SuiteS | Blakely, Mike | Monitoring - Post Go-Live | 2023-03-31 | Actual | 122 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 5/1/23 - mblakely setting to monitoring post go live and transiting the client to support and ramping down. 3/31/23 - mblakely we have switched the domain over - this is a continuation job where the client essentialy paid to work with me again. So we are live in a sense that the domain is live, but has not sent customer access or done SEO recomendations and will do those during April and May. I have set the expectation that the job ramps down in June. 3/15/2 - mblakely - so we are back with Mr. Simms overall how this job was extended/car'ed, does not feel right - the AMO left NetSuite and to push this through had the client signup for another SS4C Job, and maybe promissed the client a credit for it, and said I (Mike Blakely - FC would do it)... so that's just dandy. SS4C jobs need the ability to extend this is a good example why. | 2022-02-21 | Blakely, Mike |  |  | Cristobal, Kevin S | 2023-03-31 | 49.25 |  | 2023-05-01 | 142287937 | 403 | 403 | 458.35 | AMO
J886511 | #SC-ONLY |  | #SC-ONLY | Top Rollshutters Inc. - Professional Services : Activation - SuiteSuccess for Comm | Villa, Myr Angeli | Delayed - Per Customer |  |  | 237 | Standalone | #SC-ONLY 5/15/23 MV: As discussed with the AMO, customer will have to purchase a new implementation job since they cannot start the SuiteCommerce before the SOW expires due to ERP. 4/18/23 MV: Sent a follow to the customer to get an update on ERP and the earliest availability to start the SC implementation. 1/5/2023 MV: Done with the GRC. According to the client, the start of SC implementation might get delayed as they need to complete the ERP. No date for the kick off yet. |  | Villa, Myr Angeli |  |  | Bazzani, Emiliano |  | 76 |  |  | 135667349 |  |  |  | New Business
J880913 | #SC-ONLY |  | #SC-ONLY | Austin EV, Inc. - Professional Services : Activation - SuiteSuccess for Commerce | Bertorelli, Yvonne A | In Progress | 2023-05-02 | Revised | 275 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) 5/17/2023 - YB - Customer finally has the green light to open the site tomorrow 5/18. 4/21/2023 - YB - Customer continues to be delayed awaiting their permit to go live. No new date provided by the customer, as soon as the permit is provisioned they will launch. 3/27/2023 - YB - Customer is set to go live 3/28 but this might need to move out as they are awaiting a permit to be able to officially launch the site. Go live date will be reset daily as needed. 2/24/2023 - YB - Customer has moved go live to 3/28 and are now asking for a new theme. They have only one product but it has a large number of images and they didn't like the image display on the for the gallery. 2/22/2023 - YB - Customer moved launch date but they are still not ready, will need to see what they plan to do on our call tomorrow. They are launching with one item for now with plans to add the NetSuite Configurator to truly allow their customers to customize their cars. 1/26/2023 - YB - This customer wants to launch their site with one item which should have been simple but they have not focused on this work until now. They lost the person who was originally doing the work and now a new resource is trying to get up to speed. They have not signed with a payment provider. 1/5/2023 - YB - Still see no progress on the site and customer says they must be live by 2/14 12/15/2022 - YB - Customer is working on other internal projects which has taken away the focus from this site. They are planning now for their soft launch on 1/24 and full launch on 2/14 11/16/2022 - YB - Customer has a single product that I am still waiting to be created so we can confirm all the options are correctly configured. They want to do a soft launch in December to allow themselves time to fully test and complete the site before doing the official launch to their customers. 10/17/22 - MV - Go live will likely move to December. ERP data (e.g. Payment Profile, Item Records, Shipping Accounts) are not established yet in NS. 10/6/22 - MV - Done on PS (9/30). Client had started on offline config and site development. 9/23/22 - MV - GRC done (9/2) and Project Kick Off started. Client would like to live on 10/11 Job's Email Address: messages.NLCORP.523169582.b573e3f6a9@nlcorp.email.netsuite.com 8/26/22 - KSC - KT done; Welcome Email sent | 2022-09-22 | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 25.75 | 2023-05-02 | 2022-12-12 | 133497434 | 0 | 0 | 245.35 | AMO
J914779 | #SC-ONLY |  | #SC-ONLY | Brooklyn Bedding LLC ¦ Activation - SuiteSuccess for Commerce | Villa, Myr Angeli | In Progress |  |  | 51 | Standalone | #SC-ONLY (tracking tag DO NOT DELETE) Job email: messages.NLCORP.549190274.09bd36e5dc@nlcorp.email.netsuite.com 5/19/23 MV: Set up a follow up cal next week 4/25/23 MV: Done with GRC call 4/17/23 KSC: welcome email sent 4/17/23 MV: Sales to PS KT Set | 2023-04-25 | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 76 |  |  | 146558257 | 0 | 0 | 30.35 | AMO
J889076 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Colectivo Coffee Roasters, Inc. ¦ Consulting Time | Haugh, Donna | In Progress | 2023-01-18 | Original | 216 | Joint | #SC-CUSTOMIZATION 28-Apr-2023 (MC) overage approved 4/28/2023 DH: 40 hours Overage requested to complete Mem Transaction customization (23 hrs) and close open items for Split Order customization (11.5 hrs). The Split Order transaction custom work took much more time than estimated to complete due to complexities. SOW Extension requested to complete open items and transition and close out job. |  | Blakely, Mike |  | Bazzani, Emiliano | Williamson, Eric |  | 0.75 |  | 2023-01-18 | 136948136 |  |  |  | New Business
J897224 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Advanced Pump & Equipment Inc. ¦ Implementation Service - Fixed Bid | Bertorelli, Yvonne A | In Progress | 2023-05-30 | Revised | 168 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) 5/17/2023 - Please track updates on J897198 4/21/2023 - Please track updates on J897198 3/28/2023 - Please track updates on J897198 2/27/2023 - Please track updates on J897198 1/27/2023 - Please track updates on J897198 | 2023-02-16 | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 25 | 2023-05-30 | 2023-05-15 | 139581677 | 0 | 0 | 98.35 | AMO
J902999 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | The Spice & Tea Exchange Distribution LLC ¦ Consulting Time | Nassar, Frank | In Progress | 2023-06-20 | Original | 120 | Joint | #SC-CUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 05/15/23: We are in the process of the Site Configurations and Asset Development phase of the project. We are also review implementation timeline as Ecomm maybe pushed to a later phase. 4/27/23 FN: Completed FRD Recipe approved / One change to review on the Store locator needs to be completed / reviewed. Personalization's should be completed by 5/1. 4/7/23 CG - Confirmed gap with store locator customization. Creation of all client requested functionality will require SCA. 03-29-23 FN: Part 2 of the Customization discovery call scheduled for 3-29. Client currently working on data etc. deliverables. Current concerns - Client purchased standard SCA and premium may be required. Client also implementing 90 FO and SCA has a limitation of 100. This will be addressed by the sales team. 03-20-23 FN: We have completed the Completed Getting Ready for Commerce Meeting and currently prepping for the Customization Discovery Call 3/24 03-06-23 FN: SC project will kick 0ff on March 10 with the Commerce Kickoff call. They are now set for a June 20th go live. 02-18-23 FN: Meeting with EComm team to review project objectives and prerequires needed. We are still in the process of working with the client to determine the implementation timeline for Ecomm. | 2023-02-09 | Green, Chris |  | Bazzani, Emiliano | Murphy, Ryan |  | 611.25 |  | 2023-06-20 | 142376368 | 0 | 0 | 105.35 | New Business
J807516 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Van Beek's Landscape Supply LTD. ¦ #SC-CUSTOMIZATION Consulting Time | Onkka, Brady | In Progress | 2030-01-01 | Revised | 883 | Standalone | #SC-CUSTOMIZATION TRACKING TAG - DO NOT DELETE-KEEP AT TOP OF EXEC UPDATE) Please refer to Job J807522 4/14/23 - BO - Client currently scheduled to go live on 4/18/23. Customer had calculator customization tweaked, for notes see task on implementation job. Confirmed complete on 4/13/23 9/2/22 - BO - Client has multiple additional customizations being requested. this may change us from SC to SCA 8/5/22 - BO - Client is currently escalating regarding their Shipping solution. Client expected Netscore to host this solution, but conformed that their solution would not work for store. 1/20/22-JAL-PS has just recently started working with client again. Implementation now on going. |  | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 100.75 | 2030-01-01 |  | 88758229 |  |  |  | New Business
J882038 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Ceek Women's Health, Inc. ¦ Implementation Service - Fixed Bid | Joshi, Aarti | Monitoring - Post Go-Live |  |  | 269 | Standalone | #SC-CUSTOMIZATION 02/23/2023: Will be working AVA tax configuration validation this week. Please refer parent job "J882104" for more details. | 2022-10-06 | Joshi, Aarti |  |  | Bazzani, Emiliano |  | 0.5 |  |  | 133817455 | 0 | 0 | 231.35 | AMO
J892696 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | The Sykes Group, LLC ¦ Implementation Service - Fixed Bid | Blakely, Mike | In Progress | 2023-04-04 | Original | 190 | Standalone | #SC-CUSTOMIZATION EB All references to updates and documentation will be saved under J892627 2/28/23 AVV - Setting to in progress status to allow time entires to flow through OA integration |  | Blakely, Mike |  |  | Bazzani, Emiliano |  | 18.25 |  | 2023-04-04 | 138295305 |  |  |  | New Business
J895555 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Dugmore & Duncan, Inc. ¦ Implementation Service - Fixed Bid | Farsedakis, George | In Progress | 2023-06-01 | Original | 176 | Joint | #SC-CUSTOMIZATION 5/18/22 mblakely - client work is going well - site will be ready for erp go live July 5th, customer access will be given in late July. 12/5/22- JRH- ERP welcome letter sent |  | Blakely, Mike |  | Bazzani, Emiliano | Haines, Jefferson R |  | 21 |  | 2023-06-01 | 138994958 |  |  |  | New Business
J889972 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Ohio Taxidermy Supply, Inc. ¦ Implementation Service - Fixed Bid | Estellano, Santiago | In Progress | 2023-01-16 | Original | 209 | Standalone | #SC-CUSTOMIZATION 02-may-23: SOW extension complete, uploaded signed document 04-apr-23: job close to expiration date, notified customer 28-feb-23: test matrix items created 29-nov-22: review main job J889938 Ohio Taxidermy Supply, Inc. | 2022-12-20 | Estellano, Santiago |  |  | Bazzani, Emiliano |  | 41.75 |  | 2023-01-16 | 137181059 | 0 | 0 | 156.35 | AMO
J898108 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Infinity Sports, Inc. ¦ Implementation Service - Fixed Bid | Krikau, Timothy | In Progress | 2023-08-01 | Revised | 160 | Joint | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) TJK 5/22/23 - Project Schedule moved to 8/1 - new Project Lead assigned for all eComm deliverables. TJK 3/13/23 - Data rationalization is still an issue and having an impact on the overall schedule. TJK 2/28/23 - Project is progressing, resources assigned - customer is having issues rationalizing their item data and that is holding up all areas of the project. Schedule is at risk, but scope and budget are in tact. TJK 1/18/23 - Project Kicked off, Getting Started Sessions began, action items assigned. |  | Joshi, Aarti |  | Cristobal, Kevin S | Marchlewski, Holly |  | 2.5 | 2023-08-01 | 2023-04-03 | 140258212 |  |  |  | New Business
J899312 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | CPI Card Group Inc. ¦ Implementation Service - Fixed Bid | Farsedakis, George | Delayed - Per Other Project | 2023-11-30 | Original | 154 | Joint | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) |  | Joshi, Aarti |  | Cristobal, Kevin S | Haines, Jefferson R |  | 24.5 |  | 2023-11-30 | 140510489 |  |  |  | New Business
J889077 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Equator Coffees, LLC ¦ Consulting Time | Blakely, Mike | In Progress |  |  | 216 | Standalone | #SC-CUSTOMIZATION (Tracking TAG DO NOT DELETE) 4/26/23 - KSC - Reviewed current situation with Mike. We made an effort to send an SOW extension, but the client rejected it, and wants to talk about it. It seems like this customization is no longer needed, but it's possible that the hours might need to be repurposed. I am reaching out to AMO to see if there is any news about this. | 2022-11-21 | Blakely, Mike |  |  | Cristobal, Kevin S |  | 45 |  |  | 136948137 | 0 | 0 | 185.35 | AMO
J899440 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Blu Distribution LLC ¦ Implementation Service - Fixed Bid | Joshi, Aarti | In Progress |  |  | 153 | Standalone | #SC-CUSTOMIZATION Please refer parent "J899466" job for more details | 2023-01-20 | Joshi, Aarti |  |  | Bazzani, Emiliano |  | 1.5 |  |  | 140516604 | 0 | 0 | 125.35 | New Business
J896974 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Wallace Farm, Inc. ¦ Implementation Service - Fixed Bid | Noya, Maria | In Progress |  |  | 170 | Standalone | #SC-CUSTOMIZATION Feb 14th 2023 - MN: BOPIS is set up - however, we cannot remove the shipping option - investigating what we can do about this Jan 18th 2023 - MN: Started to set up BOPIS December 27th 2022 - MN: Starting to configure BOPIS this week | 2022-12-27 | Noya, Maria |  |  | Bazzani, Emiliano |  | 21.5 |  |  | 139419100 | 0 | 0 | 149.35 | AMO
J892172 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Sundance Institute ¦ Consulting Time | Blakely, Mike | In Progress |  |  | 197 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) 5/18/23 - mblakely feng is pushign this into prod this week - client has given the ok 12/20/22 - mblakely - AMO scheduled a sync on this with client - it appears the scoping on this was incorrect client is on Elbrus the "easy" recapcha extension does not work on this. I know the client told us they were on Elbrus - knowing Beckey they are on top of things. |  | Blakely, Mike |  |  | Cristobal, Kevin S |  | 3.25 |  |  | 138102364 |  |  |  | AMO
J862541 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Think Ink, Inc. ¦ Implementation Service - Fixed Bid | Villa, Myr Angeli | In Progress |  |  | 402 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) 4/26/23 - MV- UAT is in progress. Request a SOW extension. 4/17/23 MV: UAT is in progress 2/14/23 - AJ - Overage for 40 hours entered to accomodate SiteBuilder branding. This is EWS customer. 10/19/22 MV: Aligned with the client to review the requirements for customization (10/17). Sent a request for SOW extension. Pending customer's signature on Docusign. | 2022-06-28 | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 11.5 |  |  | 125861044 | 0 | 0 | 331.35 | AMO
J900446 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Lowcountry Block, LLC ¦ Consulting Time | Floyd, Jason D | In Progress | 2030-07-14 | Revised | 154 | Joint | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) Notes on job J849290 4/17/23 - BO - Client calls are progressing. Client has passed over requirements for requested shipping customization. Requirements passed over to AMO for scoping. |  | Onkka, Brady |  | Cristobal, Kevin S | Floyd, Jason D |  | 34.5 | 2030-07-14 | 2023-04-03 | 140766136 |  |  |  | AMO
J901348 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Wilfrid Laurier University ¦ Punchout Integration | Annamalaisamy, Athiappan | In Progress | 2023-06-01 | Original | 135 | Joint | #SC-CUSTOMIZATION #CAMPUS (tracking tag DO NOT DELETE) This change order is part of the parent Job, J870507 Wilfrid Laurier University. All progress updates of it will be tracker under that. | 2023-01-09 | Bertorelli, Yvonne A |  | Bazzani, Emiliano | Raghavan, Vidhya |  | 98.25 |  | 2023-06-01 | 141378757 | 0 | 0 | 136.35 | AMO
J917661 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Dillanos Coffee Roasters, Inc. ¦ Implementation Service - Fixed Bid | Kayastha, Piyush D | Assigned |  |  | 28 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) see J917663 for updates |  | Kayastha, Piyush D |  |  | Cristobal, Kevin S |  | 217 |  |  | 148015645 |  |  |  | AMO
J813179 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | City Mill Company Limited ¦ #SC-CUSTOMIZATION Consulting Time | Komin, Alain | In Progress | 2023-08-01 | Revised | 784 | Standalone | #SC-CUSTOMIZATION (TRACKING TAG - DO NOT DELETE) 03/30/2023 AKOMIN: Setting this job as Delayed Per Customer. 03/06/2023 AKOMIN: Customer informed that the Go Live was pushed until August 2023. 1.17.23 (MC) overage approved 11/14/22 AK: All customizations completed. Meeting with Dani today to review BOPIS+Backorder posibility. 2/16/22 TE: FRD is being reviewed internally. Customer progressing through offline configuration with our help/continued meetings. 1/18/22 TE: Personalization Sessions in progress; customer is working through offline configuration as well. FDD is being reviewed by technical consultant. 1/11/22 TE: Personalization Sessions in progress; targeted to complete by Jan 22 so we can begin FDD process. 10/15 SJE -- - Waiting for customer to respond re customizations 10/8 SJE -- - Original customization request cannot be completed in SC, and thus the CIty Mill team will need to leverage native NS BOPIS functionality that displays locations in a pop up 10/1 SJE -- - FRD review with ERP -- inventory display tied to ERP customization 9/24/21 SJE -- - FRD creation: In-Progress 9/17/21 SJE -- - FRD creation in process 9/10/21 SJE -- - Requirements Gathering sessions scheduled for 9/13 9/3/21 SJE -- - Requirements Gathering sessions scheduled for 9/13 8/20/21 SJE -- - Personalization sessions to begin week of 11/1 8/13/21 SJE -- - Customer is much farther ahead than ERP POC understood. Dani is the eComm POC and she is well aware of what items need to be completed to become data ready - Personalization sessions to kick off 11/1 8/6/21 SJE -- - Customer not prepared to begin SC work - Attended a meeting with ERP to learn they will not go live until 3/1/22 - Planning session scheduled with the City Mill team for 8/11 to share what data we need in ERP in order to begin our sessions - Potentially planning to engage heavily in January to start eCom work 7/30/21 SJE -- - PM Intro: Scheduled for 8/11 - Project will not be done by 9/1 as Personalization sessions have not started - new go live date TBD 7/21/21 SJE -- - ERP/FC KT: complete - PM Intro: Requested - Need to determine how we will proceed with work 05/14/2021 AKOMIN: Customer is delayed in terms of Getting Ready for Commerce. 06/18/2021 AKOMIN: Implementing BOPIS functionality. | 2021-12-23 | Komin, Alain |  |  | Villaverde, Alfredo |  | 104 | 2023-08-01 | 2022-03-01 | 93002847 | 0 | 0 | 518.35 | New Business
J871808 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Iowa State University of Science and Technolog¦ Implementation Service - Fixed Bid | Noya, Maria | In Progress | 2023-03-01 | Revised | 359 | Standalone | #SC-CUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) Feb 14th 2023 - MN: SSO configured - pre go live checkpoints and adjustments in implementation job Jan 18th 2023 - MN: SSO configured - UATs in implementation job December 27th 2022 - MN: SSO is configured October 17th 2022 - MN: Will start this upcoming week. October 2nd 2022 - MN: Will start sometime in the next weeks September 15th 2022 - MN: Will start sometime in the next weeks September 5th 2022 - MN: Waiting to kickoff (we´ll kick off this week) August 17th 2022 - MN: Waiting to kickoff (we´ll kick off the first week of September) July 29th 2022 - MN: Waiting to kickoff July 16th 2022 - MN: Waiting to kickoff July 2nd 2022 - MN: Waiting to kickoff | 2022-12-01 | Noya, Maria |  |  | Bazzani, Emiliano |  | 51 | 2023-03-01 | 2023-01-30 | 128688049 | 0 | 0 | 175.35 | AMO
J902927 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Stanley Black & Decker, Inc. : 3xLOGIC, Inc. ¦Consulting Time | Komin, Alain | In Progress |  |  | 120 | Standalone | #SC-CUSTOMIZATION (Tracking Tag DO NOT DELETE) Main Job: J902927 |  | Komin, Alain |  |  | Cristobal, Kevin S |  | 8 |  |  | 142341247 |  |  |  | AMO
J872026 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Way To Be Designs, LLC ¦ Implementation Service - Fixed Bid | Bertorelli, Yvonne A | In Progress | 2023-07-10 | Revised | 359 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) 5/17/2023 - YB - Requested SOW extension but it is just sitting there, opened a UTS ticket yesterday but still nothing. I will give it a couple of days and then escalate. 4/21/2023 - YB - Escalated to DL - the customer and I have reviewed all the customizations outlined in the SOW and they have decided they do not want any of them. They will go with what can be accomplished natively. Working to see if we can use the hours here to take them to go live as the activation job will expire next month. 4/5/2023 - YB - Customer has completed personalization sessions and appears to be actively working on their site. Joining calls to see what is needed in regards to this custom job. 2/27/2023 - YB - Customer has been one delay after another to get started on SC - I am stalled until that portion of the project begins. 1/26/2023 - YB - Customer has still not started his personalization sessions. 12/23/2022 - YB - Customer has still not kicked off on the SC activation job, if they continue to push will place this on delayed per customer. 11/21/2022 - YB - Personalization sessions have not yet begun. Waiting for them to kick-off so I can follow behind to get the requirements for the customization work needed. 1/31/2022 - YB - Personalization sessions should be underway in the next month. 10/13/2022 - YB - Customer has indicated they will go live sometime in Q1 of 2023. Once personalization sessions are complete we can begin gathering the requirements and getting ready to work on customizations. 9/27/2022 - YB - Customer has engaged with Brady for the initial GRC that is scheduled for Friday. |  | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 283 | 2023-07-10 | 2023-01-30 | 128728630 |  |  |  | AMO
J894825 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | United Motorsports Online, LLC ¦ SC Customizations | Lee, Julianne | In Progress | 2023-06-01 | Revised | 176 | Joint | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) 4/11/23 JL: Rework on coding due to changes in customer requirements (field changes). Testing & issue resolution on going. Moving budget to yellow for potential overage. 3/29/23 JL: Targeting mid-April golive for customization portion. Customer data issues holding up the implementation. 3/02/23 JL: Base webstore is live. Customization in progress. 2/15/23 JL: Current plan is to Go Live without the vehicle finder customization on 3/01. Customization will be deployed post-Go Live once fully tested. 1/05/23 (JL): Customer PM still pushing for Feb-1 go live and challenging SuiteCommerce delivery timeline; wants the SC resource to be more aggressive with tasks. Item search ERP customization will have to be redone and retested to be compatible with the website. 12/09/22 (JL): SuiteCommerce resource assigned; KT and GS meeting with Ray scheduled for next week. |  | Bertorelli, Yvonne A |  | Cristobal, Kevin S | Riccardi, David |  | 22.5 | 2023-06-01 | 2023-02-28 | 138922097 | 0 | 0 |  | New Business
J885281 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | MaryRuth Organics, LLC ¦ Consulting Time | Villa, Myr Angeli | In Progress | 2023-05-15 | Revised | 244 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) Parent job: J885281 5/23/2023 MK - Overage of 80 hours approved by VL Meenakshi Krishnan to support missed Tech services scripting deliverable. Job record has been updated. |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 68 | 2023-05-15 | 2023-01-03 | 135380024 |  |  |  | AMO
J842110 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Norelco SafeCam : 5982374 ¦ Implementation Service - Fixed Bid | Green, Chris | In Progress | 2023-08-09 | Revised | 562 | Standalone | #SC-CUSTOMIZATION (Tracking tag) Refer to J842111 for updates 4/27 CG - Switched to in progress after recording video for client on how to handle translations imports per their request. Noted an issue with how client is trying to handle translations via Google Translate which lead to space characters that break the xlf file. Advised client will need to look at alternative translation methods 4/27/23 BA - Switching to In Progress for stuck time |  | Green, Chris |  |  | Cristobal, Kevin S |  | 57.75 | 2023-08-09 | 2022-03-18 | 113559981 |  |  |  | AMO
J914677 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Turf Control LLC ¦ Consulting Time | Kayastha, Piyush D | In Progress |  |  | 52 | Standalone | #SC-CUSTOMIZATION |  | Kayastha, Piyush D |  |  | Bazzani, Emiliano |  | 23.75 |  |  | 146498117 |  |  |  | AMO
J902043 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Premier Manufacturing Products, LLC ¦ Consulting Time | Estellano, Santiago | In Progress |  |  | 127 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) Refer to J883000 for updates |  | Estellano, Santiago |  |  | Cristobal, Kevin S |  | 8 |  |  | 141937728 |  |  |  | AMO
J875087 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Bull Outdoor Products, Inc. ¦ Consulting Time | Onkka, Brady | In Progress |  |  | 329 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) 5/19/23 - BO - Client did some initial reviews of Checkout, but review done with not limited product. New round of testing needed. PDP page ready for internal review. 5/5/23 - BO - Pending PDP customization being made available for testing, pending client response on cart customization for finishing/signoff. 4/14/23 - BO - Cart customization almost complete. PDP customization available for testing. |  | Onkka, Brady |  |  | Cristobal, Kevin S |  | 9.5 |  |  | 130641324 |  |  |  | New Business
J884653 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Van Beek's Landscape Supply LTD. ¦ Consulting Time | Onkka, Brady | In Progress |  |  | 247 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) 4/14/23 - BO - Feng has gotten all customizations ready for launch. Client has requested a minor change to one and we will review it post launch. L:aunch scheduled for 4/18/23 11/21/22 - BO - FRD sent to customer for review |  | Onkka, Brady |  |  | Cristobal, Kevin S |  | 165.25 |  |  | 134976918 |  |  |  | AMO
J894245 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Veritas Press, LLC ¦ Consulting Time | Flores, Billy | Monitoring - Post Go-Live | 2023-04-01 | Actual | 184 | Joint | #SC-CUSTOMIZATION 5/19/23 BJF : Parent Job closed ; Waiting on billables from EC to close out this consulting job. Job will be closed by 5/26 5/5/23 BJF : Monitoring post-go live support; Team looking into Ship Central work flow / Packing list generation via mobile device. Transition to support session will happen 5/10. 4/14/23 BJF : Monitoring post-go live support; No issues reported. Minor issue with item groups reported working with John and Peter from TS on the issue. 4/4/23 BJF ; Customer officially live as of 4/1/23; Currently in Monitoring - Post Go live status 3/24/23 BJF : NS PM has presented UAT go live readiness sign off to the customer ; customer is going live with ERP/WMS/ SC and 4 x customizations on 4/1/23. No major issues reported at this time. 1/20/23: Suite commerce personlization's sessions in full swing. Customer in the process of refining themes and other requirements for Suite commerce. 1/13/23: Suite commerce personlization's sessions in full swing. Customer in the process of refining themes and other requirements for Suite commerce. 1/6/23 BJF: ERP/WMS WT1's will be completed on 1/9/23. WMS WT1's will wrap up on January 6th. ; Customer will deliver action items from session by 1/9/23 to begin SC efforts. 12/23/22 BJF: Personalization sessions completed for ERP/WMS, 2 x sessions for WT1 hosted the week of the 19th, WT1's should wrap up by January 5th. WMS WT1's will wrap up on January 6th. ; Customer will deliver action items from session by 1/9/23 to begin SC efforts. 12/16/22 BJF PK engage with customer ; Hosted SC kickoff on 12/12 ; Customer will deliver action items from session by 1/9/23 12/7/2022: BJF: Welcome Letter Sent out via Jeff Haines DL ; PK added the the customers environment. | 2022-12-12 | Kayastha, Piyush D |  | Bazzani, Emiliano | Haines, Jefferson R | 2023-04-01 | 74.5 | 2023-03-20 | 2023-04-01 | 138838221 | 110 | 110 | 164.35 | New Business
J788402 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Nowak Dental Supplies, Inc. ¦ #SC-CUSTOMIZATION Consulting Time | Villa, Myr Angeli | In Progress | 2022-11-30 | Revised | 1091 | Standalone | #SC-CUSTOMIZATION (TRACKING TAG - DO NOT DELETE) 10/24/22 MV: Go live will move to Nov 30 due to client readiness. Requested for SOW extension to extend the current engagement to 6 months. 9/23/22 MV: Go live will move to next month due to client readiness. 04/26/22 JRT: SOW Extension has been processed and signed by Oracle and Shawn Nowak. Go-Live date is extended to 09/30/2022. 03/15/22 JRT: Shawn Nowak would like to move the Go-Live date to 05/01/2022. 2/16/22 TE: Client keeps skipping weekly calls and saying he's too busy. Has pushed off next meeting till 3/15. I'll reach out to let him know our SOW expires at the end of March so anything we can do to prioritize this work. 1/18/22 TE - SOW signed and processed. Weekly customer meeting in progress. 1/11/22 TE - Job has expired; SOW extensions submitted. Customer is working on offline config and ERP implementation. 11/30/21 TE - Personalization Sessions complete. Offline config starting and weekly check-in's have been scheduled. 8/29/21 RR - Job validtity extended 8/22/21 RR - Requested SOW Extension 1/4/2021 - KSC - Phase 1 still ongoing |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | -0.5 | 2022-11-30 | 2022-01-03 | 75049809 |  |  |  | New Business
J883430 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Hi-Liner Fishing Gear and Tackle, Inc. ¦ Consulting Time | Onkka, Brady | Delayed - Per Customer |  |  | 267 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) 2/28/23 - BO - Requesting extension due to client delays starting this project. Client has run into staffing and ERP issues which have delayed kickoff. Marking relationship as Yellow to account for these delays. Consulting job for 3 SS4C Sites J883275 J883277 J883278 |  | Onkka, Brady |  |  | Cristobal, Kevin S |  | 86.5 |  |  | 133956762 |  |  |  | AMO
J857095 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Banner Wholesale Grocers ¦ Implementation Service - Fixed Bid | Villa, Myr Angeli | Delayed - Per Other Project | 2023-01-31 | Original | 451 | Standalone | #SC-CUSTOMIZATION (tracking tag DO NOT DELETE) 5/19/23 MV: No action for SuiteCommerce. 4/17/23 MV: No action for SuiteCommerce for the past few weeks. Waiting for ERP to go-live. 3/17/23 MV - Go live for ERP was supposedly last week. But according to the customer, they were not able to complete the cutover tasks and go live will probably move for a couple weeks. 2/23/23 - Customization done. Waiting for ERP to go live. |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 2.75 |  | 2023-01-31 | 122047097 |  |  |  | New Business
J791833 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Snoasis Medical ¦ #SC-CUSTOMIZATION Consulting Time | Rodriguez, Amber | In Progress | 2021-11-30 | Revised | 1035 | Standalone | #SC-CUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) AR 2/22/22: Customer requested to put job on hold until April due to other projects of theirs taking priority AR 1/20/22: implementation delayed as lead developer is sick - waiting for his recovery to continue meetings with customer during UAT AR 9/22/21: meeting scheduled with customer on 9/24 to review steps for testing AR 2/10/21: development is almost complete and internal walkthrough scheduled for this week. If all goes well, customer will be sent for QA. SOW extension requested as job is expired. AR 1/14/21: development is a little more than 90% complete but testing is only 50% complete. Overage request submitted for 120 hours due to complexity of job not being properly scoped. AR 11/05/2020: FRD was signed on 10/22. I met with developers last week to give more information about requirements. Development is underway but delayed due to outages and emergency leave due to Typhoon in Manila. AR 10/09: Customer provided requests to update the FRD which are in progress. A new developer has been assigned and has been onboarded. Development is scheduled to being next or the week after. AR 9/22: FRD is 90% complete. Timeline for customer is development won't begin until first week of november. 8/3: Customer engaged and requested first session for 8/05 to get technical requirements #SC-CUSTOMIZATION (TRACKING TAG - DO NOT DELETE) | 2020-08-05 | Rodriguez, Amber |  |  | Bazzani, Emiliano |  | 10 | 2021-11-30 | 2021-05-31 | 78132531 | 0 | 0 | 1023.35 | AMO
J886491 | #SC-CUSTOMIZATION |  | #SC-CUSTOMIZATION | Trace3, Inc. ¦ NetSuite Time & Material - NEW | Onkka, Brady | In Progress |  |  | 239 | Standalone | #SC-CUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) Moving to delayed as client hasn't needed | 2022-10-14 | Onkka, Brady |  |  | Bazzani, Emiliano |  | 215.25 |  |  | 135662481 | 0 | 0 | 223.35 | AMO
J898349 | #SC-CONSULTING |  | #SC-CONSULTING | City Mill Company Limited ¦ Consulting Time #SC-CONSULTING | Komin, Alain | Delayed - Per Customer | 2023-08-01 | Revised | 173 | Standalone | #SC-CONSULTING (Tracking Tag - Do not remove) 03/30/2023 AKOMIN: Setting this job as Delayed Per Customer. 03/06/2023 AKOMIN: Customer informed that the Go Live was pushed until August 2023. 01/25/2023 AKOMIN: This job will be used for Page Title Suffix activation and for close to go live activities (meetings, UAT, Go Live, Post GL Support). | 2021-12-23 | Komin, Alain |  |  | Villaverde, Alfredo |  | 73 | 2023-08-01 | 2022-12-05 | 140301269 | 0 | 0 | 518.35 | AMO
J875132 | #SC | #POS-NSPOS-ONLY | #SC #POS-NSPOS-ONLY | Brown University ¦ Implementation Service - Fixed Bid | Raghavan, Vidhya | In Progress | 2023-11-06 | Revised | 329 | Joint | #POS-NSPOS-ONLY #CAMPUS #SC (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2023 0518 VR: Go Live pushed to Nov. UAT will begin in July. 2023 0427 VR: W/T 2 ERP in progress. Change of personnel on Brown side. ERP sessions will end in May. 2023 0413 VR: W/T 2 pushed due to customer availability. POS W/T 2 completed. 2023 0316 VR: W/T 2 prep in progress. Go live likely to be pushed. 2023 0306 VR: W/T 2 prep in progress. Delays from customer side - Go live will be pushed to Oct. to be confirmed by Brown 2023 0223 VR: Walkthrough 2 prep in progress. TS working on xml conversion customization 2023 0124 VR: Team working on action items. ad hoc meetings with the customer to review open topics and prepare for W/T 2. 2023 0105 VR: Team working on action items. 12/21/2022 HK: Configurations and action items are being worked throughout the winter break. 12/16/2022 HK: Additional O2C Process Walkthrough scheduled for 12/19. Brown U will OOO from Dec. 23rd-Jan. 6th. NS team to work through open action items during this time. 12//09/2022 HK: Final Process Walkthroughs 1s in progress. 11/18/2022 HK: Completed D2B, P2P Core, and P2P Campus process walkthrough 1 sessions. 11/10/2022 HK: WT1 sessions in progress. 11/04/2022 HK: WT1 sessions are scheduled and planned to start on 11/10. 10/28/2022 HK: WT1 sessions are still being scheduled. Configurations are in progress in preparation for WT1s. 10/21/2022 HK: WT1 Sessions are being scheduled. 2022 1011 VR: Preparing for W/T 1 10/7/2022 HK: Data migration activities are in progress. Ecommerce personalization sessions continue. 09/29/2022 HK: ERP Personalization sessions and configurations continue. 09/23/2022 HK: ERP Personalization sessions and configurations continuing. 09/16/2022 HK: No sessions scheduled this week due to university rush. Customer focusing on full list data and training. 2022 0913 VR: ERP personalization sessions continuing. 09/09/2022 HK: Integrations discussion held 09/08. 20220908 MK ¦ Updating Practice Lead to Ryan Murphy 09/02/2022 HK: P2P and D2B Personalization sessions completed 8/29 and 8/31. Data migration is still in progress. 08/26/2022 HK: Record to Report Personalization session completed 8/22. 08/19/2022 HK: Roles & Permissions meeting scheduled. Personalization sessions starting week of 8/22. 08/12/2022 HK: Personalization Session Prep Guide and meeting invites sent out. 08/05/2022 HK: Data Migration Kick Off conducted on 8/2 and first weekly status meeting conducted on 8/3. Personalization sessions scheduled. 07/29/2022 HK: SOW Review conducted on 7/26. Project Kick Off conducted on 7/29. 07/22/2022 HK: Reserve KT was conducted on 7/18. Getting Started and Kickoff Prep sessions were conducted on 7/20. SOW Review and Kick off call to be scheduled. 7/25 [ZR]: SOW review call scheduled on 26-Jul | 2022-07-29 | Lewis, Michelle | Bazzani, Emiliano | Bazzani, Emiliano | Raghavan, Vidhya |  | 391.5 | 2023-11-06 | 2023-08-01 | 130660319 | 0 | 0 | 300.35 | New Business
J823132 |  | #POS-SCIS-PLUSCUSTOMIZATION | #POS-SCIS-PLUSCUSTOMIZATION | Cornell Online LLC ¦ #POS-SCIS-PLUSCUSTOMIZATION | Desimini, Peter N | In Progress | 2023-07-01 | Revised | 729 | Standalone | #POS-SCIS-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2023 0524- PND - Customer delays in completing UAT and prep for go-live. Customer now trying to target 6/1 go live and continues to take their time to run through remaining test cases. Currently working with Adyen to fix CC device issues. | 2022-06-27 | Zenisek, Nicholas J |  |  | Bazzani, Emiliano |  | 15.5 | 2023-07-01 | 2022-03-01 | 100072774 | 0 | 0 | 332.35 | New Business
J860594 |  |  |  | Janisource, LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | Closed - Lost (Rev Rec by Finance) |  |  | 420 | Standalone | #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) JOB_EMAIL: messages.NLCORP.504451589.a21fa8e8c4@nlcorp.email.netsuite.com SCOPE: 3 Premium Plus eCommerce (Amazon, eBay, Walmart) + (J860595 1 Premium Plus BigCommerce, 1 ShipStation) 6/8/22 GD: Installed NSC SuiteApp, Connected NSC to NS and BC, configured BC order mappings and began testing 6/14/22 GD: All the order sync testing is done except there was an issue for the BC order where the discount split and posted to the header and line. I'll investigate that. Tested SS. Currently setting up BC full product mappings |  | Dunn, Geoffrey |  |  | Villaverde, Alfredo |  | 12.75 |  |  | 124392456 |  |  |  | New Business
J919403 |  |  |  | Marlo, Activation - Suite Commerce | Shea, Paul | Delayed - Per Other Project |  |  | 22 | Joint | 5/22/23 - mblakely had KT - this is a huge project and SuiteCommerce MyAccount is a tiny tiny 20 hours on it, will be on standby till closer to client go live. |  | Blakely, Mike |  | Cristobal, Kevin S | Mohanty, Rajesh |  | 21 |  |  | 148353747 |  |  |  | New Business
J884433 |  |  |  | CARCO Group, Inc. dba Cisive - PS : #SCMA Activation | Joshi, Aarti | In Progress | 2023-06-05 | Revised | 252 | Standalone | 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. 05/03 AJ : Customer is not live yet as they are discussing HTTPS concern internally. There is another job which is open to continue activation "J884433" and closing this job. 04/20/23: AJ Concern raised by customer a. HTTPS header should include header which are required. Currently If Automatic SSL is applied then it’s not including the header information which is required to follow the guidelines for the organization. b. b. As previously noted, it may not be included in the out-of-the-box solution, but you'd like to know if there is an alternative solution that can be done on either the NS or Cisive side as this could be a blocker to setup the domain in production environment and for Go Live. requested for technical resource to see the options. 3/24/23 AVV - Customer responded on UAT testing and provided feedback to Aarti. Setting job to In Progress. 03/08/23 AJ No updates from customer on UAT status and Go live. Status is yellow due to this 02/23/2023 AJ : All configuration are completed in Sandbox and client was working on UAT testing. Did not receive any update and they are currently working other priority task. Setting this job to delayed status. 05/31/2022: AJ - GR4C meeting completed. 05/03/2022: AJ - Sales KT completed. 4/29/2022 AVV - Welcome email sent 2/27/23 AVV: Setting customer relationship status to yellow due to customer de-prioritizing the tasks related to this implementation 02/23/2023 AJ : All configuration are completed in Sandbox and client was working on UAT testing. Did not receive any update and they are currently working other priority task. Setting this job to delayed status. Please refer parent job J863827 for more details. #SCMA (Tracking Tag - DO NOT REMOVE) |  | Joshi, Aarti |  |  | Villaverde, Alfredo |  | 6.25 | 2023-06-05 | 2022-11-21 | 134786578 |  |  |  | AMO
J906013 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Macon Hardwood, LLC ¦ Implementation Service - Fixed Bid | Zenisek, Nicholas J | In Progress |  |  | 99 | Standalone | #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) |  | Zenisek, Nicholas J |  |  | Bazzani, Emiliano |  | 47.5 |  |  | 143511846 |  |  |  | AMO
J910256 |  |  |  | World Wide Marketing Inc. : Ferris Marketing Inc ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 79 | Standalone | #nsc #UTOPIA-SOW (Tracking tag - DO NOT REMOVE) Scope: 1xPremiumPlus Shopify eCommerce ¦ disc: nightowl Job email: messages.NLCORP.545348125.6f645015d5@nlcorp.email.netsuite.com 3/22/23 TK - Approved overage (5h) 3/16/23 AF - sent welcome |  | Nannaware, Anurag |  |  | Villaverde, Alfredo |  | -4.5 |  |  | 144765739 |  |  |  | AMO
J906173 |  |  |  | Beekeeper's Naturals Inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 98 | Standalone | 2/27/23 - RMO JM - #NSC #STANDALONE ¦ NSC Scope: 9 Premium Plus eCommerce connectors (x6 Shoify, x2 Amazon, x1 Walmart.com) messages.NLCORP.544431986.3b5bd73ea8@nlcorp.email.netsuite.com 4/20/23 AF - after discussing with client, their ERP is not mature enough to proceed, client will follow up with us at a later time 3/7/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 93.25 |  |  | 143575841 |  |  |  | New Business
J919453 |  |  |  | Mondelez International, Inc. : Mondelez Global DiImplementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 24 | Standalone | 5/8/23 - RMO JM - #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium and Premium Plus connector Shopify 23-May-2023 (MC) overage approved |  | Buenavista, Josiah Frances |  |  | Villaverde, Alfredo |  | 23.25 |  |  | 148372252 |  |  |  | AMO
J861228 |  |  |  | GLAMCOR LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 416 | Standalone | #NSC #STANDALONE JOB_EMAIL: messages.NLCORP.502268494.ae17611de1@nlcorp.email.netsuite.com SCOPE: 4 Premium Plus eComm (4 Amazon), 2 Premium Plus Logistics (2 Amazon MCF) 3/23/2023 AVV: Customer is now re-engaged and project is now kicked off. Setting status back to green. 3/16/23 MKP: Introducing customer to new consultant (Nate) 3/7/2023 AVV: Re-engaging an SME to resume the project 2/28/23 AVV: Setting customer relationship status to yellow due to the customer's difficulty to get through their prerequisites, as well as their apparent lack of expertise. | 2023-03-23 |  |  |  | Villaverde, Alfredo |  | 37.75 |  |  | 124659212 | 0 | 0 | 63.35 | AMO
J890774 |  |  |  | Litegear, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 206 | Standalone | 11/9/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Std Shopify JOB_EMAIL: messages.NLCORP.531571719.af3eccbae7@nlcorp.email.netsuite.com SCOPE: 1 Standard Ecommerce (Shopify) |  |  |  |  | Villaverde, Alfredo |  | 7.75 |  |  | 137368541 |  |  |  | New Business
J906066 |  |  |  | Hyer, Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 98 | Standalone | 2/23/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 1 x NS Premium Plus eCommerce Connector - Shopify messages.NLCORP.543394619.c8c9b508a1@nlcorp.email.netsuite.com 2.27.23 MK - Overage of 5 hours approved for project management hours. Approved by VL Meenakshi Krishnan. Job Record has been updated. 2/27/23 AF - sent welcome |  | ALURI, DINESH |  |  | Villaverde, Alfredo |  | 5 |  |  | 143518413 |  |  |  | AMO
J882987 |  |  |  | Monday Motorbikes, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | Closed - Lost (Rev Rec by Finance) |  |  | 267 | Standalone | 9/13/22 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ NSC Scope - Vendor Mgnt + 1 Shopify JOB_EMAIL: messages.NLCORP.525607686.38e5fad865@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus eCommerce (Shopify) |  |  |  |  | Villaverde, Alfredo |  | 24 |  |  | 133934062 |  |  |  | New Business
J913812 |  |  |  | BankSupplies, Inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 55 | Standalone | 4/7/23 - RMO JM - #NSC #STANDALONE ¦ Premium Plus Walmart, eBay, Amazon CA, Amazon US and 1 Premium Connector Add-on for Amazon US messages.NLCORP.548153240.e64449e4bd@nlcorp.email.netsuite.com 4/7/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 39.5 |  |  | 146253584 |  |  |  | AMO
J916698 |  |  |  | Sanver Supply, LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 31 | Standalone | 5/2/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Starter Amazon |  |  |  |  | Villaverde, Alfredo |  | 9 |  |  | 147849539 |  |  |  | New Business
J873506 |  | #POS-NSPOS-PHASE | #POS-NSPOS-PHASE | Montana State University Book Store, Inc.¦NetSuite Time & Material - NEW | Serron, Sennon A | Delayed - Per Accounting |  |  | 345 | Joint | #POS-NSPOS-PHASE2 5/17 Sennon This project is being closed as per instructions received from Hans Sommers [Consulting Solution Manager]. No hours have been utilized on this project. This customer was engaged on a Suite Inspire project and now the AMO [Katie Saltiel] is working to get this client to utilize ACS for further post Go Live support. That said the client has not been responsive to the AMO emails. |  | Serron, Sennon A | Bazzani, Emiliano |  | Peterson, Suzanne |  | 50 |  |  | 129632069 |  |  |  | AMO
J914284 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Wallace Electrical Systems L.L.C. ¦ Implementation Service - Fixed Bid | Shea, Paul | In Progress | 2023-10-02 | Original | 55 | Joint | #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 05/23 - requested resource for implementation of Work Order Queue 05/19 - continue Personalization - Subsidiary structure will be a challenge 05/10 - beginning Personalization Sessions w/Getting to Know your Business 05/01 - Held Data Strategy meeting, reviewed User Adoption Toolkit & Project Plan 04/25 - Held KickOff meeting - Data Strategy planned for 4/28 04/12 - Held Getting Started Session today, planning for KickOff 4/25 | 2023-04-25 | DeCotis, Brian J | Bazzani, Emiliano |  | Mohanty, Rajesh |  | 934.85 |  | 2023-10-02 | 146302829 | 0 | 0 | 30.35 | New Business
J916235 |  |  |  | Anodyne, LLC. ¦ NetSuite Time & Material - NEW | Bertorelli, Yvonne A | In Progress |  |  | 38 | Standalone |  |  | Bertorelli, Yvonne A |  |  | Cristobal, Kevin S |  | 19.5 |  |  | 147579186 |  |  |  | AMO
J874738 |  |  |  | Cygnet Online, LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 325 | Standalone | 7/13/22 - RMO JM - #NSC #STANDALONE 5/4/2023 AF UAT in Progress 4/27/2023 AF ShipStation setup call with FC 2/23/23 AF - client ready to move forward, discussing prerequisites 10/18/22 AF - client requested to wait on implementation for WMS and ERP project to mature 10/7/22 AF - extension signed by client, waiting on contracts 9/26/22 (MC) - approved overage |  | Klein, Adam D |  |  | Villaverde, Alfredo |  | 43.5 |  |  | 130547349 |  |  |  | AMO
J878759 |  |  |  | Top Gard LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | Monitoring - Post Go-Live | 2023-03-06 | Actual | 297 | Standalone | 8/12/22 - RMO JM - #NSC #STANDALONE messages.NLCORP.522301714.3dd22a3ada@nlcorp.email.netsuite.com 5/18/23 AF - client live 4/28/23 AF - client to turn on connectors next week 4/11/23 AVV - requested AMO for assistance as the customer is completely unresponsive. Targeting job closure by EOM. 4/11/23 AF - told client we would close the job as they have been non-responsive 4/3/23 AF - requested client sign SOW extension 3/28/23 AF - client followed up again, repeating old request to just get job completed while still ignoring what our email contained 3/28/23 AF - no response from client, followed up 3/24/23 AF - client finally replied, asking about getting job finished but ignored asks in previous email, replied going over previous asks 3/10/23 AF - FC following up on testing status, brought in AMO due to client lack of responsiveness. 3/6/23 AF - job completed, client testing 2/27/23 AVV - Customer relationship at yellow because of customer's habitual unresponsiveness 2/24/23 AF - client finally got back to use and wants to move forward 2/23/23 AF - sent follow up on next steps, as they have not responded 12/20/22 AF - client finally responded but said they would need at least a month if not more to be ready to move forward. 12/20/22 AF - sent follow up as no reply to Anuhya, said we would close out project 10/31/22 AF - Anuhya sent prereq breakdown follow up 10/26/22 AF - sent sow for extension 9/13/22 AF - sent follow up 8/18/22 AF -sent welcome |  | ALURI, DINESH |  |  | Villaverde, Alfredo | 2023-03-06 | 3.5 |  |  | 132376556 | 0 | 0 |  | AMO
J886618 |  |  |  | The Jack Olsta Co ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 237 | Standalone | 10/12/22 - RMO JM - #NSC #STANDALONE ¦ Magento JOB_EMAIL: messages.NLCORP.528283800.d838313f25@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus Ecommerce (Magento) |  |  |  |  | Villaverde, Alfredo |  | 7.25 |  |  | 135691195 |  |  |  | New Business
J898282 |  |  |  | E-Town Marketing & Distributing LLC ¦ Consulting Time | Farmer, Andrew | Monitoring - Post Go-Live |  |  | 160 | Standalone | 12/21/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Std Shopify and Prem Shispstation messages.NLCORP.536086355.89ce920881@nlcorp.email.netsuite.com 02/06/23 (Nate) - Configuration is complete, but Go-Live is blocked by NS Support Case 5038334. Shipping address from Shopify order does not always post correctly to NS. 12/24/22 (MC) - 5 hour overage approved for PM hours not included 12/23/22 AF - sent welcome |  | Nannaware, Anurag |  |  | Villaverde, Alfredo |  | 4 |  |  | 140275257 |  |  |  | AMO
J901094 |  |  |  | Falcon's Treehouse LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 140 | Standalone | 1/12/23 - RMO JM - #NSC #STANDALONE ¦ Prem+ Shopify JOB_EMAIL: messages.NLCORP.538375233.5d12658554@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus Ecommerce (Shopify) |  |  |  |  | Villaverde, Alfredo |  | 10 |  |  | 141118124 |  |  |  | New Business
J896744 |  |  |  | New Signature Homestyles, LLC ¦ Consulting Time | Preedanon, Melinda | Monitoring - Post Go-Live |  |  | 174 | Standalone | #NSC #UTOPIA-SOW (tracking tag - do not remove) JOB_EMAIL: messages.NLCORP.535030477.d4750ae471@nlcorp.email.netsuite.com SCOPE: 3 Upgrades Starter -> Premium Ecommerce (Shopify, Walmart, Amazon) Amazon: Anuhya Walmart & Amazon: ? | 2023-01-11 | Sivanepalli N V S, Anuhya |  |  | Villaverde, Alfredo |  | 4 |  |  | 139275223 | 0 | 0 | 134.35 | New Business
J880063 |  |  |  | RCBA Nutraceuticals LLC ¦ Implementation Service - Fixed Bid | Villa, Myr Angeli | In Progress | 2023-04-21 | Original | 283 | Standalone | 8/26/22 - RMO JM - #NSC #STANDALONE - Scope: 1xPremiumPlus Shopify Job email: messages.NLCORP.533100467.6ebc8a29cd@nlcorp.email.netsuite.com 5/15/23 MV: UAT is still in progress. Requested for SOW extension to extend the engagement. 4/17/23 MV: UAT is in progress. 4/7/23 MV: UAT is in progress. 3/31/23: MV: Implementation is complete. UAT will start the week after due to customer availability. 3/28/23 AVV: Moving schedule status to green, as we're now making progress 3/27/23 MV: Kick-Off call is set (3/28) 3/20/23 MV: Changed the status to in progress as the customer is ready to start the project. Sent an overage request for PM since the hours is not included in the PC. AVV 02 13 2023: Customer has been solely focused on their ERP implementation. We estimate that the project will be able to be resumed in the first two weeks of March. SOW Extension signed. Please refer to email communications for context. Will be assigning a new PM when the customer is ready to engage. | 2023-03-28 | N V, Akhilesh |  |  | Villaverde, Alfredo |  | 5.5 |  | 2023-04-21 | 133139482 | 0 | 0 | 58.35 | AMO
J899567 |  |  |  | International Hair and Beauty Systems ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 155 | Standalone | 1/3/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon and Shopify messages.NLCORP.536994161.91e27e25d2@nlcorp.email.netsuite.com 1/3/23 AF -sent welcome |  |  |  |  | Villaverde, Alfredo |  | -3.75 |  |  | 140525940 |  |  |  | AMO
J896959 |  |  |  | Surplus R.D. inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 171 | Standalone | 12/15/22 - RMO JM - #NSC #STANDALONE ¦ Prem Magento #delayed messages.NLCORP.535127015.58b89d040d@nlcorp.email.netsuite.com 5/16/2023 AVV - Customer re-assessing if NSC is a fit and working with Solution Architect. AMO will provide updates. Will follow-up in Mid-June. 5/15/2023 AVV - Requested assistance from AMO to get a response from the customer, as we haven't gotten any thus far. 5/5/2023 AVV - Second follow-up sent to the customer who remains unresponsive. 3/13/2023 AVV - DL followed up with the customer due to unresponsiveness (Copied AMO) 12/15/22 (MC) - approved 5 hour overage for PM hours 12/15/22 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 14 |  |  | 139414511 |  |  |  | New Business
J902515 |  |  |  | Universal Environmental Products Inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress | 2023-03-17 | Actual | 122 | Standalone | 1/31/23 - RMO JM - #NSC #STANDALONE ¦ Prem+ Amazon and Shopify and Amazon add on messages.NLCORP.540387330.89452dec9c@nlcorp.email.netsuite.com 3/17/23 GD - Sent UAT 2/21/23 GD - kickoff 2/1/23 AF - sent welcome | 2023-02-21 |  |  |  | Villaverde, Alfredo | 2023-03-17 | 2.25 |  |  | 142211230 | 24 | 24 | 93.35 | AMO
J909651 |  |  |  | Quicksilver Scientific, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 86 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: quicksilverscientific ¦SCOPE: 2 Premium Plus Ecommerce (WooCommerce) ¦ JOB EMAIL : messages.NLCORP.545520187.5a23be5621@nlcorp.email.netsuite.com 5/8/23 MKP: configuration complete, sent UAT template 4/27/2023 MK - Overage of 6 hours applied for Project management. Approved by VL Meenakshi Krishnan. Job Record has been updated. 3/16/23 MKP: welcome sent 3/10/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2x Prem Plus WooCommerce | 2023-04-18 | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 7 |  |  | 144358077 | 0 | 0 | 37.35 | AMO
J915781 |  |  |  | Hockeystickman Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 38 | Standalone | 4/24/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2x Prem Plus Shopify messages.NLCORP.550048670.d63b541359@nlcorp.email.netsuite.com 4/24/23 AF - sent welcome |  | Sivanepalli N V S, Anuhya |  |  | Villaverde, Alfredo |  | 17 |  |  | 147431222 |  |  |  | AMO
J910657 |  |  |  | Icy Strait Seafood ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 72 | Standalone | #NSC #UTOPIA-SOW ¦DISC: ¦SCOPE: 1 Premium Plus Ecommerce (Shopify) ¦JOB EMAIL: messages.NLCORP.545655592.b87b04bed9@nlcorp.email.netsuite.com 4/21/23 MKP: kickoff call 20-Mar-2023 (MC) Overage approved 3/17/23 MKP: welcome email 3/17/23 - RMO JM - (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify | 2023-04-21 | Buenavista, Josiah Frances |  |  | Villaverde, Alfredo |  | 1.25 |  |  | 145132125 | 0 | 0 | 34.35 | AMO
J896893 |  | #POS-NSPOS-PHASE | #POS-NSPOS-PHASE | Velocita, Inc. dba Zinrelo ¦ Implementation Service - Fixed Bid | Varsallona, Jeremiah J | In Progress | 2023-05-31 | Revised | 173 | Standalone | #POS-NSPOS-PHASE2 messages.NLCORP.534886011.eb1318eef8@nlcorp.email.netsuite.com 4/21 JV: Loyalty is in UAT phase with customer. Some issues reported which Mat will be addressing. 3/10 JV: Attended Weekly call to track Loyalty Solution Development. 2/7 JV: Defined Requirements. Scoped a new job for PS to perform actual customizations for Zinrelo which will be implemented for Olsen NSPOS. 12/16 JV: Held SOW and project scope review scope call. Zinrelo and Olsen reps joined. | 2022-12-22 | Varsallona, Jeremiah J |  |  | Bazzani, Emiliano |  | 4 | 2023-05-31 | 2023-11-30 | 139355482 | 0 | 0 | 154.35 | AMO
J905093 |  |  |  | Ultimate Mats, LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 108 | Standalone | 2/14/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Starter WooCommerce messages.NLCORP.542689632.68c96711da@nlcorp.email.netsuite.com 21-Feb-2023 (MC) overage approved 2/21/23 AF - sent welcome |  | ALURI, DINESH |  |  | Villaverde, Alfredo |  | 9 |  |  | 142976909 |  |  |  | AMO
J877865 |  | #POS-NSPOS-ONLY | #POS-NSPOS-ONLY | San Antonio Masonry & Tool Supply, Inc. ¦ Implementation Service - Fixed Bid | Cheung, Michelle | In Progress | 2023-08-01 | Revised | 301 | Joint | #POS-NSPOS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 5/12/2023 MC: Discussed with client yesterday and client confirmed they no longer need NSPOS. Smart Count demo is being scheduled by AMO, target go-live delayed to 8/1/2023. 5/2/2023 MC: discussed with client on NSPOS customizations. Regrouping internally on next steps. 4/18/2023: MZ: will be discussing landed cost topic tomorrow 4/19, SAMTS to confirm Versapay contracts status, SAMTS would like to revisit NSPOS as a part of the implementation, Consultants working on cash sales customization. Still working towards 6/1 go-live 3/27/2023 MC: Client would like to push target go-live to 6/1/2023, speaking with client to see if we can have a 2-phase go-live approach to not delay Go-Live so much. 3/6/2023 MC: NS team working on outstanding questions clients has surrounding their Items records. Internal session tomorrow to work through these. 3/1/2023 MC: NS team working with client on a workflow to accomplish their business needs. Waiting for client written approval to repurpose NSPOS hours. 2/15/2023 MC: Client determined NSPOS is not needed. Working with Sales and AMO on determining next steps. PWT2 sessions continue. 2/1/2023 MC: PWT2 sessions complete, except for O2C. Still determining if NSPOS is needed as what SAMTS wants may be accomplishable in native NS. 1/18/2023 MC: PWT2 sessions to continue, determining if NSPOS is needed. 1/4/2023 MC: PWT2 sessions in progress. NSPOS team working on customizations as required by client. 12/21/2022 KA: CO for NSPOS customization staffed J898393 12/16/2022 MC: Client executed CO for NSPOS customization. PWT1 scheduled to complete week of 12/19, and NS POS customizations developer work to start and target to showcase to client in mid to late January. Client has expressed interest for On-Site so working with AMO to confirm next steps for CO. 12/7/2022 MC: Final stages of completing CO for NSPOS customizations. PWT1 scheduled to start week of 12/12. 11/23/2022 MC: NS team working internally on creating a CO for NSPOS for gaps identified, in order to create a customization to achieve what the client is looking to achieve in NS. 11/1/2022 MC: NS team complete with Personalization Sessions, however, O2C and NSPOS had gaps. NS team working with client and internal teams to determine next steps. 10/19/2022 MC: Personalization Sessions ongoing. No red flags or out of scope items thus far. Configs in process, and COA upload in process. Personalization Sessions target to complete by 10/31. PWT1 target to begin 11/3. 10/4/2022 MC: GSS and DMSS scheduled for this week. Personalization Sessions to begin next week. 09/19/2022 MC: KO call scheduled for 9/26, GSS and DMSS scheduled on 9/29 and 10/6 respectively. Client's NS Login Info link expired, waiting for AMO to resend login info email. 09/06/2022 MC: PM KT with Karyn Stewart complete. Waiting for client to revert on Intro call & KO date. KStewart 2022/08/04 - Initial Job setup KStewart 2022/08/15 - Go-live is March 1. Kickoff mid/late September | 2022-09-26 | Gibson, Donald H | Bazzani, Emiliano |  | Astaphan, Karli P |  | 185.5 | 2023-08-01 | 2023-04-03 | 132180827 | 0 | 0 | 241.35 | New Business
J872445 |  |  |  | Chasing Our Tails, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | Delayed - Per Customer |  |  | 359 | Standalone | #NSC ¦ DISC: chasingourtails ¦ SCOPE: 2 Premium eCommerce (Amazon, Shopify) ¦ JOB EMAIL: messages.NLCORP.516060854.cfe20d2dd1@nlcorp.email.netsuite.com 5/16/2023 AVV: Customer provided re-engagement ETA around August due to bandwidth constraints to tackle their ERP deliverables (single stakeholder working on their ERP project). Set follow-up date to 8/1. 5/15/23 MKP: follow up 4/26/23 MKP: follow up and SOW extension 3/23/2023 AVV: Per alignment with AMO, will be setting project on hold and will follow up on the first week of May. 3/16/23 MKP: follow up with AMO 3/9/2023 AVV - New AMO on account who is now reaching out to the customer. 3/1/23 AVV - Reached out to AMO, as the customer is unresponsive for a few months now. When the job was active, the customer was to confirm the start of their ERP implementation with a partner. 7/25/22 MKP: welcome email 6/14/22 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) |  | Abella, Mary Jane |  |  | Villaverde, Alfredo |  | 14.5 |  |  | 128757861 |  |  |  | New Business
J914417 |  |  |  | Filling Machines & Systems, Inc ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 51 | Standalone | 4/10/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify |  |  |  |  | Villaverde, Alfredo |  | 6.75 |  |  | 146407494 |  |  |  | AMO
J905101 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Seiko Watch of America LLC ¦ Implementation Service - Fixed Bid | Kayastha, Piyush D | In Progress |  |  | 108 | Standalone | #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) |  | Zenisek, Nicholas J |  | Bazzani, Emiliano | Bazzani, Emiliano |  | 52.75 |  |  | 142979539 |  |  |  | AMO
J915127 |  |  |  | UBOXES LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 44 | Standalone | # ¦ DISC: movenstoredirect ¦ SCOPE: 1 Premium Plus Ecommerce (Walmart) ¦ JOB EMAIL: messages.NLCORP.549556084.76ce189b50@nlcorp.email.netsuite.com 4/20/23 MKP: welcome email 4/19/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Wal-Mart 25-Apr-2023 (MC) overage approved |  | Klein, Adam D |  |  | Villaverde, Alfredo |  | 6 |  |  | 146977335 |  |  |  | AMO
J923511 |  |  |  | Driftwood Dairy, Inc. ¦ Change Order_001 | Joshi, Aarti | Assigned |  |  | 3 | Standalone |  |  | Joshi, Aarti |  |  | Bazzani, Emiliano |  | 38 |  |  | 149544596 |  |  |  | AMO
J916227 |  |  |  | Gaudet's Door Inc ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 35 | Standalone | 4/27/23 - RMO JM - #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon messages.NLCORP.550495198.059b151d3c@nlcorp.email.netsuite.com 4/27/23 AF - Sent welcome |  |  |  |  | Villaverde, Alfredo |  | 7 |  |  | 147578765 |  |  |  | New Business
J892577 |  |  |  | Stile Products, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 191 | Standalone | 11/25/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 1 x NS Premium eCommerce Connector – Shopify JOB_EMAIL: messages.NLCORP.533420075.64324109dc@nlcorp.email.netsuite.com SCOPE: migrate from bundle to SuiteApp |  | Sivanepalli N V S, Anuhya |  |  | Villaverde, Alfredo |  | 5.75 |  |  | 138233774 |  |  |  | AMO
J855680 |  |  |  | Comfort Auto LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 454 | Standalone | #NSC #STANDALONE ¦ DISC: ¦ SCOPE: 3 Premium Plus eCommerce (2 eBay, 1 Amazon) ¦ JOB EMAIL: messages.NLCORP.495241804.b887fd0598@nlcorp.email.netsuite.com 5/1/2023 AVV: Customer has been unresponsive. Requesting assistance from AMO to get ETA from customer before we extend this SOW for the third time. 4/18/2023 AVV: Followed up with customer again to request ETA on when they'll be ready to engage 2/28/23 AVV: Setting customer relationship status to yellow due to the number of various work streams the customer is involved in which slows down their ability to get ready with their prerequisites. 3/4/22 MKP: welcome email |  |  |  |  | Villaverde, Alfredo |  | 51.25 |  |  | 121823984 |  |  |  | AMO
J910452 |  |  |  | Kokopelli Outdoor, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 77 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: kokopellioutdoorinc ¦ SCOPE: 1 Premium Plus Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.545888407.d2304fac57@nlcorp.email.netsuite.com 30-Mar-2023 (MC) overage approved 3/20/23 MKP: welcome email 3/20/23 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus Shopify |  | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 5 |  |  | 144897086 |  |  |  | AMO
J911709 |  |  |  | Distribution Enterprises, Inc. dba Graphic Marking Systems ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 65 | Standalone | 3/30 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium eCommerce Connector Magento2 messages.NLCORP.547171190.839cf76c51@nlcorp.email.netsuite.com 3/30/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 14.5 |  |  | 145695484 |  |  |  | AMO
J900425 |  |  |  | SVHB Marketing, LLC dba Horsepower Brands ¦ Consulting Time | Farmer, Andrew | Monitoring - Post Go-Live | 2023-05-04 | Actual | 153 | Standalone | 1/3/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus Shopify Please reference job J898857 for executive updates and the following email for communications: messages.NLCORP.537005970.9108350fbc@nlcorp.email.netsuite.com 5/4/23 AF - client live 3/9/23 - TK - Approved overage (5h) |  | Pitla, Venkatesh |  |  | Villaverde, Alfredo | 2023-05-04 | 6.5 |  |  | 140764802 | 0 | 0 |  | AMO
J914607 |  |  |  | Cardinal Cycling Group ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 54 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: cardinalcyclinggroup ¦ SCOPE: 3 Premium Plus Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.548146662.c2354830c1@nlcorp.email.netsuite.com 4/17/23 MKP: introduction to consultant 4/7/23 MKP: welcome sent 4/7/23 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 3x Prem Plus Shopify | 2023-04-18 | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 7 |  |  | 146474559 | 0 | 0 | 37.35 | AMO
J910108 |  |  |  | Wintis Corp ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 83 | Standalone | #NSC #UTOPIA-SOW #DELAYED ¦ DISC: wintiscorp ¦ SCOPE: 1 Premium Plus Ecommerce (Amazon), 2 Premium Ecommerce (eBay, Shopify) ¦ NOTES: replacing Celigo with NSC ¦ JOB EMAIL: messages.NLCORP.545520535.bdddf37dc2@nlcorp.email.netsuite.com 5/12/23 MKP: customer not ready to proceed with eBay and Shopify until mid-June 4/6/23 MKP: starting with Amazon (priority) and eBay, Shopify not ready yet 3/16/23 MKP: welcome sent 3/14/23 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ PST ¦ Prem Plus Amazon, Prem eBay, Prem Shopify |  | Archer, Nathaniel |  |  | Villaverde, Alfredo |  | 10.75 |  |  | 144673025 |  |  |  | AMO
J896943 |  |  |  | Alfateers Service Center Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 170 | Standalone | #NSC #STANDALONE ¦ DISC: alfateersservicecenterinc ¦ SCOPE: 2 Premium Add Ons (Inventory Adjustment Full Flow, Inbound Shipping Receipt Only) ¦ JOB EMAIL: messages.NLCORP.535551300.b9a799dcab@nlcorp.email.netsuite.com 3/2/23 GD: There are issues with these syncs b/c the client uses custom record aliases. We've been trying to figure out workarounds to make their item configuration in NS compatible with the syncs. 01/04/23 MP: configurations done offline, currently testing 12/22/22 MP: prereqs done 12/20/22 MP: welcome email sent 12/15/22 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 1 x NS Premium Connector Add-on Inventory Adjustment Full Flow - Amazon 1 x NS Premium Connector Add-on Seller Inbound Shipping Receipts Only - Amazon | 2022-12-22 |  |  |  | Villaverde, Alfredo |  | 5.25 |  |  | 139405480 | 0 | 0 | 154.35 | AMO
J914309 |  | #POS-SCIS-PLUSCUSTOMIZATION | #POS-SCIS-PLUSCUSTOMIZATION | Power Company Inc. (DBA Battery Warehouse) ¦ Implementation Service - Fixed Bid | Zenisek, Nicholas J | In Progress |  |  | 55 | Standalone | #POS-SCIS-PLUSCUSTOMIZATION |  | Zenisek, Nicholas J |  | Bazzani, Emiliano | Bazzani, Emiliano |  | 169 |  |  | 146306951 |  |  |  | New Business
J907194 |  |  |  | Wishon Evergreens, LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 92 | Standalone | 3/1/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 1 x NS Standard eCommerce Connector - Shopify messages.NLCORP.544004985.eb2c2d845c@nlcorp.email.netsuite.com 5/22/23 AF - sent client follow up on status, client had stated they need time to review prereqs 4/25/23 AF - sent folow up, no response 3/3/23 AF - sent welcome |  | ALURI, DINESH |  |  | Villaverde, Alfredo |  | 12.5 |  |  | 144008350 |  |  |  | AMO
J920192 |  |  |  | IncStores LLC ¦ Consulting Hours | Rodrigues, Jo Ann | In Progress |  |  | 16 | Standalone | 5/19/23-JR- Welcome Letter Sent 5/17/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus Amazon/Ebay/Magento2 and Walmart |  |  |  |  | Villaverde, Alfredo |  | 40 |  |  | 148753222 |  |  |  | AMO
J919254 |  |  |  | Nortek Inc. : Nice North America LLC ¦ Implementation Service - Fixed Bid | Rodrigues, Jo Ann | In Progress |  |  | 23 | Standalone | 5/15/23-JR-Adjusted hours 16-May-2023 (MC) overage approved 5/15/23- JAR- Welcome Letter Sent 5/12/23-JAR-JOB email set up, overage request 5/9/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦Premium Plus Shopify |  | Buenavista, Josiah Frances |  |  | Villaverde, Alfredo |  | 14.5 |  |  | 148293496 |  |  |  | AMO
J883318 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Grubmarket, Inc. ¦ Implementation Service - Fixed Bid | Varsallona, Jeremiah J | In Progress | 2023-03-01 | Revised | 259 | Standalone | #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 4/21 JV - Waiting for customer to confirm if they are live with SCIS now. No response yet. 4/14 JV - Users tested SCIS today and had 2 issues related to product limitations. I provided workarounds via email. 3/10 JV - Customer requested major edits to the receipt templates. SCIS has been deployed to production and ready for go live. 2/10 JV- UAT completed. Waiting for change approval to migrate settings from Sandbox to Production. 10/18 JV - Sandbox Sandbox refresh completed 10/13 JV - Project Status call 10/3 JV - Personalization Session completed 9/26 JV - Project Kick off call completed Tag job record: messages.NLCORP.524854753.2c1c779034@nlcorp.email.netsuite.com |  | Varsallona, Jeremiah J | Bazzani, Emiliano |  | Bazzani, Emiliano |  | 6 | 2023-03-01 | 2022-12-01 | 133950297 |  |  |  | AMO
J921471 |  |  |  | Ranger Industries Inc - Professional Services : Activation - SuiteSuccess for Comm | Joshi, Aarti | Assigned |  |  | 13 | Standalone |  |  | Joshi, Aarti |  |  | Cristobal, Kevin S |  | 79 |  |  | 149130264 |  |  |  | AMO
J920682 |  |  |  | Healthforce Superfoods, Inc. ¦ Implementation Service - Fixed Bid | Rodrigues, Jo Ann | In Progress |  |  | 14 | Standalone | 5/19/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium WooCommerce 25-May-2023 (MC) overage approved 5/24/23-JR- Prerequisites completed, overage hours sent, Welcome letter sent, request FC. |  |  |  |  | Villaverde, Alfredo |  | 16 |  |  | 148890625 |  |  |  | AMO
J888452 |  |  |  | Newhaven Display International Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 218 | Standalone | 10/28/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) 1 x NS Standard eCommerce Connector - BigCommerce 10/31/22 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 9.5 |  |  | 136634232 |  |  |  | AMO
J904989 |  |  |  | Velocita, Inc. dba Zinrelo ¦ NetSuite Time & Material - NEW | Varsallona, Jeremiah J | In Progress | 2023-03-31 | Original | 113 | Standalone | 5/8 JV - UAT completed. 2 outstanding issues before we can schedule go live. 2/15 JV - Mat determined next steps. Would like to have UAT by 3/15 for 3/31 go live. |  | Burnett, Mathew |  |  | Bazzani, Emiliano |  | 20 |  | 2023-03-31 | 142910825 |  |  |  | AMO
J903269 |  |  |  | OuterFactor Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 109 | Standalone | 2/3/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Starter Amazon messages.NLCORP.540685719.7648f24381@nlcorp.email.netsuite.com 2/3/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | -1 |  |  | 142435999 |  |  |  | AMO
J915242 |  |  |  | Ameico ¦ Consulting Time | Preedanon, Melinda | Monitoring - Post Go-Live |  |  | 49 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ameico ¦ SCOPE: ¦JOB EMAIL: 5/15/23 MKP: closing email 4/17/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Point of Sale Connector Shopify 18-Apr-2023 (MC) - overage approved |  | Sivanepalli N V S, Anuhya |  |  | Villaverde, Alfredo |  | 7.25 |  |  | 147043966 |  |  |  | AMO
J910556 |  |  |  | Milano Collection ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 76 | Standalone | #NSC #STANDALONE Scope: 1 x Prem eComm (Shopify) + 1xPremiumPOS(Shopify) + 4 Premium POS addl locations Job email: messages.NLCORP.545205003.550c34f48a@nlcorp.email.netsuite.com 14-Mar-2023 (MC) overage approved 3/14/23 AF - sent welcome 3/14/23 AVV: This job replaces the scope for two previously closed jobs. Previous communications with this customer tracked on job J873589 |  | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 20.5 |  |  | 145064579 |  |  |  | AMO
J905945 |  |  |  | Circufiber Inc ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 99 | Standalone | 2/22/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem plus Amazon messages.NLCORP.543379899.ac347a6985@nlcorp.email.netsuite.com 2/27/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 12 |  |  | 143481022 |  |  |  | New Business
J800941 |  |  |  | Shoes For Crews, LLC.¦Implementation Service - Fixed Bid | Loh, Chileng | In Progress | 2022-07-11 | Actual | 936 | Joint | 5/19 Subsidy discussion concluded. SDD will be published on 5/22 and signoff is expected on 5/23. Faraon will have 1-1 with Dan about his ask to record walkthrough sessions to be held in June. API advisory started on 5/16 and will be completed in the next 2 weeks, 6/2 or latest 6/9. 5/12 cloh: updated status to green based on 5/10 steering committee discussion. SDD prep and dev are in full swing. Planning calls taking place with SFC PM to incorporate code freeze, testing preparation, go-live/cutover planning, training planning etc. Faraon coordinating time for future SC meetings. 5/3 - New CO has been signed. Project has been handed off to Chileng 4/21 - currently still working on the change order and finalizing last open items (voucher) while continuing to provide support 3/31 - currently in discussion with the client on change order and out of scope hours as well as integration API requirements. 3/17 - met with the client this week to present Change Order. They did not agree with the cost and have asked to review TS work further. Next call is scheduled for the following week (3/22). 3/1 - this week scheduled a call to review new scope with Dan from S4C team to discuss CO options. 2/16/23 YH: This week final version of open TS items have been provided for scoping. Solutioning working on 2 new SOWs in order to proceed with the project. 02/08/23 MK - Overage of 5 hours applied for job balancing and task closure. Approved by Vertical Lead Meenakshi Krishnan. Job record has been updated. 2/6/2023 MK - Overage of 1000.75 approved to level out over-billed tasks and lack of Project oversight for several months. Plan to negotiate a new PS engagement to continue to support their implementation needs. Overage approved by Meenakshi Krishnan. Job Record has been updated. 2/28/2022 Scott Williams VL - Overage of 600 additional hours for ERP has been approved by Vertical Lead Scott Williams. The job has been updated. 01/31/22 (JP) - Go Live moved to March 1 due to business team request for additional time for financial reconcilation 01/03/22 (JP) - Go Live moved to target Feb 1 due to business team request 10/15/21 (JP) - Preparation for walkthrough #2 in process for week of Oct 25th and Nov 1st #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 08/18/21 - VL Scott Williams - Removing Overage hours that were declared early since they will now need to be used to complete the job. 06/30 (JP) - US project restarted, refresher sessions in process along with data migration and integration partner on-boarding. 05.24 (JP) - US project to restart, customer team has provided internal communication to their team. 4/19 - Subsidy design is behind schedule. Original date was 3/31 for design completion. Revising to 4/30. 1/31 - working on customizations with TS; just started detailed integration design. Beginning CRP's this week 12/30 - Completed S&P Sessions. Conducting several follow up sessions to clarify issues for configuration and customizations Shoes for Crews US job | 2020-03-31 | Foster, Sheriden | Bazzani, Emiliano |  | Lopez, Faraon | 2022-07-11 | 0 | 2023-07-01 | 2022-01-03 | 84339987 | 832 | 832 | 1150.35 | AMO
J913391 |  |  |  | Ironmill Fasteners and Hardware ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 56 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ironmillfastenersandhardware ¦ SCOPE: 1 Premium Ecommerce (Amazon) ¦ JOB EMAIL: messages.NLCORP.548147587.a2f1a31fd6@nlcorp.email.netsuite.com 4/7/23 MKP: welcome email 4/7/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Amazon |  |  |  |  | Villaverde, Alfredo |  | 9.25 |  |  | 146212418 |  |  |  | AMO
J903214 |  |  |  | Jay Squared LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | Monitoring - Post Go-Live | 2023-03-08 | Actual | 118 | Standalone | 2/3/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify and Amazon messages.NLCORP.540682205.f1c436d26d@nlcorp.email.netsuite.com 2/3/23 AF - sent welcome 2/9/23 GD - kickoff call 3/9/23 GD - Provided UAT and Go Live docs | 2023-02-09 |  |  |  | Villaverde, Alfredo | 2023-03-08 | -2.75 |  |  | 142412349 | 27 | 27 | 105.35 | AMO
J901259 |  |  |  | Joe Brands, LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 136 | Standalone | 1/17/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Shipstation JOB_EMAIL: messages.NLCORP.538632637.9d9e6db0e7@nlcorp.email.netsuite.com SCOPE: 1 Premium Logistics (ShipStation) | 2023-02-07 | Buenavista, Josiah Frances |  |  | Villaverde, Alfredo |  | 2.75 |  |  | 141347257 | 0 | 0 | 107.35 | AMO
J907212 |  |  |  | Cygnet Online, LLC ¦ Consulting Time | Farmer, Andrew | In Progress | 2023-03-15 | Actual | 83 | Standalone | 3/2/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Shipstation Using JR email from J874738: messages.NLCORP.544002744.ed589dbac3@nlcorp.email.netsuite.com 10-Mar-2023 (MC) overage approved 3/3/23 AF - sent welcome | 2023-03-15 |  |  |  | Villaverde, Alfredo | 2023-03-15 | 7.25 |  |  | 144013174 | 0 | 0 | 71.35 | AMO
J916238 |  |  |  | The Solar Biz, Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 35 | Standalone | 4/26/23 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ CAR for Solar Biz 17-May-2023 (overage approved) 4/26/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 1.25 |  |  | 147579792 |  |  |  | AMO
J903271 |  |  |  | Boat Bling, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 97 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: boatblinginc ¦ SCOPE: 1 Standard Ecommerce (Shopify) ¦ JOB_EMAIL: messages.NLCORP.540897904.55032c0835@nlcorp.email.netsuite.com 4/18/23 TK - Approved overage (+8) 4/10/23 MKP: troubleshooting refund sync issues 3/22/23 TK - Approved overage (6h) 3/22/23 MKP: kickoff call 3/9/23 MKP: welcome email 2/3/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Standard Shopify | 2023-03-22 |  |  |  | Villaverde, Alfredo |  | 2.25 |  |  | 142436703 | 0 | 0 | 64.35 | AMO
J857514 |  |  |  | Texas Gas Utility Services, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 444 | Standalone | #NSC #STANDALONE ¦ DISC: ¦ SCOPE: 1 Premium Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.498095411.9c85a811bc@nlcorp.email.netsuite.com 5/2/2023 AVV: Followed up with customer and looped AMO. Requested the customer's commitment or ETA for engagement before we consider extending the job again next month (extended this job twice already). 4/19/23 MP: follow up 1/5/23 MP: follow up 12/2/22 MP: status meeting; still not able to complete prerequisites 11/23/22 MP: follow up, starting early December 10/26/22 MP: follow up 9/7/22 MP: not ready to start yet; targeting late Oct/early Nov |  | Dunn, Geoffrey |  |  | Villaverde, Alfredo |  | 7 |  |  | 122432989 |  |  |  | AMO
J920483 |  |  |  | GSM DEPOT ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 14 | Standalone | 5/16/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ NSC Scope: 1. Netsuite Premium AddOn Seller Inbound Shipping Full Flow Connector Amazon 2. Netsuite Premium Plus eCommerce Connector Amazon 3. Netsuite Premium eCommerce Connector Shopify |  |  |  |  | Villaverde, Alfredo |  | 30 |  |  | 148865974 |  |  |  | AMO
J914937 |  |  |  | L'Chef LLC ¦ Consulting Time | Preedanon, Melinda | In Progress | 2023-05-30 | Original | 48 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: lchef ¦ SCOPE: 2 Premium Ecommerce (Amazon, Shopify) ¦ JOB EMAIL: messages.NLCORP.549355315.4da90fac32@nlcorp.email.netsuite.com 5/23/23 MKP: configuration complete 5/10/23 MKP: kickoff call 5/2/23 MKP: resource request 4/18/23 MKP: welcome sent 4/17/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Amazon and Prem Shopify | 2023-05-10 | Klein, Adam D |  |  | Villaverde, Alfredo |  | 11 |  | 2023-05-30 | 146886764 | 0 | 0 | 15.35 | AMO
J916799 |  |  |  | ZPacks Corp ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 31 | Standalone | 4/28/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify messages.NLCORP.550956014.64344141ba@nlcorp.email.netsuite.com 5/1/23 AF - sent welcome |  | ALURI, DINESH |  |  | Villaverde, Alfredo |  | 5 |  |  | 147863814 |  |  |  | AMO
J916611 |  |  |  | MFASCO ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 31 | Standalone | 5/1/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Amazon and Prem Shipstation messages.NLCORP.551240511.be2d59aa0f@nlcorp.email.netsuite.com 5/3/23 AF - sent welcome |  | Jakke, Goutham |  |  | Villaverde, Alfredo |  | 19.5 |  |  | 147842077 |  |  |  | AMO
J871204 |  |  |  | Right Stuf, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 363 | Standalone | 6/10/2022 - RMO JM - #NSC #STANDALONE 3/28/23 (MC) Overage approved 1/23/23 (MC) Overage approved JOB_EMAIL: messages.NLCORP.514143327.26c00f4dcb@nlcorp.email.netsuite.com SCOPE: 4 Premium Plus eCommerce (2 Amazon (US & Japan), 1 Shopify, 1 Magento) | 2022-07-11 |  |  |  | Villaverde, Alfredo |  | 0 |  |  | 128618196 | 0 | 0 | 318.35 | AMO
J863235 |  |  |  | Big&J Industries, LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 395 | Standalone | #NSC #STANDALONE ¦ DISC: bigjindustries ¦ SCOPE: 1 Standard eCommerce (Amazon) ¦ JOB EMAIL: messages.NLCORP.506498305.c62903e287@nlcorp.email.netsuite.com 5/19/23 MKP: customer needs to grant access to Goutham and then ready for kickoff call 5/5/23 MKP: customer willing to finish project but communicated they may cancel in the future 5/2/2023 AVV: Unresponsive customer. Followed with AMO to request assistance before putting this project in delayed status. 04/11/2023 AVV: Sent a follow-up note to the customer and looped in AMO, as customer has not given visibility over when they intend to engage. As we have extended this engagement multiple times, trying to get firm commitment from the customer before we consider extending it yet again in August. 4/11/2023 AVV: Customer has not moved forward with the prerequisites and were evaluating their use of Amazon. |  | Jakke, Goutham |  |  | Villaverde, Alfredo |  | 7.25 |  |  | 126235373 |  |  |  | AMO
J848512 |  | #POS-NSPOS-PLUSCUSTOMIZATION | #POS-NSPOS-PLUSCUSTOMIZATION | Goodwill Industries of Sacramento Valley & North Implementation Service - Fixed Bid | Jonathan, Nicholas | Monitoring - Post Go-Live | 2022-11-02 | Actual | 519 | Joint | #POS-NSPOS-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) NJ 5/17: ERP scope complete; Brant Ueckert PM of NSPB NJ 5/3: ERP scope complete. NSPOS to provide any updates separately. NJ 3/30: ERP scope complete. NJ 3/15: ERP scope complete 2/21 NJ: On ERP side, customer post go live support continues. CO 02 (J892567) complete and another CO is in process to extend ERP PGLS through 3/31. This sits with AMO currently. 02152023 BWU: Customer is live and we are working post go live Case and Defect items for the customer. We have provided the change order work and customer is in final UAT for those. We are also in development for a new SOW T&M for reporting and custom NSPOS items requested from the customer. NJ 1/5: Post Go Live Support activities continue. The change order for extended hours has been put in place. Customer is rapidly consuming budget due to systemic challenges with certain data imports (i.e., subsidiary imports). Budget risk is 10-12 hours, for which we will plan to leverage contingency. Risk of an overage is present but small. Customer satisfaction is high, however their status as a future Net Promoter is unclear. NJ 12/13: Post Go Live Support activities continue. Change Order for extended PGLS provided to customer today (per AMO). This extension is intended to take us through 1/31/23. However, customer is still burning hotter than sustainable with respect to PGLS budget. Conversation will be had with customer around leveraging ACS team (which is active) for appropriate tasks. Customer is expected to be referenceable. 12072022 BWU: NSPOS go live continues. Store Roll out to continue through December. We are also performing break fix actions for customization and impacting stores in different states. NJ 11/3: Go Live achieved and successful! There was a system outage in the customer's account on 11/1, so Go Live was formally achieved on 11/2. The customer continues to be pleased with the ERP team's efforts and customer service, and is inquiring on possible extensions of PGLS (via Change Order). They do have ACS (and their ACS team has been introduced), so we are navigating next steps based on what's best for the customer and for PS. A Net Promoter score is expected, but we will continue to deliver value through PGLS. NJ 9/27: Customer still working through UAT and is rather delayed. Soft Go Live with a non-NSPOS subsidiary (community link) planned for 10/1. Customer knows they'll need to enter dual transactions for October. Full Go Live still planned for 11/1. Data Migration is on track. NSPOS is a little behind schedule and is prohibiting customer from finishing UAT related to intake, but the team expects to be complete soon. NJ 8/16: Customer wants to push Go Live to 11/1 to focus on UAT and quarter end close. Some positive traction on the NSPOS side, with the customer feeling more confident in NSPOS solution as opposed to looking for alternate providers (i.e. Supro). Data Migration on a terrific clip thanks to great work from Hiba and Estalynn on the NetSuite side, and good support from Angela on customer side. Peter August's MICR line config is still a work in progress, after all, with small fixes and tweaks requested by the customer this week. Budget overall is on track, but we will need to be diligent with our budgeting over the final 2 months of the extended timeline. Customer relationship remains great. NJ 8/4: Some challenges faced by the customer around NSPOS (specifically, finding a 3rd party provider for goods intake), coupled with the customer's desire to roll out NetSuite at sub-location(s) before organization-wide Go Liver, are likely going to yield an adjustment to project schedule. The customer has requested a Go Live for Community Link on 10/1, with a full Goodwill Sacramento Go Live on 11/1. NetSuite team is still strategizing on this and will discern best / most recommendable approach. NSPOS may require a CO given additional integration requirements posed by the customer's new intake solution provider (Supro). NJ 7/13: UAT to begin Wednesday, 7/20, but might need to be delayed or de-prioritized given some needed walkthroughs / conversations around labor expense allocations, locations, and budget validation. Go Live target is now 9/1, at customer's request. Currently on track but without much more room to wiggle. Budget is in a good spot mostly due to underruns on the NSPOS side. NJ 6/21: PWT2 still underway, with some customer driven delays in finishing. Expect Go Live target to be 9/1/22. NJ 6/1: PWT2 begins tomorrow, 6/2. Customer is slightly behind on data migration, but has done an admirable job catching up on Fundamentals training. A new customer CFO started today, but has completed her training and will be ramped up quickly as part of UAT. NSPOS PWT2 began yesterday. UAT planning session held today. Go Live tentatively expected for 8/1. NJ 5/18: Process Walkthrough 1's to complete this week. Customer still has not finished Nonprofit fundamentals training. This has been brought up many times. NJ 4/13: Personalization complete. Process Walkthrough has needed to be rescheduled several times due to customer schedule complications, which has resulted in higher than anticipated PM budget burn. PWT1 scheduled to begin next week. Project plan has been formalized and shared with customer team, targeting an August 1 Go Live. NJ 3/28: Customer requested 2-week delay to go through FY end close. Personalization resumed end of last week, and will persist through the first week of April. Process Walkthrough I is scheduled throughout April. Project budget remains healthy, with no immediate concerns (though a project plan will not be defined until we complete Personalization). NJ 3/9: Personalization underway and going according to plan. Process Walkthroughs expected for early April. NJ 2/15: Project kickoff will be tomorrow, 2/16. The miss in including NSPOS verbiage on the SoW has been corrected for (with a $0 Change order prepared by Brant Ueckert & signature obtained by the customer on 2/14. We are ready to roll. NJ 2/2: SoW Review scheduled with customer for Tuesday, 2/8. Customer wants to be strategic with timing of Project Kickoff, mainly due to recovering from a recent data hack & the hiring of a new VP of Technology (whose first day is 2/7). I will reserve a time for kickoff this week & will verify with customer on Monday's SoW Review. Note: There was a miss in the original SoW, as NSPOS was not included in scope. However, the hours for NSPOS were factored into the BP & the job, so Brant Ueckert (NSPOS PM) is working to submit a $0 CO to update the SoW. This is ideally complete before the 2/8 meeting with the customer (so that I can speak to an accurate SoW), but I plan to hold the meeting either way. NJ 1/18: Intro call scheduled for 1/20/22. NSPOS was priced in PC but not included originally in-scope. A team with NSPOS experience has been provisioned, but we need an updated SoW to work from. NSPOS team completed store roll-out, and the project is largely in a state of success and it's been a pleasure working with the Goodwill team. | 2022-02-16 | Chakrabarty, Probaho | Bazzani, Emiliano |  | Nelson, Scott | 2022-11-02 | 11.5 | 2022-11-02 | 2022-09-01 | 117301210 | 259 | 259 | 463.35 | New Business
J897791 |  | #POS-NSPOS-PHASE | #POS-NSPOS-PHASE | Goodwill Industries of Southern California ¦ NetSuite Time & Material - NEW | Zenisek, Nicholas J | In Progress |  |  | 162 | Standalone | #POS-NSPOS-PHASE2 Email: messages.NLCORP.539241771.dc7c438825@nlcorp.email.netsuite.com 1.7 kick off meeting 1.24 provided mat details 1.30 mat to start work next week 2.24 Mat has deployed to sandbox. will update on return from PTO 4.11 completed extension end of month in march. received signed extension and updated EB 5-9-23: EWR Escalation submited, NSPOS server replication related issues prevented implementation team to deploy solution, PS not responsive due to other go lives/escalations, prioritized to provide updates by EOD | 2023-01-18 | Burnett, Mathew | Bazzani, Emiliano |  | Bazzani, Emiliano |  | 12 |  |  | 140000939 | 0 | 0 | 127.35 | AMO
J880291 |  |  |  | OE Wheel Distributors ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 280 | Standalone | 8/30 - RMO JM - #NSC #STANDALONE JOB_EMAIL: messages.NLCORP.523865682.f72e2c759e@nlcorp.email.netsuite.com SCOPE: 3 Premium Plus eCommerce (3 WooCommerce) 4/17/23 MP: follow up 1/16/23 MP: follow up 11/15/22 MP: SOW extension 10/26/22 MP: resource reassignment, working through errors, 2 WooCommerce connectors done, not ready for last connector 11/23/22 MP: not ready to continue with 3rd WooCommerce connector yet 1/5/23 MP: follow up | 2022-10-14 | Sivanepalli N V S, Anuhya |  |  | Villaverde, Alfredo |  | 3.5 |  |  | 133223958 | 0 | 0 | 223.35 | AMO
J856686 |  |  |  | Douglass Innovations, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 451 | Standalone | #NSC #STANDALONE ¦ DISRIM: dilabs ¦ SCOPE: 1 Premium Plus eCommerce (WooCommerce) ¦ JOB EMAIL: messages.NLCORP.497323695.fc6931b3d0@nlcorp.email.netsuite.com 3/30/23 MKP: SOW extension complete 3/17/23 MKP: follow up 9/22/22 MKP: kickoff call, on hold 3/15/22 MKP: welcome email | 2022-09-22 | Dunn, Geoffrey |  |  | Villaverde, Alfredo |  | 17.75 |  |  | 122009952 | 0 | 0 | 245.35 | New Business
J892518 |  |  |  | Elizabeth Grant International Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 191 | Standalone | 12.21.2022 MK : Overage of 5 hrs applied for Proj mgmt hours. Approved by Vertical Lead Meenakshi S Krishnan. Job has been updated 11/23/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 1 Shopify premium plus messages.NLCORP.532652451.8caee92ebb@nlcorp.email.netsuite.com 11/23/22 AF - sent welcome |  | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 4.5 |  |  | 138218012 |  |  |  | AMO
J915273 |  |  |  | University Co-operative Society, Inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 44 | Standalone | 4/19/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Shopify messages.NLCORP.550046911.3833fc6f82@nlcorp.email.netsuite.com 5/9/23 AF - client wants to self implement to test shopify trial before their actual shopify contract, discussing with AMO 4/24/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 11 |  |  | 147055269 |  |  |  | AMO
J918748 |  |  |  | Azurous, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 27 | Standalone | #NSC #STANDALONE ¦ DISC: cabeauinc ¦ SCOPE: 2 Premium Plus eCommerce (Amazon EU, Shopify EU), 5 Premium Add Ons (2 FBA Inv Adjustment CA, EU and 3 FBA Inbound Shipping US, CA, EU) + 20 hrs Reconfiguration of current set up ¦ JOB EMAIL: messages.NLCORP.551766319.b53b193525@nlcorp.email.netsuite.com 5/19/23 MKP: introduction to FC to start on re-configurations first 5/8/23 MKP: Sales KT, welcome email 5/5/23 - RMO JM - #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon/Shopify, 5x Premium Amazon FBA Inventory Adjustment |  |  |  |  | Villaverde, Alfredo |  | 72.25 |  |  | 148117487 |  |  |  | AMO
J899271 |  |  |  | Cimarron Firearms - Professional Services : Activation - SuiteSuccess for Commerce | Holt, Jonhenry | In Progress | 2023-07-21 | Original | 154 | Joint | 24 May- Customer still not wanting to engage with suitecommerce 16 MAY- Customer still is unresponsive despite multiple emails and face to face meetings. The customer is viewing the website as a second priority. They are however experiencing issues with firearm payment processors with Cybersource. 26 APR- Customer is non responsive for ecommerce. Will take steps to engage. 13APR- Team is set to begin personalization sessions for ecommerce. The team will complete by 14 April. 28MAR: Invite has been sent out. Customer to begin personalization sessions after introduction held last week. 15 Mar: Customer has requested to begin ecommerce after ERP implementation. Lead FC has reached out about beginning some preliminary work for the ecommerce implementation. 1MAR:1 MAR: Personalization sessions finishing. Ecommerce welcome letter has been sent out and lead ecommerce FC will be introduced to customer. 2/24/123- JRH- Welcome letter sent for Ecommerce. 22 FEB: Customer will be meeting with lead ecommerce FC to being implementation and personalization sessions. ERP personalization sessions have begin and now ecommerce will coincide. 8FEB:8FEB: Customer has had Kick off and GSS was supposed to take place (7FEB). Customer has lost/cannot find log in information and GSS and personalizatoins will have to be delayed. I had sent the customer a customer service number to retrieve the log in information Wednesday morning 8 FEB. Awaiting confirmation of log in info 24JAN- Customer had into meeting/SOW and is awaiting their license activation which begins 31JAN #SC-ONLY (tracking tag DO NOT DELETE) 1/5/23- JRH- Welcome Letter for ERP sent |  | Joshi, Aarti |  | Bazzani, Emiliano | Haines, Jefferson R |  | 77.5 |  | 2023-07-21 | 140508670 |  |  |  | New Business
J857993 |  |  |  | Stone Products Unlimited, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 440 | Standalone | #OPI-CHILD-CONNECTOR (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) #NSC #STANDALONE JOB_EMAIL: messages.NLCORP.499779028.6915861c6e@nlcorp.email.netsuite.com SCOPE: 1 Standard eCommerce (BigCommerce) | 2022-11-16 | Klein, Adam D |  |  | Villaverde, Alfredo |  | 6.25 |  |  | 123017237 | 0 | 0 | 190.35 | AMO
J890299 |  |  |  | Kaspien Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | Monitoring - Post Go-Live | 2023-07-01 | Original | 209 | Standalone | #NSC #STANDALONE ¦ DISC: kaspien ¦ SCOPE: 1 Premium Plus Ecommerce (Amazon), 2 Premium Add Ons (FBA to NS Inv Adj, Inbound Shipping Sync Receipt-Only) ***SANDBOX ONLY ¦ JOB EMAIL: messages.NLCORP.530992174.24477aedd8@nlcorp.email.netsuite.com 4/26/23 MKP: all syncs configured and live in sandbox 21-Apr-2023 (MC) overage approved 29-Mar-2023 (MC) overage approved 27-Feb-2023 (MC) overage approved 11/4/22 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 1 Premium Ecomm Connector (Amazon) + 2 Connector Add Ons (FBA Inventory Adjustment, Fulfillment Inventory Sync) | 2023-02-01 |  |  |  | Villaverde, Alfredo |  | 4 |  | 2023-07-01 | 137241240 | 0 | 0 | 113.35 | AMO
J917094 |  |  |  | Delta Millworks Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 30 | Standalone | 5/3/23 - RMO JM - #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Order sync re-configuration. |  |  |  |  | Villaverde, Alfredo |  | 17.25 |  |  | 147926917 |  |  |  | AMO
J906144 |  |  |  | Maty's Healthy Products LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 98 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: matyshealthyproducts ¦ SCOPE: 3 Premium Plus Ecommerce (1 Shopify, 2 Amazon) ¦ JOB_EMAIL: messages.NLCORP.543000376.5a4e7958cc@nlcorp.email.netsuite.com 3/24/23 MKP: prereqs call; NS live, Amazon live, Shopify recently live 2/24/23 MKP: welcome email 2/23/23 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Shopify |  |  |  |  | Villaverde, Alfredo |  | 22.5 |  |  | 143572297 |  |  |  | AMO
J914444 |  |  |  | JPL Global LLC, dba IQ Power Tools. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 52 | Standalone | #NSC #UTOPIA-SOW ¦DISC: iqpower ¦ SCOPE: 1 Premium Ecommerce (Shopify EU) ¦ JOB EMAIL: messages.NLCORP.547888381.ceb51dceef@nlcorp.email.netsuite.com 4/5/23 MKP: adding scope to J909962, customer adding/authorizing connector, no welcome email needed | 2023-04-05 | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 8.75 |  |  | 146410718 | 0 | 0 | 50.35 | AMO
J903645 |  |  |  | Veterninary & Poultry Supply Co. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 115 | Standalone | 2/8/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Shopify messages.NLCORP.541474700.b67b0891f9@nlcorp.email.netsuite.com 2/20/23 TK - approved overage (5h) 2/10/23 AF - sent welcome |  | Nannaware, Anurag |  |  | Villaverde, Alfredo |  | 4 |  |  | 142531341 |  |  |  | AMO
J881881 |  |  |  | Expo Supplies, Inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | Monitoring - Post Go-Live | 2022-12-08 | Actual | 272 | Standalone | 9/8/22 - RMO JM - #NSC #STANDALONE 1 x NS Premium Plus eCommerce Connector - Walmart, eBay and WooCommerce 1 x NS Premium Logistics Connector - ShipStation messages.NLCORP.525026621.136bee3dd1@nlcorp.email.netsuite.com 5/18/2023 AF - Scope complete. Customer requesting Settlement sync which is not in scope. Looping AMO in for resolution. 4/11/2023 AVV - Moving project to green status, as we're closing in the last remaining issues 3/8/23 AF - working to set up final calls with client 2/17/23 AF - tested amazon setup, modified some settings for woocommerce, 2/15/2/3 AF - client was taking a very long time to test, FC followed up on status to test refunds, 12/8/22 GD - I provided UAT and go live instructions today. However, we still need to test eBay, Walmart, and WooCommerce refund sync. I'm waiting on the client for orders I can refund for eBay and Walmart. There is a support case for a WooCommerce error. 11/3/22 GD - Kickoff call. Began configuring Amazon order sync 9/13/22 AF - sent welcome | 2022-11-03 |  |  |  | Villaverde, Alfredo | 2022-12-08 | 9 |  |  | 133781505 | 36 | 36 | 203.35 | AMO
J888081 |  |  |  | Astroflav LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 227 | Standalone | 10/24/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Shopify + Shipstation #delayed Job email: messages.NLCORP.544258765.1eed91e894@nlcorp.email.netsuite.com 5/16/2023 AVV - Partner (Paapri) conveyed that the customer is quite unresponsive and elusive around ERP deliverables. Paapri's leadership will put pressure on customer to commit to a firm timeline to drive the go live. Will await for Paapri's updates. 5/15/2023 AVV - Followed-up with AMO and Partner stakeholder to get insight on ERP project's expected Go Live. 4/18/23 AVV - Sent follow-up to customer after final configuration call recap email sent by consultant. Customer should be performing UAT testing by now, although we have not received a response on status. 4/10/23 AVV - Conducted final configuration session. Both ShipStation and Shopify mappings have been completed. Sent UAT test cases to customer. 4/3/23 AVV - Followed up with AMO manager, as AMO left the company. We have a major communication gap with the partner involved, and it is unlikely that that the customer will be able to complete their action items without help. The customer is frustrated. Setting customer relationship status to yellow. May need to escalate if we don't find resolution for next steps within the following days. 3/13/23 AF - pinged AMO on project status and how they could help with the outreach 3/6/23 AF - AMO working to reach out to client 2/8/23 AF - discussed situation again with client 1/5/23 AF - explained situation to NS escalations team 1/4/23 AF - pinged client and told them their partner was unresponsive 12/2/22 AF - client working with partner on prereqs 10/25/22 AF - sent welcome | 2023-04-03 | Pitla, Venkatesh |  |  | Villaverde, Alfredo |  | 8.5 |  |  | 136392717 | 0 | 0 | 52.35 | New Business
J835556 |  |  |  | Le Groupe Lemur Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 618 | Standalone | #NSC-UNKNOWN-STANDARD-QTY4 #NSC-UNKNOWN-PREMIUM #STANDALONE JOB_EMAIL: messages.NLCORP.465886090.b827765e33@nlcorp.email.netsuite.com SCOPE: 4 Standard eCommerce (4 Shopify) upgrade to Premium Plus, 1 Premium Logistics (Shipstation) 5/2/23 MKP: need to schedule closing call 2/16/22 - We sent out meeting invites throughout the month of March, the kickoff call and the rest of the meetings will need to be rescheduled 12/23/22 - TK - approved overage (15h) | 2022-05-17 | Seo, Joo Youn |  |  | Villaverde, Alfredo |  | 0.5 |  |  | 108590826 | 0 | 0 | 373.35 | New Business
J865047 |  |  |  | New Signature Homestyles, LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 388 | Standalone | 5/10 - RMO JM - #NSC #STANDALONE JOB_EMAIL: messages.NLCORP.520020347.7906796ab9@nlcorp.email.netsuite.com SCOPE: 3 Starter eCommerce (Amazon, Shopify, Walmart, 1 Premium Logistics (ShipStation) | 2022-08-24 | Archer, Nathaniel |  |  | Villaverde, Alfredo |  | 4 |  |  | 126643696 | 0 | 0 | 274.35 | New Business
J914860 |  |  |  | Bags Unlimited, Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 50 | Standalone | 4/12/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Std Walmart messages.NLCORP.548651490.5a2501c7f2@nlcorp.email.netsuite.com 4/12/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 14 |  |  | 146625718 |  |  |  | AMO
J904958 |  |  |  | ElleVet Sciences LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 112 | Standalone | 2/10/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2 x NS Premium Plus eCommerce Connector - WooCommerce messages.NLCORP.541895290.b88cd98dd8@nlcorp.email.netsuite.com 15-Feb-2023 (MC) overage approved for PM hours 2/14/23 AF - sent welcome |  | N V, Akhilesh |  |  | Villaverde, Alfredo |  | 21 |  |  | 142787280 |  |  |  | New Business
J911587 |  |  |  | Featherstone Foods Inc. ¦ Activation - SuiteSuccess for Commerce | Blakely, Mike | In Progress | 2023-06-01 | Original | 64 | Standalone | 5/22/23 mblakely gave access to 800 customers today - 5/18/23 - mblakely client gave access to 20 customers today it's a start. We have about 980 to go, but this first round should get them excited. 5/4/23 - mblakely given the client only has a myaccount site, we are going to spend May to get catalog ready so we can leave the client with a functioning ecommerce site to avoid debook risk. May is the catalog sprint to get the client to turn on items. 5/1/23 - mblakely we got the client live - they need to send welcome email to customers, but J825072 that became a 100 day CO/CAR is now live! |  | Blakely, Mike |  |  | Cristobal, Kevin S |  | 37 |  | 2023-06-01 | 145633723 |  |  |  | AMO
J864465 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Goodman Community Center ¦ Implementation Service - Fixed Bid | Varsallona, Jeremiah J | In Progress | 2023-05-15 | Revised | 391 | Standalone | #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) Email tag: messages.NLCORP.528187917.73327b9eb5@nlcorp.email.netsuite.com 4/21 JV - Customer is testing ERP use cases in Sandbox to check if other functions were impacted by the changes required to install the SCIS bundle. 4/14 JV - Customer refreshed sandbox with removed all work. Had to spend additional time to reconfigure the sandbox account and continue walkthroughs. Versapay CC hardware has arrived. 3/10 JV - SCIS deployment and configurations still in progress in Sandbox. Walkthroughs expected next week. 01/31/23 - Project restarted and SCIS personalization session has been scheduled for 2/7/2023. 12/11 JV - Job is delayed until January 2023. 10/27 JV- Held SOW review call with customer. Customer asked me to schedule Walkthrough sessions in January 2023. | 2022-10-27 | Varsallona, Jeremiah J |  |  | Bazzani, Emiliano |  | 57.5 | 2023-05-15 | 2023-04-03 | 126579337 | 0 | 0 | 210.35 | AMO
J838964 |  |  |  | Maravia Corporation, DBA Cascade River Gear ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 594 | Standalone | #NSC-WOOCOMMERCE #PREMIUMPLUS #STANDALONE JOB_EMAIL: messages.NLCORP.493623788.7b0fc47098@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus eCommerce (WooCommerce) 1/23/23 (MC) Overage approved (10 hours) 11/04/21 MP: on hold discussion; NS go live is March 01/21/22 MP: follow up; NS go live is April now 01/24/22 MP: sent SOW extension for signature 01/26/22 MP: ERP PM timeline discussion 12/22/22 (MC) Overage approved | 2022-12-15 | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 3.25 |  |  | 110887092 | 0 | 0 | 161.35 | New Business
J865036 |  |  |  | Noel Furniture, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | Monitoring - Post Go-Live |  |  | 391 | Standalone | #NSC #STANDALONE ¦ DISC: noelfurniture ¦ SCOPE: 1 Standard Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.509239712.ab1db036da@nlcorp.email.netsuite.com 4/28/23 (MC) overage approved 4/18/23 MKP: UAT follow up 4/7/23 MKP: SOW extension processed, target to finish by EOM 4/5/2023 AVV: Followed up with AMO to request assistance, as customer has not signed the SOW extension yet. 3/23/2023 Customer will be signing SOW Extension (requested Melinda to be resent via DocuSign) 3/10/2023 (MC) overage approved 3/2/23 AVV: Engaged Melinda as PM on this project. Customer will meet with Goutham to review outstanding issues next week. Keeping schedule until we have certainty of imminent project closure. 3/1/2023 AVV: Our FC is following up with the customer on outstanding issues. 2/28/2022: Attempting to get the customer's confirmation for the completion of this project, as they have not replied to a request to confirm whether they had any outstanding issues. Setting the status to Delayed - Per Customer until we can close it. Will follow up next week. 2/28/23 AVV: Setting Customer relationship status to yellow due to the responsiveness level of this customer, as well as the communication and decision-making dynamics across the multiple stakeholders. 11/22/2022 AVV: Reached out to AMO as customer has been unresponsive since May and job is expired.. Review Messages tab for communications. 5/9 - RMO JM - #NSC NSC Scope: 1xStd Shopify |  | Jakke, Goutham |  |  | Villaverde, Alfredo |  | 4.5 |  |  | 126643289 |  |  |  | AMO
J881205 |  | #POS-SCIS-PLUSCUSTOMIZATION | #POS-SCIS-PLUSCUSTOMIZATION | AAA Distributor, LLC ¦ Implementation Service - Fixed Bid | Varsallona, Jeremiah J | Delayed - Per Customer | 2023-08-22 | Original | 276 | Standalone | #POS-SCIS-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) Job record tag: messages.NLCORP.524133231.ed582df85b@nlcorp.email.netsuite.com EB: 4/13 AMO replied today, said we are not sure when they will be able to resume this engagement. follow up set as May 1st JV: 4/11 No change in Status. AMO has been notified that customer is unresponsive. JV: 3/10/2023 Customer has not responded. Escalated to AMO. AMO advised customer is under going an audit and had recent layoffs. AMO will notify me when they are ready to restart the project. JV: 01/23/23 AMO notified me the customer would like to start the project on 3/1. JV: 11/30 Kevin asked to put job on hold until January 2023. JV: 11/7 Kevin advised they might postpone implementation until January. JV: 9/27 Aman Sable is engaged with customer to implement commission module. JV: 10/11 Customer is waiting for customization to be in place and then will schedule a sandbox refresh JV: 10/11 SCIS Personalization Session JV: 9/22 Kick Off Call |  | Varsallona, Jeremiah J | Bazzani, Emiliano |  | Bazzani, Emiliano |  | 143 |  | 2023-08-22 | 133573748 |  |  |  | New Business
J919459 |  |  |  | Greenes Fence Co., Inc. ¦ Implementation Service - Fixed Bid | Waris, Clare | In Progress |  |  | 24 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ¦ SCOPE: ShipStation Premium Logistics Connector ¦ JOB EMAIL: messages.nlcorp.552350074.dbad62cba0@nlcorp.email.netsuite.com 5/15/23 CEW: Welcome email sent 5/8/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Shipstation |  |  |  |  | Villaverde, Alfredo |  | 14.25 |  |  | 148379322 |  |  |  | AMO
J910022 |  |  |  | Gryphen Specialty Products and Services, LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 84 | Standalone | 3/13/23 - RMO JM - #NSC #STANDALONE ¦ Premium Plus Shopify messages.NLCORP.545081611.6d793de096@nlcorp.email.netsuite.com 5/19/23 AF - sent follow up 3/13/23 AF - sent welcome |  | Jakke, Goutham |  |  | Villaverde, Alfredo |  | 9 |  |  | 144615445 |  |  |  | AMO
J900806 |  |  |  | Valley Distribution and Logistics, LLC. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 144 | Standalone | #NSC #STANDALONE ¦ DISC: ¦ SCOPE: 1 Premium Logistics (ShipStation) ¦ JOB_EMAIL: messages.NLCORP.537720256.338e572a41@nlcorp.email.netsuite.com 5/3/23 MKP: follow up and sent SOW extension 1/27/23 (TK) - overage approved (6h) 1/18/23 MKP: welcome sent 1/9/23 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Shipstation |  |  |  |  | Villaverde, Alfredo |  | 7.75 |  |  | 140898063 |  |  |  | New Business
J919602 |  |  |  | Nowak Dental Supplies, Inc. ¦ Consulting Time | Villa, Myr Angeli | In Progress |  |  | 21 | Standalone |  |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 112 |  |  | 148427699 |  |  |  | AMO
J901452 |  |  |  | Gallagher Promotional Products, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 135 | Standalone | 1/18/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Std Magento JOB_EMAIL: messages.NLCORP.538770940.404f07bc2d@nlcorp.email.netsuite.com SCOPE: 1 Standard Ecommerce (Magento) |  |  |  |  | Villaverde, Alfredo |  | 5.5 |  |  | 141454206 |  |  |  | New Business
J883273 |  |  |  | Cleanco Distributors, Inc. - Professional Services : Activation - SuiteSuccess for | Null, Taylor | Delayed - Per Other Project | 2023-08-18 | Revised | 266 | Joint | 3.10.2023 TN -- Kickoff held on 3/7. Charlie said SC will likely be pushed to post go-live. He expressed concerns with functionality included in SC base edition and made comments that he is not sure they made the right choice with SC, so EWS escalation was logged. 3.3.2023 TN -- SC kickoff scheduled for 3/7. 2.17.2023 TN -- Still waiting on sample data for ERP to move to PW1s. Once PW1s have been scheduled, I will schedule a call between Santiago, myself, and Charlie to talk about SC timeline. 11.23.2022 TN -- KO held on 11/21. Charlie brought up WMS again, Christina is connecting him to SP for scoping. Charlie wants to pause the project until he figures out the WMS piece. 11.10.2022 TN-- ERP Intro call scheduled for 11/14. ERP project should kick off soon and then SC can get engaged in the following weeks. 10.20.2022 TN -- Reached out to Charlie to schedule introduction meeting. Has not responded. 9.30.2022 TN -- Charlie does not want to kickoff until 10/31. Will place job in delayed status next week. 9.23.2022 TN -- POC has not started at the company yet, want to wait a few weeks to kickoff. #SC-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) |  | Estellano, Santiago |  | Bazzani, Emiliano | Footitt, Lindsey N |  | 71.5 | 2023-08-18 | 2023-03-01 | 133947729 |  |  |  | New Business
J887629 |  |  |  | Ameico ¦ Consulting Time | Preedanon, Melinda | Monitoring - Post Go-Live |  |  | 232 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ameico ¦ SCOPE: 1 Premium Ecommerce (Shopify), 1 Premium Plus Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.529578309.84ca9b5cb4@nlcorp.email.netsuite.com 5/15/23 MKP: closing email 27-Apr-2023 (MC) overage approved 3/3/23 MKP: FC followed up 31-Jan-2023 (MC) overage approved for PM hours 1/30/23 MKP: kickoff call 10/26/22 MKP: welcome email 10/14/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Shopify 2x | 2023-01-30 | Pitla, Venkatesh |  |  | Villaverde, Alfredo |  | 6.75 |  |  | 136176585 | 0 | 0 | 115.35 | AMO
J906868 |  |  |  | Kline Franchising, Inc. ¦ Consulting Time | Farmer, Andrew | In Progress | 2023-05-17 | Actual | 93 | Standalone | 2/28/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify messages.NLCORP.543548088.dc06396feb@nlcorp.email.netsuite.com 2/28/23 AF - sent welcome 3/8/23 GD - Kickoff 5/16/23 - Provided UAT and Go Live instructions | 2023-03-07 |  |  |  | Villaverde, Alfredo | 2023-05-17 | 0.75 |  |  | 143909705 | 71 | 71 | 79.35 | AMO
J890535 |  |  |  | Steve Weiss Music ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 206 | Standalone | 11/9/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 1 X Std Shopify 11/18/22 (MC) Overage approved 11/9/22 AF - sent welcome |  | Pitla, Venkatesh |  |  | Villaverde, Alfredo |  | 12 |  |  | 137349826 |  |  |  | AMO
J893393 |  |  |  | Shine Company, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 188 | Standalone | 11/25/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Shipstation JOB_EMAIL: messages.NLCORP.533423669.85c7ee64ae@nlcorp.email.netsuite.com SCOPE: 1 Premium Logistics (ShipStation) 12/22/22 (MC) - overage approved | 2022-12-17 | N V, Akhilesh |  |  | Villaverde, Alfredo |  | 2.75 |  |  | 138522230 | 0 | 0 | 159.35 | New Business
J913689 |  |  |  | POWER DENTAL U.S.A. INC. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 55 | Standalone | 4/7/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Magento messages.NLCORP.548153785.84517b4aed@nlcorp.email.netsuite.com 4/7/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 27 |  |  | 146247060 |  |  |  | AMO
J909419 |  |  |  | Razertip Industries Ltd. ¦ Consulting Time | Farmer, Andrew | In Progress | 2023-04-20 | Actual | 86 | Standalone | 3/10/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Standard Amazon messages.NLCORP.545072470.41ebf1dad5@nlcorp.email.netsuite.com 3/13/23 AF - sent welcome 4/20/23 GD - Kickoff call. Finished order/fulfillment sync. The client didn't need product sync. Provided UAT and go live instructions. | 2023-04-20 |  |  |  | Villaverde, Alfredo | 2023-04-20 | 8.75 |  |  | 144343567 | 0 | 0 | 35.35 | AMO
J898669 |  |  |  | Hunt Textiles ¦ Consulting Time | Farmer, Andrew | Monitoring - Post Go-Live | 2023-05-18 | Actual | 156 | Standalone | 1/3/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ No info on the 2 Storefronts yet messages.NLCORP.537004000.2d2a7f5355@nlcorp.email.netsuite.com 5/18/23 AF - client live 3/29/23 AF - customer wants to proceed 3/6/23 AF - followed up again, said if we do not hear back we will close the project, client finally responded and said NS is still being set up by a partner, changing the job to on-hold 2/22/23 AF - followed up due to nonresponsiveness 1/4/23 AF - followed up with client on prereqs 01 03 2023 MK : Overage of 5 hrs applied for Proj mgmt hours. Approved by Vertical Lead Meenakshi S Krishnan. Job has been updated 1/3/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo | 2023-05-18 | 14 |  |  | 140387716 | 0 | 0 |  | New Business
J905896 |  |  |  | Inside Source, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 99 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: insidesource ¦ SCOPE: 2 Premium Ecommerce (2 Shopify) ¦ JOB EMAIL: messages.NLCORP.542972318.fcac1696b6@nlcorp.email.netsuite.com 2/23/23 MKP: welcome email 2/22/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2x Prem Shopify |  | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 19.75 |  |  | 143453607 |  |  |  | AMO
J856890 |  |  |  | SD Bullion, Inc ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress | 2023-04-01 | Original | 451 | Standalone | JOB_EMAIL: messages.NLCORP.495246897.2d78689e49@nlcorp.email.netsuite.com Important note: This job was repurposed to complete the ERP implementation from job J851711, as the customer did not want to move forward with the implementation of 2 Premium Plus eCommerce connectors (1 Magento, 1 eBay). 4/13/2023 AVV - Sent SOW Extension via DocuSign to customer. Additional Cutover Support from Lilly Brown: Built CSV Imports for transactions Cutover at transaction level - high volume assisted with configuration between magento and NS Cleared enviorment for go-live helped with bank rec set up and tax set up Find below the notes on previous work completed for NSC scope 6/21: Provided UAT doc and go live instructions. Order sync is completed. The client said product sync and eBay refund was unnecessary for them. M2 to NS refund sync was insufficient for their needs b/c they wanted to refund customer deposits and payments. The connector only supports posting credit memos and cash refunds. The connector is currently configured to post invoices to NS. We had previously configured it to post sales orders and cash sales. The client had changed the type of transactions b/c he wants to account for the payments on orders. While testing he reported an issue with discounts. I asked for an example but the client did not provide one. 6/8/22 GD: Installed NSC SuiteApp, connected NS to NSC, set up order mappings for M2 and ran into an issue when testing M2 order b/c taxes are not configured in NS | 2022-06-21 |  |  |  | Villaverde, Alfredo |  | 19.5 |  | 2023-04-01 | 122029176 | 0 | 0 | 338.35 | AMO
J915816 |  |  |  | Too Corporation Americas ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 38 | Standalone | 4/26/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon |  |  |  |  | Villaverde, Alfredo |  | 9.5 |  |  | 147437589 |  |  |  | AMO
J898196 |  |  |  | Geartrade Retail LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 160 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: geartradecom ¦ SCOPE: 1 Premium Plus Ecommerce (Amazon) ¦ JOB EMAIL: messages.NLCORP.537720335.23abaa895f@nlcorp.email.netsuite.com 5/17/23 MKP: follow up 1/20/23 MKP: sandbox discussion, not in scope 1/10/23 MKP: welcome email 12/21/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦Premium eCommerce Connector - Amazon |  |  |  |  | Villaverde, Alfredo |  | 8.25 |  |  | 140264082 |  |  |  | AMO
J906563 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Cheap Joe's Art Stuff ¦ Implementation Service - Fixed Bid | Desimini, Peter N | In Progress | 2023-09-01 | Revised | 93 | Joint | 5/16/23 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus Magento #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2023 0524- PND - Personalization Follow up sessions completed. Walkthrough 1 Sessions in progress. Expected to be completed by 6/14 for ERP, WMS and SCIS. Engage checkpoint scheduled for 5/25 2023 0511- PND - Personalization Sessions Completed. Follow up sessions expected to be completed by May 19. Walkthrough 1 Sessions scheduling in progress. | 2023-03-21 | Barchichat, Yoni | Bazzani, Emiliano |  | Riccardi, David |  | 461.5 | 2023-09-01 | 2023-09-01 | 143832673 | 0 | 0 | 65.35 | New Business
J919701 |  |  |  | STUDSON, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 21 | Standalone | 5/11/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon |  |  |  |  | Villaverde, Alfredo |  | 8.25 |  |  | 148475041 |  |  |  | AMO
J903022 |  |  |  | Optimum Foods LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 119 | Standalone | 2/2/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Std Shopify JOB_EMAIL: messages.NLCORP.540899876.a635446fbd@nlcorp.email.netsuite.com SCOPE: 1 Standard Ecommerce (Shopify) 21-Mar-2023 (MC) - overage approved |  | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 0.75 |  |  | 142388904 |  |  |  | AMO
J912453 |  |  |  | HollowPoint, LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 56 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: wickededgeprecisionsharpeners ¦ SCOPE: 1 Premium Plus Ecommerce (Amazon) ¦ JOB EMAIL: messages.NLCORP.547906958.a5c291e884@nlcorp.email.netsuite.com 4/5/23 MKP: welcome email 4/4/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon |  |  |  |  | Villaverde, Alfredo |  | 4 |  |  | 146027483 |  |  |  | AMO
J912176 |  |  |  | KC Store Fixtures ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 62 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ¦ SCOPE: 1 Premium Plus Ecommerce (Amazon) ¦ JOB EMAIL: messages.NLCORP.547737270.fe631f59a8@nlcorp.email.netsuite.com 4/4/23 MKP: welcome email 3/31/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus Amazon |  |  |  |  | Villaverde, Alfredo |  | 9.25 |  |  | 145964286 |  |  |  | AMO
J915993 |  |  |  | Shani Darden Skincare, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 37 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ¦ SCOPE: 1 Premium Plus Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.550556140.bbd4fc849a@nlcorp.email.netsuite.com ¦ NOTES: switching from Celigo which ends on 7/28 5/2/23 MKP: welcome email 4/27/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify |  |  |  |  | Villaverde, Alfredo |  | 7.5 |  |  | 147504729 |  |  |  | AMO
J890746 |  |  |  | Gurunanda LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 206 | Standalone | 11/9/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Shopify + Amazon Job email: messages.NLCORP.543860921.1080ff25d9@nlcorp.email.netsuite.com 5/22/2023 TK - Approved overage (5h) 5/17/2023 AVV - Following up with AMO, as customer is unresponsive and has not signed the SOW extension. Setting schedule to yellow. 4/3/23 AF - sending welcome 3/2/23 AF - pinged amo on status 11/9/22 AF - Per AMO Farah from client, put on hold until 2023 and they say they re ready. AMO Said would notify us |  |  |  |  | Villaverde, Alfredo |  | 25 |  |  | 137363972 |  |  |  | AMO
J914752 |  |  |  | Nowak Dental Supplies, Inc. ¦ Implementation Service - Fixed Bid | Villa, Myr Angeli | In Progress |  |  | 51 | Standalone |  |  | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | 15.25 |  |  | 146552523 |  |  |  | AMO
J896395 |  |  |  | Ciro Corporation ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 176 | Standalone | 12/14/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ x2 Prem+ Shopify messages.NLCORP.535024904.e95675405e@nlcorp.email.netsuite.com 5/18/23 AF - client finally responding, moving forward with setup and sow extension 3/3/23 AF - sent follow up to client on connector names, discussed with AMO, this job is for a follow up to oru shopify set up, but it was confusing 12/14/22 AF - sent welcome |  | Nannaware, Anurag |  |  | Villaverde, Alfredo |  | 15.5 |  |  | 139068896 |  |  |  | New Business
J917198 |  |  |  | Bootstrap Brands, Inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 30 | Standalone | 5/3/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify and 2x Amazon , Premium Shipstation, Premium AddOn Inventory Adjustment Full Flow Connector Amazon , Premium AddOn Seller Inbound Shipping Full Flow Connector Amazon messages.NLCORP.551245914.75d65ba478@nlcorp.email.netsuite.com 5/3/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 63.5 |  |  | 147936957 |  |  |  | AMO
J921065 |  |  |  | Sahni's Enterprises, Inc. ¦ Implementation Service - Fixed Bid | Waris, Clare | Assigned |  |  | 14 | Standalone | 5/19/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus Amazon and 2x BigCommerce |  |  |  |  | Villaverde, Alfredo |  | 30 |  |  | 149024131 |  |  |  | AMO
J902451 |  |  |  | Omni Distributors, LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 125 | Standalone | 1/31/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Shipstation messages.NLCORP.540525898.2c10c328c9@nlcorp.email.netsuite.com 2/2/23 AF - sent welcome |  | Nannaware, Anurag |  |  | Villaverde, Alfredo |  | 14 |  |  | 142164937 |  |  |  | New Business
J883401 |  |  |  | Manskape LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | Monitoring - Post Go-Live | 2023-04-26 | Actual | 267 | Standalone | 5/18 TK - Approved overage (+15) 5/12 AV - Met with client. Reviewing UAT testing 4/26/23 AF - wrapped up shipstation 4/10/23 AF - wrapping up testing on shopify 2/28/23 AF - client resuming, requested sow extension 1/12/23 AF - client requested a hold on the job 12/20/2022 AF - kicked off 9/24/22 - TK - approved overage (7h) 9/13/22 - RMO JM - #NSC #STANDALONE ¦ NSC Scope - 1x NS Standard eCommerce Connector Shopify, Walmart, Amazon + 1 x NS Premium Logistics Connector - ShipStation 9/15/22 AF - sent welcome | 2022-12-20 |  |  |  | Villaverde, Alfredo | 2023-04-26 | 10.25 |  |  | 133954704 | 127 | 127 | 156.35 | AMO
J916424 |  |  |  | Huskie Tools ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 34 | Standalone | 4/28/23 - RMO JM - #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon and Premium AddOn Seller Inbound Shipping Full Flow Connector Amazon messages.NLCORP.550662517.2595a99cbf@nlcorp.email.netsuite.com 4/28/23 AF - Sent welcome |  |  |  |  | Villaverde, Alfredo |  | 23 |  |  | 147786393 |  |  |  | AMO
J917784 |  |  |  | The Gifting Group LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 28 | Standalone | 5/4/23 - RMO JM - #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify and Amazon |  |  |  |  | Villaverde, Alfredo |  | 18.75 |  |  | 148041780 |  |  |  | AMO
J904774 |  |  |  | JDC TECHNOLOGY LLC dba Equine ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 113 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ¦ SCOPE: 1 Premium Plus Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.541518814.e3b1feeedd@nlcorp.email.netsuite.com 4/6/23 MKP: follow up 2/13/23 MKP: welcome email 2/9/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify |  |  |  |  | Villaverde, Alfredo |  | 8.25 |  |  | 142723916 |  |  |  | AMO
J914455 |  |  |  | Event Cameras LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 54 | Standalone | 4/11/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Starter eBay , Premium Plus Amazon |  |  |  |  | Villaverde, Alfredo |  | 19 |  |  | 146412283 |  |  |  | New Business
J912407 |  |  |  | Carlson Pet Products, Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 57 | Standalone | 4/4/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2x Prem Shopify messages.NLCORP.547745268.f948be4216@nlcorp.email.netsuite.com 4/4/23 AF - sent welcome |  | Nannaware, Anurag |  |  | Villaverde, Alfredo |  | 11 |  |  | 146018673 |  |  |  | AMO
J876179 |  |  |  | Naked Viking Surf ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 316 | Standalone | 7/18/22 - RMO JM - #NSC #STANDALONE messages.NLCORP.518988455.39391a27e2@nlcorp.email.netsuite.com 5/15/2025 - AVV - DL to meet with AMO and customer on 5/17 to determine next steps. 5/15/2025 - AVV - Customer has been unresponsive for three months. Followed up with AMO's manager, as previous AMO is no longer with the company. Will not be able to keep the job open past May without confirmation from the customer around their willingness to proceed. 5/4/2023 AF - Followed up with AMO on closure 3/27/2023 AVV - AMO leadership reaching out to the customer. Set follow-up date to mid April. Setting back to yellow status, as ERR33262 was marked as completed. 3/13/23 AVV - Setting customer relationship status to red due to internal EWS (ERR33262). AMO facing challenges with the customer's responsiveness, as it may be possible an ERP engagement may be needed for this project to move forward. 2/24/23 AF - client chose to set up his ERP on his own, but has been unsuccessful and wants to pursue a PS engagement. AMO providing a quote on this. 2/13/23 AF - client has still not signed sow extension, going to close the project down, checking with amo 1/15/23 AF - client has been extremely unresponsive this whole time, we've sent 2 sow extensions and only after threatening to shut down the project do we get any response 12/21/22 AF - client needing help with tax setup but out of scope 11/15/22 AF - client working with amo team on additional scope 10/24/22 AF - sent follow on sow extension signature 10/7/22 AF - sent follow up to client, requested sow extension, client was having issues with erp 7/19/22 AF - sent welcome |  | Sivanepalli N V S, Anuhya |  |  | Villaverde, Alfredo |  | 6 |  |  | 131404441 |  |  |  | AMO
J899032 |  |  |  | ECOBags Products, Inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | Monitoring - Post Go-Live | 2022-12-26 | Actual | 154 | Standalone | 12/22/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Shopify messages.NLCORP.535967424.47356893dd@nlcorp.email.netsuite.com 2/13/23 AF - said would close job now due to being completed with no response 1/31/23 AF - pinged again on status 1/23/23 - AF - reached out again on if they approve of the fixes our FC performed end of December 12/28/22 AF - pots go live troubleshooting on going 12/26/22 AF - job completed 12/22/22 AF - sent welcome | 2022-12-26 | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo | 2022-12-26 | 7.5 |  |  | 140456245 | 0 | 0 | 150.35 | AMO
J915894 |  |  |  | Honey Girl Organics, LLC ¦ Consulting Time | Preedanon, Melinda | Monitoring - Post Go-Live | 2023-05-15 | Actual | 37 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: honeygirlorganics ¦ SCOPE: 1 Standard Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.550529239.3fe7b36eef@nlcorp.email.netsuite.com 5/15/23 MKP: go live 5/11/23 MKP: configuration complete, go live instructions sent 05082023 MK - Overage of 5 approved to accommodate for Proj mgmt hours. Overage approved by VL Meenakshi Krishnan. Job Record has been updated. 5/5/23 MKP: kickoff call 4/28/23 MKP: welcome email 4/27/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Standard Shopify | 2023-05-05 | Buenavista, Josiah Frances |  |  | Villaverde, Alfredo | 2023-05-15 | 2.25 |  |  | 147489921 | 10 | 10 | 20.35 | AMO
J912955 |  |  |  | Socksmith Design Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 63 | Standalone | 4/4/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify 4/17/2023 MK - Overage of 6 hours approved for Proj Mgmt. Approved by VL Meenakshi Krishnan. Job Record has been updated. |  | N V, Akhilesh |  |  | Villaverde, Alfredo |  | 5 |  |  | 146139748 |  |  |  | AMO
J907785 |  |  |  | NSN APPAREL CO, LLC dba DREW HOUSE ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 90 | Standalone | 3/6/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2 x NS Premium Plus eCommerce Connectors - Shopify ¦JOB EMAIL¦ messages.NLCORP.544660937.bdb2f1ee85@nlcorp.email.netsuite.com ¦SCOPE¦ 2 Premium Plus Ecommerce (Shopify) 3/9/23 MKP: welcome sent |  |  |  |  | Villaverde, Alfredo |  | 17.25 |  |  | 144070980 |  |  |  | New Business
J909962 |  |  |  | JPL Global LLC, dba IQ Power Tools. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 80 | Standalone | #NSC #UTOPIA-SOW ¦DISC: iqpower ¦SCOPE: 1 Premium Ecommerce (Shopify) ¦JOB EMAIL: messages.NLCORP.544662016.e748807836@nlcorp.email.netsuite.com 3/30/23 MKP: kickoff call 3/9/23 MKP: welcome sent 3/7/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Shopify | 2023-03-30 | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 3.25 |  |  | 144474186 | 0 | 0 | 56.35 | AMO
J901569 |  |  |  | Alex's Lemonade Stand Foundation ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 133 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: alexslemonadestandfoundation ¦ SCOPE: 1 Premium Plus Ecommerce (Shopify) ¦ JOB_EMAIL: messages.NLCORP.539115139.8919a16218@nlcorp.email.netsuite.com 4/10/23 MKP: kickoff call 1/27/23 MKP: welcome email 1/20/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus eCommerce Connector - Shopify | 2023-04-10 | Pitla, Venkatesh |  |  | Villaverde, Alfredo |  | 4.5 |  |  | 141548173 | 0 | 0 | 45.35 | AMO
J911086 |  |  |  | Europe 2 You LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 69 | Standalone | 3/28/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Standard Shopify messages.NLCORP.547137531.96831e929c@nlcorp.email.netsuite.com 4/25/23 AF - on going setup making good progress 3/30/23 AF - sent welcome |  | Nannaware, Anurag |  |  | Villaverde, Alfredo |  | 3.5 |  |  | 145470271 |  |  |  | AMO
J915846 |  |  |  | Undercover ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 38 | Standalone | 4/26/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon |  | Archer, Nathaniel |  |  | Villaverde, Alfredo |  | 7.25 |  |  | 147443555 |  |  |  | AMO
J912614 |  |  |  | Oracle Arms, LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 58 | Standalone | 4/4/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus WooCommerce messages.NLCORP.547743908.3abf8f208d@nlcorp.email.netsuite.com 4/4/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 12.5 |  |  | 146048755 |  |  |  | AMO
J853870 |  |  |  | Eartheasy Sustainable Living Ltd ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 468 | Standalone | #NSC #STANDALONE ¦ DISC: eartheasycom ¦ SCOPE: 2 Premium Plus eCommerce (2 Amazon) ¦ JOB EMAIL: messages.NLCORP.493667979.2bdf0c266b@nlcorp.email.netsuite.com 2/24/22 MKP: welcome email |  | ALURI, DINESH |  |  | Villaverde, Alfredo |  | 3 |  |  | 121118552 | 0 | 0 |  | AMO
J841299 |  |  |  | Gouda Group LLC ¦ Consulting Time | Preedanon, Melinda | Delayed - Non Responsive |  |  | 573 | Standalone | #NSC #STANDALONE ¦ DISC: heartisanfoods ¦SCOPE: 2 Premium Plus eCommerce (Amazon, Shopify) ¦ JOB EMAIL: messages.NLCORP.474492984.c6f2b59d66@nlcorp.email.netsuite.com 5/16/2023 AVV: Sent follow-up to customer and communicated we will be putting the project on hold, and won't be able to extend past October unless we have visibility over timeline and next steps. Will set the job to Delayed - Per customer status next week (after time entries flow through OA) and follow up in October, one month prior to the expiration date, to assess the closure of the job if the customer remains unresponsive. 5/16/2023 AVV: Customer has been unresponsive to AMO as well. 5/9/2023 AVV: Followed up with AMO 5/2/2023 AVV: Requested help from AMO to get visibility over customer's plans to reengage and a firm timeline. 5/2/23 MKP: follow up on SOW extension 4/26/23 MKP: sent SOW extension 3/27/23 MKP: project will go on hold due to customer constraints, determining follow up date 3/17/23 MKP: Followed up with customer 3/7/23 AVV: Followed up with AMO, as customer does not convey firm convictions of continuing with the implementation (messages subtab) 01/09/23 MKP: follow up with customer 01/27/22 MP: status check 11/04/21 MP: welcome sent; on hold discussion, NS not ready | 2022-05-11 |  |  |  | Villaverde, Alfredo |  | 1 |  |  | 112664635 | 0 | 0 | 379.35 | New Business
J882965 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Lee Douglas Interiors, Inc. ¦ Implementation Service - Fixed Bid | Verma, Meenakshi | In Progress | 2023-06-01 | Revised | 267 | Joint | #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 05/06 - Did follow-up with Michele to know the UAT status and expected date of closure. 04/20 - UAT is still in progress and suggested to complete UAT by 28th April, to still Go-Live by 1st June. 04/15 - UAT is not completed and recommended Michele to complete the UAT by 20th April, so that business can concentrate more on Cutover data & End User training. 04/7 - Michele is still assigning the test cases to respective users. UAT progress is very slow. As per revised plan the UAT should complete by 14th April. 03/30 - W2 sessions are complete. UAT discussion session held and customer is good to proceed with UAT. 03/20 - W2 sessions are in progress and last W2 session is scheduled on 24th March. Revised Go-Live date is 1st June 2023. 03/13 - W2 sessions are in progress. Last W2 is scheduled on 22nd March. Go-Live by 1st June seems more realistic, after considering parameters like – W2 is still in progress, UAT, Credit Card integration (post getting it confirmed), cutover activities, etc. Advance Order Management – though it’s part of scope, but it’s not applicable for Lee Douglas business as their inventory is received at one location and then it is cash sale. 03/03 - Walkthrough 2 sessions slot is shared with Kate/Michele. 02/24 - PS Implementation team has addressed all the open issues listed by Kate. 02/17 - Kate has shared list of open issues to be addressed prior to W2. NS team is working on these concerns. 02/08 - Almost entire full list of data is imported, their are few errors on which Sade is working along with Lee team. Post successful import of data, expected to start the W2 effective 13th or 14th Feb. 02/02 - Vendor data is uploaded on File Cabinet. Inventory & Customer data will be shared by 3rd Feb. 01/27 - W1 sessions are completed on 20th Jan. Michele is working on full list of data. 01/13 - Walkthrough 1 session of Advance Order Mgt is still pending. As per Michelle's email dated 5th Jan they want to post pone NS Go-Live date to April 2023, due to their readiness 01/02 - No progress during last week. 12/24 - Michele has requested to schedule other sessions in Jan 2023 due to busy schedule. 12/19 - W1 sessions are in progress and last session is scheduled today. 12/06 - W1 sessions are in progress and expected to complete by 15th Dec. 11/25 - W1 sessions are in progress. 11/21 - W1 sessions are in progress. 11/10 - Michele will work on COA and sample data, and expected to share it by 16th Nov. Walkthrough 1 sessions to be scheduled from – 18th till 30th Nov. 11/4 - Michele has cancelled the weekly review due to non availability. PS sessions are complete. 10/26 - PS sessions are in progress 10/13 - Shared the project plan and shared the slots for PS sessions. Michele has provided the availability from 14th Oct for PS sessions. 10/3 - Kick-off meeting held on 26th Oct. 09/26 - PM Intro held on 23rd Sept and Kick-off is scheduled today. 09/20 - Michele has dropped an email to reschedule the PM Intro meeting on Friday - 23rd Sept. It's rescheduled now. 09/16 - Reverse Sales to PS KT held on 16th Sept and came to know that Solution team was not involved during Sales discussion. PM Intro meeting is rescheduled on 20th Sept as per Michele's request. | 2022-09-29 | Hegde, Vishwanath | Bazzani, Emiliano |  | Catalan, Arvie I |  | 46.75 | 2023-06-01 | 2023-02-01 | 133932549 | 0 | 0 | 238.35 | New Business
J914593 |  |  |  | Pivot Solar Breeze ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 51 | Standalone | #NSC #UTOPIA-SOW scope: 1xPrm+Amazon ecomm ¦ Job email: messages.NLCORP.547881983.9a94443f59@nlcorp.email.netsuite.com 4/5/2023 AVV: Sent Welcome email to customer with prerequisites. Review messages tab. 4/19/23 GD - Kickoff call. Finished FBA and MFN order/fulfillment sync. Finished price/qty sync (mapping only qty). Client is going live with those syncs as soon as possible so I provided them with UAT and go live instructions today. The client was unsure if we are going to configure settlement sync. |  | Dunn, Geoffrey |  |  | Villaverde, Alfredo |  | 10.75 |  |  | 146472235 |  |  |  | AMO
J886032 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Nicolock Paving Stones LLC ¦ Implementation Service - Fixed Bid | Zenisek, Nicholas J | In Progress |  |  | 239 | Standalone | #POS-SCIS-ONLY email tag: messages.NLCORP.528194524.61090e205a@nlcorp.email.netsuite.com 1/4 reached out to customer with dates and times for personalization and kick off 1/5 Personalization schedule for the 6th 1.6 personalization 2.7 walkthrough 1 complete 2.22 getting daily calls setup 4.17 Weekly calls have been on going. Hardware list has been shared. Working with Victor on calls. | 2023-01-06 | Zenisek, Nicholas J | Bazzani, Emiliano |  | Bazzani, Emiliano |  | 54 |  |  | 135578444 | 0 | 0 | 139.35 | AMO
J872661 |  |  |  | Above Food Corp. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | Delayed - Per Customer |  |  | 346 | Standalone | #NSC ¦ DISC: abovefoodcorp ¦ SCOPE: 1 Premium eCommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.513925665.3bc0d0f595@nlcorp.email.netsuite.com 5/9/23 MKP: project delayed until at least June but may not continue, following up end of May 3/16/23 MKP: Not ready to start until June due to customer's "resource constraints and not having a need for the product at this time". 3/7/23 AVV: PM followed up with the customer 2/27/23 AVV: Setting Customer Relationship Status to yellow due to customer's resource constraints. 6/14/22 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) NSC assignment ETA: Awaiting for customer to confirm readiness ETA (working on prereqs on week of 7/3) NSC Scope: 1xShopify(Premium) |  | Teves, Khristine Shara Lee |  |  | Villaverde, Alfredo |  | 5.75 |  |  | 128821291 |  |  |  | New Business
J904094 |  |  |  | Lime Crime, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 115 | Standalone | 2/8/23 - RMO JM - #NSC #STANDALONE ¦ Prem Plus Shopify 3/7/2023 MK - Overage of 6 hours approved for Project management. Approved by VL Meenakshi Krishnan. Job Record has been updated. JOB_EMAIL: messages.NLCORP.541518711.a5c3d0fefb@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus Ecommerce (Shopify) |  | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 3.75 |  |  | 142592990 |  |  |  | AMO
J913231 |  |  |  | Indaba Trading Ltd ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 56 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ¦ SCOPE: 1 Premium Plus Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.547908123.352e119b5c@nlcorp.email.netsuite.com 4/6/23 MKP: welcome email 4/5/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem plus Shopify |  |  |  |  | Villaverde, Alfredo |  | 9.25 |  |  | 146176741 |  |  |  | AMO
J904215 |  |  |  | iPowerResale, Inc ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 114 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ipowerresaleinc ¦ SCOPE: 4 Premium Plus Ecommerce (Amazon, Shopify, eBay, Walmart) ¦ JOB EMAIL: messages.NLCORP.540354703.a23e69bb77@nlcorp.email.netsuite.com 2/3/23 GD - Kickoff call 2/2/23 MKP: welcome email 2/1/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 4x Premium Plus eComm Connectors including Shopify, Amazon, Walmart and eBay. | 2023-02-03 | Dunn, Geoffrey |  |  | Villaverde, Alfredo |  | 27.25 |  |  | 142634813 | 0 | 0 | 111.35 | AMO
J862967 |  |  |  | GEBHARDTS ENTERPRISES, INC. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 402 | Standalone | #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) JOB_EMAIL: messages.NLCORP.505689631.2a6630a7a4@nlcorp.email.netsuite.com SCOPE: 1 Starter eCommerce (BigCommerce), 1 Premium Logistics (ShipStation) |  |  |  |  | Villaverde, Alfredo |  | 13.75 |  |  | 126180111 |  |  |  | AMO
J898857 |  |  |  | SVHB Marketing, LLC dba Horsepower Brands ¦ Implementation Service - Fixed Bid | Farmer, Andrew | Monitoring - Post Go-Live | 2023-05-04 | Actual | 156 | Standalone | 1/3/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus Shopify messages.NLCORP.537005970.9108350fbc@nlcorp.email.netsuite.com This includes updates and communications for job J900425 5/4/23 AF - completed 3/24/2023 AVV Moving project back to green making great progress and about to complete configurations. 3/17@# AF - client almost ready, team helping with prereqs 3/3/23 AF - Client is finally in a place where they are working on prereqs, should be get back to us by next week 3/3/2023 AVV - Setting schedule to yellow and follow-up date while we get confirmation on next steps 3/2/23 AF - sent follow up 1/27/23 - TK - approved overage (5h) 1/18/23 AF - followed up on prereqs 1/3/23 AF - Sent welcome |  | Pitla, Venkatesh |  |  | Villaverde, Alfredo | 2023-05-04 | 3 |  |  | 140404011 | 0 | 0 |  | New Business
J887582 |  |  |  | Elcometer, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 230 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: elcometerinc ¦ SCOPE: 2 Premium Ecommerce (Amazon) ¦ JOB EMAIL: messages.NLCORP.529578522.77cb3e73f4@nlcorp.email.netsuite.com 12/9/22 MKP: closing call 12/1/22 MKP: configuration complete 11/30/22 GD - kickoff call 12/1/22 GD - Provided UAT and Go Live instructions 10/14/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2 x NS Premium eCommerce Connector - Amazon | 2022-11-30 |  |  |  | Villaverde, Alfredo |  | 15.25 |  |  | 136165030 | 0 | 0 | 176.35 | AMO
J906190 |  |  |  | TFO Holdings, LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 98 | Standalone | 2/27/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 1 x NS Premium Plus eCommerce Connector - Amazon JOB_EMAIL: messages.NLCORP.543394402.1824525fd4@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus Ecommerce (Amazon) |  |  |  |  | Villaverde, Alfredo |  | 7.75 |  |  | 143578938 |  |  |  | New Business
J906836 |  |  |  | Driftwood Dairy, Inc. ¦ Consulting Time | Joshi, Aarti | In Progress | 2023-05-08 | Original | 93 | Standalone |  |  | Joshi, Aarti |  |  | Bazzani, Emiliano |  | 10 |  | 2023-05-08 | 143901088 |  |  |  | AMO
J893328 |  |  |  | Fuzion Sports, LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 205 | Standalone | 11/23/22 - RMO JM - #NSC #STANDALONE ¦ Shipstation JOB_EMAIL: messages.NLCORP.532654505.98dc7c5588@nlcorp.email.netsuite.com SCOPE: 1 Premium Logistics (ShipStation) |  |  |  |  | Villaverde, Alfredo |  | 3.5 |  |  | 138515951 |  |  |  | New Business
J910136 |  |  |  | DETROIT SPONGE & CHAMOIS CO., INC. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 83 | Standalone | 3/15/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2x Prem Shopify messages.NLCORP.545621504.ff256ae6de@nlcorp.email.netsuite.com 4/25/23 AF - sent follow up on client testing 3/17/23 AF - sent welcome |  | ALURI, DINESH |  |  | Villaverde, Alfredo |  | 5 |  |  | 144680575 |  |  |  | AMO
J909791 |  |  |  | That's It Nutrition, LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 24 | Standalone | 3/7/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Shopify Prem Shipstation messages.NLCORP.544536832.9ed29c4c42@nlcorp.email.netsuite.com 3/8/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 10.25 |  |  | 144398607 |  |  |  | AMO
J917236 |  |  |  | Sentinel Door Controls, LLC Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 29 | Standalone | 5/4/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Standard Shopify and Prem Plus Amazon messages.NLCORP.551397276.66c690b126@nlcorp.email.netsuite.com 5/4/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 24 |  |  | 147942629 |  |  |  | AMO
J846620 |  |  |  | Danik Industries Ltd ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 532 | Standalone | #NSC #STANDALONE ¦ DISC: swagman ¦ SCOPE: 2 Premium eCommerce (2 Shopify) ¦ JOB EMAIL: messages.NLCORP.483090031.4294bc4168@nlcorp.email.netsuite.com 5/12/23 MKP: support case 5152245 ERP issues blocking progress 4/11/23 MKP: SOW extension complete 3/13/23 MKP: kickoff status from FC 1/3/22 MKP: welcome email #NSC-UNKNOWN-QTY2 #PREMIUM (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) #KICKOFFFAIL customer has another job for new ERP that is also underway. They can't meet pre-reqs of creating the same orders manually they are trying to sync. Job stalled until that happens. | 2023-03-13 | Abella, Mary Jane |  |  | Villaverde, Alfredo |  | -1.75 |  |  | 116272946 | 0 | 0 | 73.35 | AMO
J904014 |  |  |  | Corkcicle, LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 114 | Standalone | 2/8/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Shopify messages.NLCORP.541476209.c83f5ba8b3@nlcorp.email.netsuite.com 2/10/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | -0.25 |  |  | 142579254 |  |  |  | AMO
J917348 |  | #POS-NSPOS-PHASE | #POS-NSPOS-PHASE | Delaware North Companies, Incorporated ¦ Consulting Time ¦ Venuetize | Sass, David | In Progress |  |  | 23 | Joint | #POS-NSPOS-PHASE2 (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 2023 0519 ¦ DMS ¦ DL requesting overage. AMO presenting new SOW to customer to finish phase 2. Kick off meeting for Venuetize issues was today and customer is going to work with Nick on recreating errors so that we can debug. 2023 0505 ¦ DMS ¦ Working with DL to request overage. New job assigned and KT with ACS is Tuesday. Tapin2 working with the APIs and reach out to Ravi when they get stuck. First script development complete. Second script is still not defined. 5/2/23: RWG: Welcome letter sent to customer / project team. |  | Zenisek, Nicholas J | Bazzani, Emiliano |  | Gabrielli, Richard |  | 115.25 |  |  | 147976766 |  |  |  | AMO
J904699 |  |  |  | Dealmed Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 111 | Standalone | 2/13/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Shopify messages.NLCORP.542167941.dec85c396a@nlcorp.email.netsuite.com 5-May-2023 (MC) overage approved 21-Feb-2023 (MC) overage approved for PM hours not included 2/16/23 AF - sent welcome |  | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 7 |  |  | 142717500 |  |  |  | AMO
J905787 |  |  |  | Insight 2 Design, LLC ¦ Consulting Time | Farmer, Andrew | Monitoring - Post Go-Live | 2023-03-15 | Actual | 100 | Standalone | 2/21/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ NSC Scope: 1 x NS Premium eCommerce Connector - Walmart messages.NLCORP.543115351.5de469383c@nlcorp.email.netsuite.com 5/24/23 AF - will close when time is settled 3/15/23 AF - client live 2/24/23 AF - sent welcome |  | Jakke, Goutham |  |  | Villaverde, Alfredo | 2023-03-15 | 5 |  |  | 143413909 | 0 | 0 |  | AMO
J905870 |  | #POS-NSPOS-PHASE | #POS-NSPOS-PHASE | Olsen Europe Fashion Canada Inc. ¦ Consulting Time | Varsallona, Jeremiah J | In Progress |  |  | 99 | Standalone | #POS-NSPOS-PHASE2 3/31 JV - Met with Jenny to fix tax calculation issue for Test Canadian location using NSPOS 202.1.10 3/10 JV - Completed fixing tax issues. Still researching for Root Cause and testing taxes in new version of NSPOS. 2/16 JV - Kicked off project with the customer today. Engage Nick Zenisek who did the configurations for them in February 2022. | 2023-02-16 | Zenisek, Nicholas J |  |  | Bazzani, Emiliano |  | 5.25 |  |  | 143446001 | 0 | 0 | 98.35 | AMO
J914532 |  |  |  | Capsule Supplies LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 52 | Standalone | 4/10/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon messages.NLCORP.548370289.97bf34cec5@nlcorp.email.netsuite.com 4/17/23 MK - Overage of 5 hours approved for Proj mgmt. Approved by VL Meenakshi Krishnan. Job Record has been updated. 4/10/23 AF - sent welcome. |  |  |  |  | Villaverde, Alfredo |  | 6.75 |  |  | 146422988 |  |  |  | AMO
J905486 |  |  |  | Tishkoff Enterprises, LLC (Drew Shoe) ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 105 | Standalone | 2/17/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon messages.NLCORP.542830744.b3dd4ec3be@nlcorp.email.netsuite.com 3/3/23 AF - client is not live in NetSuite yet, assessing set up so far, client also wants a sandbox setup which is not in scope, discussing with AMO 2/23/2023 MK - Overage of 5 hours added for project management. Approved by Vertical Lead Meenakshi Krishnan. Job Record has been updated. 2/22/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 11.75 |  |  | 143158482 |  |  |  | AMO
J884319 |  |  |  | LaborLawCenter, LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 253 | Standalone | 9/15/22 - RMO JM - #NSC #STANDALONE JOB_EMAIL: messages.NLCORP.525635235.fed6507329@nlcorp.email.netsuite.com SCOPE: 3 Premium Plus eCommerce (Amazon sandbox & prod), 1 Premium Logistics (ShipStation prod) 10/5/22 GD: Kickoff call 10/13/22 GD: Finished Amazon Premium in NS sandbox | 2022-09-16 |  |  |  | Villaverde, Alfredo |  | 12.75 |  |  | 134730052 | 0 | 0 | 251.35 | AMO
J909470 |  |  |  | Soko, Inc. ¦ Consulting Time | Preedanon, Melinda | Monitoring - Post Go-Live | 2023-05-10 | Actual | 86 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: sokoinc ¦ SCOPE: 1 Premium Plus Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.545520471.cbced54b45@nlcorp.email.netsuite.com 3/16/23 MKP: welcome sent 3/10/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus Shopify | 2023-04-03 | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo | 2023-05-10 | -2.75 |  |  | 144347446 | 37 | 37 | 52.35 | AMO
J911172 |  |  |  | Pop-A-Shot Enterprise LLC ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | Monitoring - Post Go-Live | 2023-05-15 | Actual | 69 | Standalone | #NSC #STANDALONE ¦ DISC: popashotenterprisellc ¦SCOPE: NSC SuiteApp Migration ¦ JOB EMAIL: messages.NLCORP.548774449.cf1294af31@nlcorp.email.netsuite.com 5/15/23 MKP: closing email 4/28/23 MKP: configuration complete 4/14/23 MKP: kickoff 4/13/23 MKP: welcome email sent | 2023-04-14 |  |  |  | Villaverde, Alfredo | 2023-05-15 | 9.25 |  |  | 145485503 | 31 | 31 | 41.35 | AMO
J907588 |  |  |  | Progressive Materials LLC. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 90 | Standalone | 3/2/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Standard Shopify messages.NLCORP.543885372.16a5b07db8@nlcorp.email.netsuite.com 3/2/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | -1.75 |  |  | 144062974 |  |  |  | AMO
J916457 |  |  |  | Pangaea Holdings, Inc ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 35 | Standalone | 4/27/23 - RMO JM - #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 3x Prem Plus Amazon and Add-ons (eCommerce, Logistics, Universal) |  |  |  |  | Villaverde, Alfredo |  | 64.25 |  |  | 147789840 |  |  |  | AMO
J918213 |  |  |  | Great Innovations, LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 27 | Standalone | 5/5/23 - RMO JM - #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2x Prem Shipstation, 2x Prem Plus Connector (no Storefronts) messages.NLCORP.552604132.e42a7e0ed0@nlcorp.email.netsuite.com 5/15/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 42 |  |  | 148079312 |  |  |  | New Business
J893850 |  |  |  | Goal3 LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 184 | Standalone | 12/2/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Starter Ebay + Amazon messages.NLCORP.534090914.38d8f2088a@nlcorp.email.netsuite.com 12/8/22 (MC) approved 5 hour overage for PM time that was not included 12/6/22 AF - sent welcome |  | Jakke, Goutham |  |  | Villaverde, Alfredo |  | 2 |  |  | 138621711 |  |  |  | AMO
J914582 |  |  |  | Patriot LLC dba AngelFire Ammunition ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 54 | Standalone | 4/10/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Std BigCommerce messages.NLCORP.548364868.a5a2587710@nlcorp.email.netsuite.com 4/10/23 AF - sent welcome |  | Pitla, Venkatesh |  |  | Villaverde, Alfredo |  | -3 |  |  | 146471166 |  |  |  | AMO
J894959 |  |  |  | Amanda Blu & Co., L.L.C. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 177 | Standalone | 12/7/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem + Amazon messages.NLCORP.534977464.89c7644a44@nlcorp.email.netsuite.com 12/14/22 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 3.75 |  |  | 138937379 |  |  |  | AMO
J909545 |  |  |  | Matevosian Enterprises Inc ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 86 | Standalone | 3/6 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 1 x NS Premium eCommerce Connector - Shopify messages.NLCORP.531086768.6813d3e087@nlcorp.email.netsuite.com <--- Job record email for J890375 Matevosian Enterprises Inc 3/6/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | -2.5 |  |  | 144352561 |  |  |  | AMO
J922496 |  | #POS-NSPOS-ONLY | #POS-NSPOS-ONLY | The SFO Forecast Inc. ¦ Implementation Service - Fixed Bid | OLSHAN, RYAN | Awaiting Assignment |  |  | 6 | Joint | #POS-NSPOS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) |  |  | Bazzani, Emiliano |  | OLSHAN, RYAN |  | 419 |  |  | 149393816 |  |  |  | New Business
J914351 |  |  |  | Crystal Fresh, Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 49 | Standalone | 4/11/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Std Shopify messages.NLCORP.548634851.2b74e23775@nlcorp.email.netsuite.com 4/12/23 AF - sent welcome |  | ALURI, DINESH |  |  | Villaverde, Alfredo |  | 2.5 |  |  | 146403937 |  |  |  | AMO
J892801 |  |  |  | Meizhou Guo Wei Electronics Co., LLC dba SGW Global ¦ Consulting Hours | Preedanon, Melinda | In Progress |  |  | 190 | Standalone | #NSC #UTOPIA-SOW - Scope: 1xPremPlus Shopify Job email: messages.NLCORP.532634312.7187d56bd2@nlcorp.email.netsuite.com JOB_EMAIL: messages.NLCORP.532654594.4fa7e9ba14@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus Ecommerce (Shopify) 3/30/23 - TK - Approved overage (6h) |  | N V, Akhilesh |  |  | Villaverde, Alfredo |  | 8.75 |  |  | 138312256 |  |  |  | AMO
J920241 |  |  |  | SuperOrdinaryCo USA, Inc. ¦ Consulting Time | Rodrigues, Jo Ann | In Progress |  |  | 16 | Standalone | 05/17/23- JAR- Adjusted hours 05/12/23- JR: The discriminator is superordinary 5/12/23 - RMO JM - #NSC #UTOPIA-SOW ¦ Premium Logistics Shipstation Job email: messages.NLCORP.552320126.9ce805a0e3@nlcorp.email.netsuite.com 5/12/2023 AVV: Sent welcome letter to customer. Customer is live with ERP and just purchased NSC. Constrained with time. Copied AMO request email for context. Working on staffing a consultant. |  | Holt, Ebin |  |  | Villaverde, Alfredo |  | 12 |  |  | 148791806 |  |  |  | New Business
J919090 |  |  |  | Savage Brands, LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 24 | Standalone | 5/5/23 - RMO JM - #NSC #STANDALONE (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2x Standard Shopify |  |  |  |  | Villaverde, Alfredo |  | 18.75 |  |  | 148262429 |  |  |  | New Business
J866685 |  |  |  | Tilt Five, Inc. ¦ Implementation Service - Fixed Bid | Villa, Myr Angeli | Monitoring - Post Go-Live | 2023-02-27 | Original | 367 | Standalone | 5/23/2022 - RMO JM - #NSC #STANDALONE NSC Scope: 1xStd eComm Job Email: messages.NLCORP.537133774.e90c042278@nlcorp.email.netsuite.com 5/15/23 MV: Connector is already live. 5/5/2023 AVV: UAT has commenced 4/18/23 MV: Customer is requesting to extend the SOW as they need more time to test the connector before going live. There will also be a delay on UAT due to their busy schedule and bandwidth constraints. Sent them a follow up and proposed schedule for a meeting to help them moving this project forward. 2/6/23: On going implementation. Requested to extend the SOW to 4/13 to continue the implementation until go live. | 2022-11-10 | Sivanepalli N V S, Anuhya |  |  | Villaverde, Alfredo |  | 5.25 |  | 2023-02-27 | 127711897 | 0 | 0 | 196.35 | New Business
J850932 |  |  |  | Game On Chip Company ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | In Progress |  |  | 490 | Standalone | #NSC #STANDALONE ¦ DISC: h6tactical_02 ¦ SCOPE: 2 Standard eCommerce (2 Magento), 1 Premium Logistics (ShipStation) ¦ JOB_EMAIL: messages.NLCORP.489253994.487904a36a@nlcorp.email.netsuite.com 5/3/23 MKP: 1st Magento and Shipstation in progress, 2nd Magento site is not set up yet. 4/12/23 MKP: kickoff call 2/28/23 AVV: Setting customer relationship status to Yellow because of the customer's lack of responsiveness. 02/07/22 MP: NS not ready 0/2/02/22 MP: welcome sent |  | Klein, Adam D |  |  | Villaverde, Alfredo |  | -0.25 |  |  | 119267580 |  |  |  | AMO
J905014 |  |  |  | Head Kandy LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 111 | Standalone | 2/9/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2 Prem Amazon and Shipstation, 1 2x Prem Plus Shopify JOB_EMAIL: messages.nlcorp.541451261.982821507a@nlcorp.email.netsuite.com SCOPE: SuiteApp migration 2/13/23 GD: I created a backup, uninstalled the bundles, installed the NSC SuiteApp, reconnected NS to NSC. Now I'm working on importing the backup back into NS | 2023-02-10 |  |  |  | Villaverde, Alfredo |  | 33.25 |  |  | 142917095 | 0 | 0 | 104.35 | AMO
J852532 |  |  |  | Nexa3D Inc.¦ Implementation Service - Fixed Bid | Preedanon, Melinda | Delayed - Per Other Project |  |  | 479 | Standalone | #NSC #STANDALONE ¦ DISC: nexa3d ¦SCOPE: 1 Premium Plus Ecommerce (Shopify) ¦ JOB_EMAIL: messages.NLCORP.492728956.70b2d54db6@nlcorp.email.netsuite.com 4/18/23 MKP: AMO confirmed they are implementing with a partner and tentative ERP go live is August, this project is going on hold. 3/28/23 MKP: AMO is discussing ERP implementation cost with customer 3/23/23 MKP: prerequisite call with customer, they aren't set up on NetSuite and expressed that they might not continue because their business is too small right now. 3/14/23 AVV: There is a change in the customer main POCs. Restarting engagement with new POC. Resent prerequisites. 3/14/23 AVV: Followed-up with the customer on status of prerequisites completion. 2/28/23 AVV: Setting customer relationship status to yellow due to the customer's overall responsiveness, the various projects they're involved with, turnover in the past, and seemingly insufficient understanding of the scope of this project. #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) -: 1xPrem Plus eCommerce (Shopify) |  | Dunn, Geoffrey |  |  | Villaverde, Alfredo |  | 8.25 |  |  | 120038992 |  |  |  | New Business
J916544 |  |  |  | OG Racing Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 34 | Standalone | 4/28/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ NSC Scope:4x Prem Plus Shopify / Prem Plus Amazon / Prem Shipstation messages.NLCORP.550925149.6a0a6ce0cf@nlcorp.email.netsuite.com 5/1/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 57 |  |  | 147805851 |  |  |  | AMO
J909340 |  |  |  | The Green Pet Shop Enterprises, LLC ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 86 | Standalone | 3/8/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 3x Premium Plus Shopify messages.NLCORP.544541691.51ab87b5de@nlcorp.email.netsuite.com 3/8/23 AF - sent welcome |  | Nannaware, Anurag |  |  | Villaverde, Alfredo |  | 0.75 |  |  | 144338405 |  |  |  | AMO
J901458 |  |  |  | Betenbough Homes, LLC ¦ Consulting Time | Preedanon, Melinda | Monitoring - Post Go-Live | 2023-05-16 | Actual | 134 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: elevatebuildingsupplyllc ¦ SCOPE: 1 Premium Plus Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.539114938.863dca7f7a@nlcorp.email.netsuite.com 5/16/23 MKP: live with order, fulfillment, and product sync 4/28/23 MKP: kickoff with new FC 4/5/23 MKP: unsuccessful kickoff call; customer was unhappy that consultant didn't have their camera on during call; requested consultant reassignment 3/31/23 MKP: SuiteApp issue resolved, scheduling kickoff 3/14/23 MKP: engineer working on defect, on hold until finished 2/22/23 MKP: resource reassignment, still issues uninstalling SuiteApp 2/7/23 MKP: issues uninstalling SuiteApp (Case# 5039144) 01/23/23 MKP: welceome email sent 1/20/25 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus eCommerce Connector - Shopify | 2023-04-28 | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo | 2023-05-16 | -1.25 |  |  | 141484363 | 18 | 18 | 27.35 | AMO
J919850 |  |  |  | MUVZ, Inc. ¦ Implementation Service - Fixed Bid | Waris, Clare | In Progress |  |  | 22 | Standalone | #NSC #UTOPIA-SOW ¦ DISC: ¦ SCOPE: Netsuite Premium Plus eCommerce Connector Amazon, Netsuite Premium AddOn Seller Inbound Shipping Receipts Only Connector Amazon ¦ JOB EMAIL: messages.nlcorp.552351736.9627f856a9@nlcorp.email.netsuite.com 16-May-2023 (MC) overage approved 5/15/23 CEW: Welcome email sent 5/10/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon and Premium AddOn Seller Inbound Shipping Receipts Only Connector Amazon |  |  |  |  | Villaverde, Alfredo |  | 24.5 |  |  | 148623676 |  |  |  | AMO
J902424 |  |  |  | Spectrum Color, Inc. ¦ Consulting | Farmer, Andrew | In Progress |  |  | 122 | Standalone | 1/31/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Shopify messages.NLCORP.540387924.5eecdf7610@nlcorp.email.netsuite.com 4/25/23 AF - sent follow up on closing job if we do not hear back 2/1/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 6.5 |  |  | 142162103 |  |  |  | AMO
J919123 |  |  |  | Wintis Corp ¦ Consuliting Time | Preedanon, Melinda | In Progress |  |  | 22 | Standalone | #NSC #UTOPIA-SOW #DELAYED ¦ DISC: wintiscorp ¦ SCOPE: 1 Premium Plus Logistics (Amazon MCF) ¦ JOB EMAIL: messages.NLCORP.551942254.bcd735a257@nlcorp.email.netsuite.com 5/12/23 MKP: customer not ready to proceed until mid-June 5/10/23 MKP: welcome email 5/9/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Amazon Multi-Channel Fulfillment 3PL Premium Plus Logistics Connector |  | Archer, Nathaniel |  |  | Villaverde, Alfredo |  | 13.5 |  |  | 148276460 |  |  |  | AMO
J902193 |  |  |  | Newpro Corporation ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 127 | Standalone | 1/24/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ 2x Magento JOB_EMAIL: messages.NLCORP.539818080.16f120c8cd@nlcorp.email.netsuite.com SCOPE: 2 Premium Plus Ecommerce (2 Magento) |  |  |  |  | Villaverde, Alfredo |  | 17.75 |  |  | 142012244 |  |  |  | AMO
J910839 |  |  |  | Bindertek ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 71 | Standalone | 3/23/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Shipstation messages.NLCORP.546847496.378044847e@nlcorp.email.netsuite.com 5/24/23 AF - setup mostly completed, however it only just came out that the client wants two fields in the item fulfillment record, the info needed to be sent was 3rd party billing account number and zip code. We cannot map those fields (as they are not custom fields) from Netsuite to Shipstation. customer is requesting a refund, reached out to AMO. 29-Mar-2023 (MC) overage approved 3/28/23 AF - sent welcome |  | N V, Akhilesh |  |  | Villaverde, Alfredo |  | 6 |  |  | 145252928 |  |  |  | AMO
J894578 |  |  |  | NK International Trading, LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 178 | Standalone | 12/7/22 - RMO JM - #NSC #STANDALONE ¦ Prem + Amazon messages.NLCORP.534329785.80690eb7d1@nlcorp.email.netsuite.com 12/8/22 AF - sent welcome | 2023-01-05 |  |  |  | Villaverde, Alfredo |  | 3.75 |  |  | 138869741 | 0 | 0 | 140.35 | AMO
J894517 |  |  |  | DanielHouse Studios, LLC ¦ Consulting Time | Preedanon, Melinda | Monitoring - Post Go-Live |  |  | 183 | Standalone | #NSC #STANDALONE ¦ DISC: danielhousestudiosllc ¦ SCOPE: 1 Single Tier Upgrade Starter -> Standard Ecommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.533705602.391e2b37be@nlcorp.email.netsuite.com 5/8/23 MKP: closing email 4/5/23 MKP: configurations complete, requested longer UAT because developer is out of town 02/30/23 (MC) overage approved 12/22/22 (MC) overage approved 12/14/22 MKP: kickoff call 12/8/22 MKP: welcome email 12/2/22 - RMO JM - #NSC (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Upgrade to full product sync from Starter Shopify | 2022-12-14 |  |  |  | Villaverde, Alfredo |  | 2.5 |  |  | 138864357 | 0 | 0 | 162.35 | AMO
J912173 |  |  |  | Michael Roger, Inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress | 2023-05-12 | Actual | 62 | Standalone | 4/4/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Amazon messages.NLCORP.547742936.f03d0fdcea@nlcorp.email.netsuite.com 06-Mar-2023 (MC) overage approved 4/4/23 AF - sent welcome 5/10/23 GD - Kickoff call 5/12/2023 GD - Provided UAT and Go LIve instructions | 2023-05-10 | Dunn, Geoffrey |  |  | Villaverde, Alfredo | 2023-05-12 | 6.25 |  |  | 145963983 | 2 | 2 | 15.35 | AMO
J905906 |  |  |  | Fair Anita ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 99 | Standalone | 2/22/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Big Commerce messages.NLCORP.543116777.78a5522223@nlcorp.email.netsuite.com 5/9/23 AF - We are done with the initial setup and order mapping and had issues with the tax setup. 4/18/23 AF - checked in on prereq status, client states some resources out of town 2.25.23 MK - Overage of 5 hours approved for project management hours. Approved by VL Meenakshi Krishnan. Job Record has been updated. 2/24/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | -1 |  |  | 143454320 |  |  |  | AMO
J905152 |  |  |  | Strawberry Hill Povitica Inc. ¦ Consulting Time | Farmer, Andrew | Monitoring - Post Go-Live | 2023-05-10 | Actual | 111 | Standalone | 2/13/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦Premium Plus Amazon messages.NLCORP.542688089.db65f2ad28@nlcorp.email.netsuite.com 21-Feb-2023 (MC) overage approved 2/21/23 AF - sent welcome 5/10/23 - GD - Send UAT doc and go live instructions for Amazon and BigCommerce | 2023-03-01 |  |  |  | Villaverde, Alfredo | 2023-05-10 | -4.25 |  |  | 142991438 | 70 | 70 | 85.35 | AMO
J885170 |  |  |  | Outdoor Sports Center ¦ Consulting Time | Preedanon, Melinda | In Progress | 2022-11-30 | Actual | 244 | Standalone | 9/30/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Shopify JOB_EMAIL: messages.NLCORP.527340298.f0494515ad@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus Ecommerce (Shopify) 4/26/23 MKP: confirmed live on NSC 11/30/22 MKP: closing call 10/19/22 MKP: kickoff call 10/7/22 (MC) approved overage 10/5/22 MKP: welcome email 11/29/22 (MC) approved additional 4 hour overage | 2022-10-19 | Satra, Ankit |  |  | Villaverde, Alfredo | 2022-11-30 | 2 |  |  | 135223254 | 43 | 43 | 218.35 | AMO
J870467 |  | #POS-SCIS-PLUSCUSTOMIZATION | #POS-SCIS-PLUSCUSTOMIZATION | Forest Lawn Memorial-Park Association ¦ Implementation Service - Fixed Bid | Ueckert, Brant | In Progress | 2023-09-01 | Revised | 363 | Joint | #POS-SCIS-PLUSCUSTOMIZATION (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 04132023 BU: Customer has been delivered 56 week third party integration of Sales Force Commerce. We are building the FDDs for the deed management and i am extending the job and new go live date for this job. 04012023 BU: Customer has setup two meetings with third party vendors for integration and build of Sales Force Commerce. 02152023 BU: Customer Onsite scheduled for Deed management ON 03/06 02062023 BU: Customer WT1 sessions have started. Integration TS team member assigned and weekly calls have started. 01152023 BU: Customer WT1 Sessions are scheduled to begin 02/06 11042022 BU: Customer has provided the COA and we are in the second round of personalization sessions with the customer. 09052022 BU: Customer GL COA not available until 09/19 Canceling personalization sessions until this is completed. 08242022 BU: GL segmentation and GL review calls. Customer is behind on GL chart of accounts and is impacting Schedule for personalization calls. 08192022 BU: Architectural call full customer team. 08022022 BU: Data Migration Kick Off Call 07212022 BU: ACS Introduction and kick off call. 07142022 BU: Full team kick off call. 07072022 BU: SCIS Scoping review call customer facing. 07012022 BU: SOW review call completed 06222022 BU Sales KT Calls completed. 06012022 BU: Customer opening of job and resource assignments. | 2022-07-14 | Jones, Cory | Bazzani, Emiliano |  | Conor, Katharine S |  | 917.5 | 2023-09-01 | 2023-04-03 | 128523233 | 0 | 0 | 315.35 | New Business
J885193 |  |  |  | MaryRuth Organics, LLC - Professional Services : Activation - SuiteSuccess for Com | Villa, Myr Angeli | In Progress | 2023-05-30 | Revised | 244 | Standalone | 5/17/23 MV: Moving the go-live to 5/30 due to remaining issues in ERP. 4/28/23 MV: Moving the go-live to 5/15 due to remaining issues in ERP and other website issues impacted by the bundle version upgrade. But the date can be rescheduled earlier once the issues have been resolved. 4/17/23 MV: Versapay has been installed in NS account and now working with the SC website. UAT is in progress. Go live date is 5/1. 3/21/23 MV: Move the go-live date to 5/1 due to customer readiness. 3/14/23 MV: No specific launch date yet. According to the customer, they need more time to set up the Payment Processing Profile in NS account prior to deciding when the site will go live. 1/31/22 MV: UAT is in progress. Go live will likely move to a month as the Payment Processing Profile is not established in NS account yet. 11 Jan 2023 – CS Ops: SOW Expiry being adjusted to align to the signed Estimate Terms. Per NS SSA, Estimate terms supersede the TOS terms, thus making this adjustment to ensure compliance to the SSA. There is no revenue impact from making this adjustment. #SC-PLUSCUSTOMIZATION (tracking tag DO NOT DELETE) 11/30/22 MV: Offline configuration and site development are in progress. Go live will move to 1/3/23 due to client readiness. 10/6/22 - MV: GRC done 10/4 9/26/22 - Sales to PS KT Set | 2022-11-17 | Villa, Myr Angeli |  |  | Cristobal, Kevin S |  | -2.25 | 2023-05-30 | 2023-01-03 | 135230767 | 0 | 0 | 189.35 | AMO
J887330 |  |  |  | Stojo Products Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 236 | Standalone | 10/7/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Shopify JOB_EMAIL: messages.NLCORP.527992850.ff1e4ab3ae@nlcorp.email.netsuite.com SCOPE: 1 Reconfiguration for Shopify connector (import orders as SO/Deposits) | 2022-10-17 |  |  |  | Villaverde, Alfredo |  | 1.75 |  |  | 135918062 | 0 | 0 | 220.35 | AMO
J886963 |  |  |  | Drellishak & Drellishak, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 236 | Standalone | 10/11/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Woocommerce JOB_EMAIL: messages.NLCORP.528283025.758d87eb62@nlcorp.email.netsuite.com SCOPE: 1 Standard Ecommerce (WooCommerce) | 2022-11-15 | Jakke, Goutham |  |  | Villaverde, Alfredo |  | 3.25 |  |  | 135797445 | 0 | 0 | 191.35 | AMO
J837930 |  |  |  | Suwanee Decorative Hardware, Inc. ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 602 | Standalone | #NSC-MAGENTO2 #STANDALONE #PREMIUMPLUS (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) JOB_EMAIL: messages.NLCORP.469853731.ba3e22b979@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus eCommerce (Magento2) 02/28/22 MP: requested 2nd SOW extension | 2021-11-15 |  |  |  | Villaverde, Alfredo |  | 2 |  |  | 109999447 | 0 | 0 | 556.35 | AMO
J903919 |  |  |  | QM USA Corp. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 119 | Standalone | 2/3/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus WooCommerce messages.NLCORP.540680023.5a61f38422@nlcorp.email.netsuite.com 2/3/23 AF - sent welcome |  | N V, Akhilesh |  |  | Villaverde, Alfredo |  | 2.5 |  |  | 142570322 |  |  |  | AMO
J890375 |  |  |  | Matevosian Enterprises Inc ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 213 | Standalone | 11/9/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Amazon 2/7/23 AF - Amazon product sync completed 12/2/22 AF - kicked off 11/9/22 AF - sent welcome | 2022-12-02 |  |  |  | Villaverde, Alfredo |  | 0 |  |  | 137302536 | 0 | 0 | 174.35 | AMO
J905485 |  |  |  | Blendjet ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 104 | Standalone | 2/20/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Standard Connector messages.NLCORP.542831987.209d7d619f@nlcorp.email.netsuite.com 4/25/23 AF - sent follow up 22-FEB-2023 (MC) Overage approved 2/22/23 AF - sent welcome |  |  |  |  | Villaverde, Alfredo |  | 11 |  |  | 143158359 |  |  |  | New Business
J862795 |  |  |  | Transaction Data Systems, Inc. ¦ Implementation Service - Fixed Bid | Preedanon, Melinda | Delayed - Per Customer |  |  | 405 | Standalone | #NSC #STANDALONE ¦ DISC: transactiondatasystems ¦ SCOPE: 1 Standard eCommerce (Shopify) ¦ JOB EMAIL: messages.NLCORP.505689624.1cfadca3a6@nlcorp.email.netsuite.com 3/16/23 MKP: not ready to start until Sept due to other projects: NS ERP and Salesforce integrations. 3/13/2023 AVV: PM followed up with the customer. 2/28/23 AVV: Setting customer relationship status to yellow due to the customer's lack of commitment to this project. The customer is prioritizing other work streams and is not providing a clear timeline on when they will be able to focus on the prerequisites. 1/5/23 MKP: follow up with customer on start date 11/23/22 MKP: follow up with customer on start date 10/26/22 MKP: not ready, SOW extension 9/7/22 MKP: not ready to start; Shopify not ready |  |  |  |  | Villaverde, Alfredo |  | 6.75 |  |  | 126004267 |  |  |  | AMO
J916225 |  |  |  | Gettenberg & Wellisch, L.L.C. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 35 | Standalone | 4/27/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Magento2 messages.NLCORP.550508852.cd9526048c@nlcorp.email.netsuite.com 28-Apr-2023 (MC) overage approved 4/27/23 AF - sent welcome |  | Jakke, Goutham |  |  | Villaverde, Alfredo |  | 13 |  |  | 147578449 |  |  |  | AMO
J865742 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Black Hills Works, Inc. ¦ Implementation Service - Fixed Bid | Zenisek, Nicholas J | In Progress | 2023-03-06 | Actual | 385 | Standalone | #OPI-POS (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) 1/3/22 Met with customer, everything is looking good. Waiting on IT team to run cables for pinpads. We will be going live first in the kitchen then the store. rolling go live. Kitchen only sells 4 items and is card only. So this is a good stress test before we go live in store. 1/18 Continued weekly calls waiting on version to fix issue with PI enabled still. final hurdle for go live 2/1 new bundle installed and testing before go live 2/13 soft go live in a slow store 4.11 another extension requested. final store is now live so i need to wrap up job and final support with this extension 5.19 New CO signed and uploaded. finalizing go live and closing out soon | 2022-06-07 | Zenisek, Nicholas J | Bazzani, Emiliano |  | Bazzani, Emiliano | 2023-03-06 | 50.5 |  | 2023-02-20 | 127027510 | 273 | 273 | 352.35 | AMO
J910761 |  |  |  | Fuzion Sports, LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 72 | Standalone | 3/23/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Shipstation |  | Pitla, Venkatesh |  |  | Villaverde, Alfredo |  | 9.25 |  |  | 145202203 |  |  |  | New Business
J900241 |  |  |  | QCK LLC ¦ Consulting Time | Preedanon, Melinda | In Progress |  |  | 148 | Standalone | 1/9/22 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Plus Shopify JOB_EMAIL: messages.NLCORP.537813005.298be720cd@nlcorp.email.netsuite.com SCOPE: 1 Premium Plus Ecommerce (Shopify) 21-Mar-2023 (MC) overage approved |  |  |  |  | Villaverde, Alfredo |  | 12 |  |  | 140733661 |  |  |  | New Business
J914982 |  |  |  | Cygnet Online, LLC ¦ Consulting Tme | Farmer, Andrew | In Progress |  |  | 49 | Standalone | #Utopia messages.NLCORP.544002744.ed589dbac3@nlcorp.email.netsuite.com 4/12/23 AF - sent welcome 4/18/23 TK - Approved overage (14h) |  |  |  |  | Villaverde, Alfredo |  | 53 |  |  | 146896384 |  |  |  | AMO
J890954 |  |  |  | Handicapped Pets, Inc. ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 206 | Standalone | 11/10/22 - RMO JM - #NSC #STANDALONE ¦ Amazon 05112023 MK - Overage of 10 hours approved to project management and additional troubleshooting of issues Approved by VL Meenakshi Krishnan. Job Record has been updated. 01/24/2023 MK - Overage of 13 hours approved to support pending sync issues. Approved by VL Meenakshi Krishnan. Job Record has been updated. 11/10/2022 MK - Overage of 5 hours added for project management. Approved by VL Meenakshi Krishnan. Job record has been updated. 11/10/22 AF - sent welcome | 2022-12-01 |  |  |  | Villaverde, Alfredo |  | 6 |  |  | 137416187 | 0 | 0 | 175.35 | AMO
J912948 |  |  |  | Show Cats, LLC ¦ Implementation Service - Fixed Bid | Farmer, Andrew | In Progress |  |  | 52 | Standalone | 4/12/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Premium Shopify messages.NLCORP.549467413.0e51d00621@nlcorp.email.netsuite.com 4/19/23 AF - Sent welcome |  | Buenavista, Josiah Frances |  |  | Villaverde, Alfredo |  | 7.5 |  |  | 146137112 |  |  |  | AMO
J914951 |  |  |  | RoboNation, Inc. ¦ Consulting Time | Farmer, Andrew | In Progress |  |  | 49 | Standalone | 4/17/23 - RMO JM - #NSC #UTOPIA-SOW (TRACKING TAG – DO NOT DELETE – KEEP AT TOP OF EXEC UPDATE) ¦ Prem Plus Shopify messages.NLCORP.549331052.faa42e3b0a@nlcorp.email.netsuite.com 4/18/23 AF - sent welcome |  | Sumudlayon, Via Marie |  |  | Villaverde, Alfredo |  | 12.5 |  |  | 146888258 |  |  |  | AMO
J908140 |  | #POS-SCIS-ONLY | #POS-SCIS-ONLY | Blush Lingerie Inc ¦ Implementation Service - Fixed Bid | Zenisek, Nicholas J | In Progress |  |  | 87 | Standalone | #POS-SCIS-ONLY (TRACKING TAG - DO NOT DELETE - KEEP AT TOP OF EXEC UPDATE) |  | Zenisek, Nicholas J |  |  | Bazzani, Emiliano |  | 30 |  |  | 144178789 |  |  |  | AMO
Total | [8 empty] | 94,527 | [8 empty] | 20,325.95 |  |  | 2147483647 | 6,471.0 | 6471 | 42,949.55
Note on AB27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: checkouts can have input fields